## Continuity
Amendment | Topics | Council Score | Staff Weight | 2019-09-01 | 2019-12-01 | 2020-03-01 | 2020-06-01 | 2020-09-01 | 2020-12-01 | 2021-03-01 | 2021-06-01 | 2021-09-01 | 2021-12-01
SG AF3 | Blueline Tilefish | 71 | 0 | bar: 2019-09-01 to 2019-12-01
SG RA33 | Red Snapper Season Mods | 52 | 0 | bar: 2019-09-01 to 2019-12-01
CMP Framework 8 | KM Trip Limits in Season 2 | 62 | 0 | bar: 2019-09-01 to 2019-12-01
CMP Framework 9 | Spanish Mackerel Trip Limits |  | 1 | bar: 2019-09-01 to 2020-03-01
DW A10 | Dolphin ACL sharing, OY, etc. | 57 | 4 | bar: 2019-09-01 to 2019-12-01; 2020-06-01 to 2021-03-01
SG RA31 | Recreational AMs | 62 | 4 | bar: 2019-12-01; 2020-12-01 to 2021-06-01
DW 12 | Bullet & Frigate ecosystem | 47 | 3 | bar: 2019-09-01 to 2020-09-01
Shrimp 11 | Shrimp Transit Provisions |  | 1 | bar: 2019-12-01 to 2020-03-01
| Future Allocation Discussions | 45 | 5 | bar: 2020-03-01
| Unassessed Species ABCs/Alloc |  | 5 | bar: 2020-03-01 to 2021-03-01
| Greater Amberjack Assess/Alloc |  | 6 | bar: 2020-06-01 to 2021-06-01
| Red Porgy Assess/Alloc |  | 6 | bar: 2020-06-01 to 2021-06-01
| Yellowtail Snapper Assess/Alloc |  | 6 | bar: 2020-06-01 to 2021-06-01
| King Mackerel Assess/Alloc |  | 6 | bar: 2020-06-01 to 2021-06-01
| Golden Tilefish Assess/Alloc |  | 6 | bar: 2020-12-01 to 2021-12-01
| Snowy Grouper Assess/Alloc |  | 6 | bar: 2020-12-01 to 2021-12-01
SG RA34 | NC/SC SMZs | 39 | 3* | bar: 2020-03-01 to 2020-06-01
C 10 | Oculina Extension | 38 | 0 | bar: 2020-06-01 to 2021-09-01
SG A48 | Wreckfish ITQ Modernization | 51 | 6 | bar: 2020-06-01 to 2021-06-01
| Com Electronic Logbooks | 56 | 6
SG A46 | Rec Permit & Reporting | 61 | 6 | 2020-06-01: CHIP; 2021-03-01: Weight
SL RA5 | SG1 & lobster tailing permits | 45 | 6 | 2020-06-01: CHRISTINA; 2021-03-01: 0; 2021-06-01: Complete
SG 45/GC 11/Sa 4/C 11 | ABC Control Rule | 38 | 5 | 2020-06-01: JOHN; 2021-03-01: 1; 2021-06-01: Ready to approve or not much work left
| Deep H2O Species Allocation | 35 | 6 | 2020-06-01: MYRA; 2021-03-01: 2; 2021-06-01: Anaylsis complete, writing is well underway
SG A44 | YT Snapper long term | 34 | 6 | 2020-06-01: BRIAN; 2021-03-01: 3; 2021-06-01: Data are available, analysis ongoing
SG 26/DW 3/CMP 21/GC 7 | Bycatch Reporting | 26 | 5 | 2021-03-01: 4; 2021-06-01: Still awaiting data, a lot of work still to do
| Almaco Jack White Paper |  | 6 | 2021-03-01: 5; 2021-06-01: Just beginning
| Mackerel Port Meetings |  | 6 | 2021-03-01: 6; 2021-06-01: Not yet started
[10 empty] | 3* | No or limited quantitative data, but ongoing writing and qualitative analysis