## READ ME
Attachment 22: October 2020 SSC Meeting
Navigating this workbook and worksheet descriptions
Worksheet: HOW WORKLOAD IS ESTIMATED: Summary of how the assesment project workload for each Council meeting is tabulated in the remaining sheets. Based on the Council guidance to address at most 6 FMPs per meeting.
Worksheet: ASSESSMENT PRIORITY APPROACH: This is a proposed future workplan for allocating the resources (Staff and Council meeting discussion time) available. This approach addresses FMP projects for recent and upcoming assessements and was presented at the August 7 2020 Executive Committee meeting.
August 7 Executive Committee Guidance: The Committee reviewed this document and supported the overall approach.
The Committee recommended moving ahead with the assessment priority workplan option with the following:
(1) Include additional work related items that require staff time and council discussion time, such as white papers or appointments, in the planning process. The target Council meeting workload, with these topics added, is 8 or fewer.
and
(2) Request Council input on whether to add Coral 10, CHAPC modifications or the ABC Control Rule amendment to the workplan in September 2020.
Additional notes:
The Snowy Grouper assessment was delayed and will not be reviewed by the SSC in October. If we wait to review in April, the SSC will have 4 assessment to consider (Snowy, Gag, Tilefish, Red Snapper) and the Council will receive all 4 in June. Given that is excessive for both the SSC and the Council, staff recommends holding an SSC Webinar to review Snowy prior to the March Council meeting, and presenting results to the Council in March.

## HOW WORKLOAD IS ESTIMATED
Example discussion level at various stages of FMP development.
And Color Coding Scheme in the following sheets
Type of Discussion | Workload Estimation Weight | Council Meeting Time
Initial Options Paper | 1 | 1-2h
Options discussions, review AP/SSC comments | 0.5 | 3-4h
Review and approve for Hearing | 0.5 | 3-4h
Address hearing comments | 1 | 1-2h
Final Approval | 1 | 1-2h
Council Meeting Workload Estimation and Time Management Approach
Council previously directed that 6 FMPs were the most that could be addressed in a Council meeting. Over the last several years this has proven to be an accurate estimate.
To address the current excessive workload and backlog of projects, we attempted to refine this some by considering the level of discussion that occurs at different stages of FMP development. For example, the first time the Council considers an amendment and reviews a general options paper will take less discussion time than a later discussion when actions are reviewed and preferred alternatives selected.
We weighted the different discussion stages as either 1 or 0.5. Summing these weights for a meeting gives an estimate of the discussion time needed. Keeping the sum at or below 6 should keep the workload manageable within a single meeting.
Estimating the workload in this manner for several years forward, and through final approval of projects, provides a long-term persepective on the FMP workload. Individual FMP project schedules may need to be adjusted to address future meetings if the workload rating gets too high. It will also allow us to illustrate the impacts on other projects and on future meeting workloads when projects fall behind.

## Assessment Priority Approach
Assessment Priority Approach Proposed Workplan
|  | COUNCIL |  | Actions to be completed prior to the scheduled Council Meeting
Amend # | Amendment | SCORE | SAFMC Lead | 2020-09-20 | 2020-10-20 | 2020-12-20 | 2021-03-01 | 2021-06-01 | 2021-09-01 | 2021-12-01 | 2022-03-01 | 2022-06-01 | 2022-09-01 | 2022-12-01
DW 10 | ACLs, Alloc., AMs, Other | 57 | JohnH | 2020-09-20: Doc; 2020-12-20: PH; 2021-03-01: Doc; 2021-06-01: A
DW 12 | Bullet and Frigate Mack. as EC Sp. | 47 | JohnH | bar: 2020-09-20
SG 50 | Red Porgy Assess/Alloc/Rebuiding | NEW 06/20 | Myra | O |  | Doc | Doc | Doc | PH | Doc | A
SGXX | Red Snapper | NEW 06/21 | JohnH | 2021-06-01: AR; 2021-09-01: O/S; 2021-12-01: PH; 2022-03-01: Doc; 2022-06-01: A
SG 48 | Wreckfish ITQ Modernization | 51 | BC/Christina | 2020-09-20: O/S; 2020-12-20: Doc; 2021-03-01: Doc; 2021-06-01: PH; 2021-09-01: A
| King Mack Assess/Alloc | NEW 06/20 | Christina | 2020-12-20: O; 2021-03-01: S; 2021-06-01: Doc; 2021-09-01: PH; 2021-12-01: doc; 2022-03-01: A | Key to the expected meeting discussion or action
SGA44 | YT Snapper Assess/Allocate/longterm | NEW 12/20 | Myra |  |  | AR | O | S | Doc | PH | doc | A |  |  | AR | Assessment Received by Council
| Greater AJ Assess/Alloc | NEW 06/20 | MikeS | 2020-12-20: O; 2021-03-01: S; 2021-06-01: Doc; 2021-09-01: PH; 2021-12-01: doc; 2022-03-01: A | O | Options paper REVIEW
| Snowy Grouper Assess/Alloc* | NEW 12/20 | TBD | 2021-03-01: AR; 2021-06-01: O; 2021-09-01: S; 2021-12-01: Doc; 2022-03-01: PH; 2022-06-01: A | S | Discuss, Approve for Scoping
| Gag Assess/Alloc | NEW 6/21 | TBD | 2021-06-01: AR; 2021-09-01: O; 2021-12-01: S; 2022-03-01: DOC; 2022-06-01: PH; 2022-09-01: A | Doc | Amend writing/editing/reviewing
| golden Tilefish Assessment | NEW 6/21 | TBD | 2021-06-01: AR; 2021-09-01: O/S; 2021-12-01: Doc; 2022-03-01: PH; 2022-06-01: Doc; 2022-09-01: A | PH | Approve for Public Hearings
Workload Subtotal: Current FMP Projects listed Above |  |  |  | 2.5 |  | 4 | 5.5 | 7 | 7.5 | 6 | 5 | 3 | 1 |  | A | Final Approval
RECURRING & | Selection AP or SSC | bar: 2020-09-20; 2020-12-20; 2021-06-01; 2021-12-01; 2022-06-01; 2022-12-01
SPECIAL TOPICS | Emerg Rule and Exec Order |  |  | 2020-09-20: 0.5
Allocation | bar: 2020-09-20
| Joint WorkGroup Rec Sec 102 |  |  | 2020-10-20: 0.25; 2021-03-01: 0.5
| Rec Items (SG 31 AMs, SG 46 Permits, MFC) |  |  | 2020-10-20: 0.75
INFO PAPER | SG EC SPECIES |  | MYRA | 2020-12-20: 0.5
WORKLOAD SUBTOTAL - Recurring and special topic activities |  |  |  | 2.5 | 1 | 1.5 | 0.5 | 1 | 0 | 1 | 0 | 1 | 0 | 1
SUBTOTAL : Current FMP projects (line 15) + recurring & special topics (Line 22) |  |  |  | 5 | 1 | 5.5 | 6 | 8 | 7.5 | 7 | 5 | 4 | 1 | 1
| OPTION: CHAPC(Coral 10) OR ABC CR? |  |  | 2020-12-20: Doc; 2021-03-01: Doc; 2021-06-01: Doc; 2021-09-01: PH; 2021-12-01: A
TOTAL WORKLOAD |  |  |  | 5 | 1 | 6 | 6.5 | 8.5 | 8 | 7.5 | 5 | 4
* Snowy Grouper was delayed and will be available in early November 2020. Recommend holding an SSC webinar review prior to the March Council meeting. | bar: 2020-09-20 to 2022-03-01
Other Amendments underway, requested, or to address assessments expected in 2022
|  |  |  | COUNCIL |  | FMP TIMELINES IN TERMS OF COUNCIL MEETINGS
Amend # | Amendment | History | SAFMC Lead | SCORE |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
SG Reg 31 | Rec Ams | started |  | 62 |  | FMP TIMELINES IN TERMS OF COUNCIL MEETINGS 1: DOC; FMP TIMELINES IN TERMS OF COUNCIL MEETINGS 2: PH; FMP TIMELINES IN TERMS OF COUNCIL MEETINGS 3: A
SG 46 | Rec Permit/Reporting | started | JohnH | 61 |  | O | S | Doc | Doc | PH | A
Comp XX | Allocation, Unassessed Spp. ABC/ACL | new | BC/Christina | 45 |  | O | S | DOC | Doc | PH | A
SL RA5 | SG1 & lobster tailing permits | new |  | 45
Coral 10 | CHAPC Oculina modification | new | Roger | 38 |  | S | Doc | Doc | PH | A
SG 45/GC 11/Sa 4/C 11 | ABC Control Rule | started | MikeS | 38 |  | O | S | Doc | Doc | PH | A
SG XX | Deep water Species Allocation | new |  | 35
COMPXX | SBRM Amend | new |  |  |  | O | Doc | Doc | PH | Doc | A
CMP Framework 9 | Spanish Mackerel Assessment | NEW 06/22 |  | 2022-06-01
SG XX | Black Sea bass Assessment | NEW 06/22 |  | 2022-06-01
Amend XX | Com Electronic Logbooks | new
DW 13 | Dolphin PLL Fishery | new |  | NEW
Other Activities
info paper | Almaco Jack White Paper | new |  | NA
workshop | Mackerel Port Meetings | new |  | NA
| Scenario Planning | new
Values in these blocks indicate Council discussion and actions.
Orange blocks are 1 workload unit,
Yellow blocks are .5 workload units
Values in these blocks indicate the workload unit