## Sheet1
Amendment | Topics | SERO Staff Lead | Council Staff Lead | IPT Tier | Next Consideration | Begin Dev | Scoping | Actions/Alts | Public Hearing | Select Prefs | Approval | Notes
SG A38 | Blueline Tilefish N of Hatteras | Mary | Roger | V |  | 2015-03-01
SG A42 | Turtle release/SG Framework | Frank | Christina | II |  | 2018-03-01 | 2018-04-18 | 2018-06-18 |  |  | 2019-03-19
SG A44 | YT Snapper long term | Nikhil | John H | V |  | 2016-06-01 | 2016-08-01 | 2016-09-01 | Jan/Feb-17 |  |  | Focus shifted to RA32 Mar-18
SG A46 | Rec Permit & Reporting | Rick/Frank | Chip | V |  | 2017-12-01
SG RA29 | Best Practices & Powerheads | Frank | Christina | III | 2018-09-18 | 2018-03-01 | 2018-08-01 | 2018-09-01 | Spring-19 |  | 2019-09-01
SG RA30 | Reg Grouper Rebuilding | Mary | John H | II | 2018-09-18 | 2018-03-01 |  | 2018-06-01 | 2018-09-01 | 2018-09-01 | 2019-09-01
| Wreckfish ITQ review | Nikhil | Brian | II |  | 2017-06-01 |  |  |  |  | 2019-09-19 | Tier score based on analysis revisions and completion of section writing that is needed. Not an Amendment, but a required review of the catch share program
C 10/S 11/GC 10 | GC Areas/Oculina Ext/transit | Karla | Chip | V |  | 2018-03-01 | [5 empty] | Coral 10/Shrimp 11/Golden Crab 10
CMP 24 | Atlantic SM allocations | Karla | Christina | V |  | 2013-09-01 | 2014-01-01 |  |  |  |  | *Inactive*
DW A10 | Dolphin ACL sharing, OY, etc. | Nikhil | John H | V |  | 2016-06-01 | 2018-08-01 |  |  |  |  | Suspended until new MRIP estimates are available
SG 45/GC 11/Sa 4/C 11 | ABC Control Rule | Nikhil | John C | IV |  | 2016-12-01 | 2019-01-19 |  |  |  |  | SG A45/GC A11/S A4/C A11
SG Reg 31/DW Reg 2 | Recreational AMs | Rick/Frank | Brian | III |  | 2017-12-01 | 2019-01-19 |  |  |  |  | SG RA31/DW RA2 - need to begin work on the amendment and have IPT meet
| Com Electronic Logbooks | Karla | John C | V |  | 2012-12-01 | [5 empty] | *Inactive*
| Bycatch Reporting | Frank | Chip | V |  | 2014-09-01 | [5 empty] | Suspended until NMFS publishes Standard Bycatch Reporting Methodology (SBRM)
| Allocation Trigger Plan | ??? | Brian | III | 2018-12-18 | 2018-12-18 | [5 empty] | Needs to begin in Dec 2018 - Need to have allocation review triggers plan by August 2019.
| Marine Aquaculture Plan | ??? | Roger | V |  | 2018-06-01 | [5 empty] | Need to determine the impact of the latest court ruling as to whether the Council can develop a Marine Aquaculture Plan
Council to work on in March 2019 |  |  |  | Abbreviation Explanations
SG RA30 | Reg Grouper Rebuilding |  |  | SG = Snapper Grouper
SG Reg 31/DW Reg 2 | Recreational AMs |  |  | A = Amendment
DW A10 | Dolphin ACL sharing, OY, etc. |  |  | RA = Regulatory Amendment
SG 42 | Turtle release/SG Framework |  |  | AF = Abbreviated Framework
SG Reg 29 | Best Practices & Powerheads |  |  | C = Coral
| Allocation Trigger Plan |  |  | CMP = Coastal Migratory Pelagics = King Mackerel, Spanish Mackerel, and Cobia
SG 45/GC 11/Sa 4/C 11 | ABC Control Rule |  |  | DW = Dolphin Wahoo
| Wreckfish ITQ Review |  |  | SL = Spiny Lobster
Black bars indicate where not required
Tentative for June 2019 |  |  |  | Tentative for September 2019
SG RA29 | Best Practices & Powerheads |  |  | SG RA29 | Best Practices & Powerheads
| Wreckfish ITQ review |  |  | C 10/S 11/GC 10 | GC Areas/Oculina Ext/transit
C 10/S 11/GC 10 | GC Areas/Oculina Ext/transit |  |  | SG A38 | Blueline Tilefish N of Hatteras
SG A38 | Blueline Tilefish N of Hatteras |  |  | SG 45/GC 11/Sa 4/C 11 | ABC Control Rule
SG 45/GC 11/Sa 4/C 11 | ABC Control Rule |  |  | SG Reg 31/DW Reg 2 | Recreational AMs
SG Reg 31/DW Reg 2 | Recreational AMs |  |  | DW A10 | Dolphin ACL sharing, OY, etc.
DW A10 | Dolphin ACL sharing, OY, etc. |  |  | SG 46 | Rec Permits & Reporting
Allocation Trigger Plan
SG RA30 | Reg Grouper Rebuilding
SG 46 | Rec Permits & Reporting

## Sheet2
Amendment | Topics | IPT Tier | Council Score | March | June | September
SG A38 | Blueline Tilefish N of Hatteras | V
SG A44 | YT Snapper long term | V
SG A46 | Rec Permit & Reporting | V
SG RA29 | Best Practices & Powerheads | III
SG RA30 | Reg Grouper Rebuilding | II
| Wreckfish ITQ review | II
C 10/S 11/GC 10 | GC Areas/Oculina Ext/transit | V
CMP 24 | Atlantic SM allocations | V
DW A10 | Dolphin ACL sharing, OY, etc. | V
SG 45/GC 11/Sa 4/C 11 | ABC Control Rule | IV
SG Reg 31/DW Reg 2 | Recreational AMs | III
| Com Electronic Logbooks | V
| Bycatch Reporting | V
| Allocation Trigger Plan | III
| Marine Aquaculture Plan | V
SG 42 | Turtle release/SG Framework | II | <-- If not approved in March