## HOW WORKLOAD IS ESTIMATED
Example discussion level at various stages of FMP development.
And Color Coding Scheme in the following sheets
Type of Discussion | Workload Estimation Weight | Council Meeting Time
Initial Options Paper | 0.5 | 1-2h
Options discussions, review AP/SSC comments | 1 | 3-4h
Review and approve for Hearing | 1 | 3-4h
Address hearing comments | 0.5 | 1-2h
Final Approval | 0.5 | 1-2h
Council Meeting Workload Estimation and Time Management Approach
Council previously directed that 6 FMPs were the most that could be addressed in a Council meeting. Over the last several years this has proven to be an accurate estimate.
To address the current excessive workload and backlog of projects, we attempted to refine this some by considering the level of discussion that occurs at different stages of FMP development. For example, the first time the Council considers an amendment and reviews a general options paper will take less discussion time than a later discussion when actions are reviewed and preferred alternatives selected.
We weighted the different discussion stages as either 1 or 0.5. Summing these weights for a meeting gives an estimate of the discussion time needed. Keeping the sum at or below 6 should keep the workload manageable within a single meeting.
Estimating the workload in this manner for several years forward, and through final approval of projects, provides a long-term persepective on the FMP workload. Individual FMP project schedules may need to be adjusted to address future meetings if the workload rating gets too high. It will also allow us to illustrate the impacts on other projects and on future meeting workloads when projects fall behind.

## 2022-2024 WorkPlan
Att. 3b | SAFMC 2022-2024 WORKPLAN - INCORPORATING PROJECTS UNDERWAY AND UPCOMING ASSESSMENTS |  |  | 2022 Q4 - December Meeting DRAFT
Amendments with statutory deadline
| Amend # | Amendment | SAFMC Lead | 2022-12-01 | 2023-03-01 | 2023-06-01 | 2023-09-01 | 2023-12-02 | 2024-03-01 | 2024-06-01 | 2024-09-01 | 2024-12-02 |  |  | Amendments that do not respond to a stock assessment
UNDERWAY | SG 51 | Snowy Grouper Assess Response | Allie | bar: 2022-12-01
| SG 53 | Gag Assess Response | Allie | 2022-12-01: DOC; 2023-03-01: A
|  | STATUTORY DEADLINE WORKLOAD SUBTOTAL |  | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SG Reg 35 | SG Release Mort. Reductions (Gear Modifications, Education and Outreach) | Mike | [9 empty] | Changed per SG Committee Discussion. Timeline shortened by 1 quarter. | bar: 2022-12-01 to 2023-03-01
| SG | Long-term RS response (MSE, SG fishery management measures) | TBD | 2024-12-02: O/S | DOC | DOC | DOC | Amendment begins at completion of the MSE
| SG 52 | Golden Tilefish Assess/Blueline Tilefish Mgmt Measure | Roger/Myra | bar: 2022-12-01
| SG 48 | Wreckfish ITQ Modernization | Christina | 2022-12-01: SKIP; 2023-03-01: DOC; 2023-06-01: SKIP; 2023-09-01: A | Every other meeting per Council guidance. Extended 6 months.
| SG 46 | Rec Permit+Reporting | JohnH | O/S | DOC | DOC | PH | DOC | A?
| CMP 33 | Gulf King Mackerel (Gulf is lead) | Christina | 2022-12-01: PH; 2023-03-01: SKIP; 2023-06-01: A
| DW Reg 3 | Dolphin (Recreational Measures) | JohnH | SKIP | DOC | DOC | PH | DOC | A?
|  | Dolphin MSE | SEFSC (JH&JB)
| DW/CMP/SG/RF? | Commercial E-Logbooks | Myra | bar: 2022-12-01 to 2023-03-01
| SG 45/GC 11/DW11 | ABC Control Rule | Mike | bar: 2022-12-01
|  | UNDERWAY FMP WORKLOAD SUBTOTAL |  | 5 | 4 | 1.5 | 2.5 | 1 | 1
PLANNED | SG 44 | YT Snapper Assess Response (Allocations/Management Measures) | Allie | (AP) | O/S | DOC | DOC | PH | DOC | A
| CMP | 2022 Spanish Mackerel Assess Response | Christina | (AP & ADT) | O/S | DOC | DOC | PH | DOC | A
| SG | Black Sea Bass Assess Response (03/23) | TBD |  | (SSC) | AR | (AP) | O/S | DOC | DOC | PH | DOC | A
| DW | Dolphin Wahoo (Pelagic Longline Measures) | JohnH |  | O/S | DOC | DOC | DOC | PH | DOC | A |  |  | Timeline depends on updated Biological Opinion
| SG | Scamp OA Response (12/22) | Allie |  |  | AR | (AP) | O/S | DOC | DOC | PH | DOC | A
| SG/DW | Unassessed Stocks ABC | TBD | 2023-12-02: O/S; 2024-03-01: DOC; 2024-06-01: DOC; 2024-09-01: DOC; 2024-12-02: PH | DOC | A | Begin after ABC CR approved and implemented
| WORKLOAD SUBTOTAL: FMP Projects listed Above. Target is 6 |  |  | 5.5 | 5.5 | 5 | 5.5 | 5.5 | 5.5 | 4.5 | 3.5 | 2
| FMP ITEMS PER MEETING: Target is 8 |  |  | 9 | 9 | 8 | 6 | 8 | 7 | 6 | 4 | 3
| OTHER COUNCIL ACTIVITIES |  |  | 2022-12-01 | 2023-03-01 | 2023-06-01 | 2023-09-01 | 2023-12-01 | 2024-03-01 | 2024-06-01 | 2024-09-01 | 2024-12-01
|  | EVERY MEETING - Liaison, Agency, Staff Reports |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | Selection AP or SSC | KI/CC | 2022-12-01: 0.5; 2023-06-01: 0.5; 2023-12-01: 0.5; 2024-06-01: 0.5; 2024-12-01: 0.5
|  | SEDAR Committee | CC | 2023-03-01: 0.5; 2023-09-01: 0.5; 2024-03-01: 0.5; 2024-09-01: 0.5
|  | Citizen Science Committee | JB | 2023-06-01: 0.5; 2023-12-01: 0.5; 2024-06-01: 0.5; 2024-12-01: 0.5
|  | Habitat Committee | RP | 2022-12-01: 0.5; 2023-03-01: 0.5; 2023-09-01: 0.5; 2024-03-01: 0.5; 2024-09-01: 0.5
|  | Law Enforcement Committee | MB | 2023-06-01: 0.5; 2023-09-01: LEOY; 2024-06-01: 0.5; 2024-09-01: LEOY
|  | Outreach and Communications Committee | KI/NS | 2022-12-01: 0.5; 2023-06-01: 0.5; 2023-12-01: 0.5; 2024-06-01: 0.5; 2024-12-01: 0.5
|  | Scenario Planning | RP | 2022-12-01: 0.5; 2023-03-01: 0.5
|  | FKNMS and WECAFC Dolphin and Flyingfish WG | MB | [9 empty] | *Review at special meeting Sept. 21, 2022 | bar: 2022-12-01
|  | Joint WorkGroup Rec Sec 102 | JC | 2022-12-01: 0.5
|  | False Albacore White Paper | Christina | 2022-12-01: 0.5 | Added per MC Committee guidance
|  | SG Discard White Paper | TBD | bar: 2023-03-01
|  | Habitat Blueprint | MB/JC/RP | [9 empty] | **Suggest review at special meeting | bar: 2023-03-01
|  | 5-year review of EFH | TBD | 2023-03-01: 0.5
| WORKLOAD SUBTOTAL: Recurring and special topic activities |  |  | 3.5 | 3.5 | 2.5 | 1.5 | 2 | 1.5 | 2.5 | 1.5 | 2
| WORKLOAD TOTAL : FMP projects (Line 26) + Recurring & special topics (Line 41). Target is 8 |  |  | 9 | 9 | 7.5 | 7 | 7.5 | 7 | 7 | 5 | 4
Other Amendments underway, requested, or anticipated to address assessments expected in 2023-2024
| Committee | Amendment | Target Start
| DW | Dolphin Wahoo regional management and other items | ? | 2022-12-01: Amendment could address regional management, limited access for com. permit, and FH baglimit slales
| SG | Mutton Snapper Assessment Response (tentative) | 2024-06-01
| SG | Red Grouper Assessment Response (Final 12/23) | 2024-06-01
| SG | Gray Triggerfish Assessment Response | 2024-12-01
| SG | Golden Tilefish Assessment Response | 2024-12-01
| SG | Blueline Tilefish Assessment Response | 2024-12-01
| SG | Vermilion Snapper Assessment Response (postponed Indefinitely)
Spiny lobster & SG permit holder item
Coral AM 10
|  | Update on dolphin related items in the Carribean | Mar-23'
Address sunsetting of SMZs
Other Activities
| Workshop | Mackerel Port Meetings | ?

## General Timeline
Generalized FMP Timeline Example
Illustrates a signficant FMP Amendment - not a framework to update ACL
Plan Code | Clock | eg mo | Council Meeting Activity | Note | More Info
AR | 1 | June | Assessment Report Presented (or FMP started formally) | Also present general fishery info - landings+effort trends, recent years, by state, season, etc; catch per trip frequency, recent mgmt changes or AMs implemented | When initiated by an AR: Provide ACL options. - there really are not that many, at least for FMPs without allocation changes. When not an AR: discuss the problem Council wishes to solve and why.
(AP),(SSC) | 4 | Oct | AP or SSC review | Include in council meet schedule to show work is progressing, explain why skipping a meeting. Deadline to Obtain official IPT dataset for analysis | Intent-bring in AP sooner, help develop response to stock condition or the problems to solve, help develop items to scope
O/S | 6 | Dec | Present Options, Approve for Scoping | Council select the preferred ACL at this meeting | Approve ACLs by this meeting - critical to the evaluations of specific actions that will follow
DOC | 9 | March | Review Actions-Alternatives | Review scoping comments, finalize range of actions and alternatives
DOC | 12 | June | Review Actions-Alternatives, Select Preferreds | Review evaluation of actions and alternatives. Select preferred options where appropriate and feasible. Need for this or an additioanl meeting of this type determined by FMP complexity and number of actions. | Consider dividing topics across meeting for a complex FMP with many actions - e.g., one meeting on rec topics, one on comm topics, so that if several meetings needed, avoid starting each meeting by discussing action 1 and going over the entire FMP in action order. May add in additional SSC or AP meetings between OS and PH as needed
PH | 15 | Sept | Review Actions-Alternatives, Select preferreds, and Approve for hearings | Review evaluation of actions and alternatives, select preferred alternatives for hearing
doc | 18 | Dec | Review hearing comments, revise preferreds
A | 21 | March | review any additional analysis, approve for submission | Need to have codified text in time to review
| 24 | June | FMP Submitted by | final draft, codified, etc - submit before the next meeting