## HOW WORKLOAD IS ESTIMATED
Example discussion level at various stages of FMP development.
And Color Coding Scheme in the following sheets
Type of Discussion | Workload Estimation Weight | Council Meeting Time
Initial Options Paper | 0.5 | 1-2h
Options discussions, review AP/SSC comments | 1 | 3-4h
Review and approve for Hearing | 1 | 3-4h
Address hearing comments | 0.5 | 1-2h
Final Approval | 0.5 | 1-2h
Council Meeting Workload Estimation and Time Management Approach
Council previously directed that 6 FMPs were the most that could be addressed in a Council meeting. Over the last several years this has proven to be an accurate estimate.
To address the current excessive workload and backlog of projects, we attempted to refine this some by considering the level of discussion that occurs at different stages of FMP development. For example, the first time the Council considers an amendment and reviews a general options paper will take less discussion time than a later discussion when actions are reviewed and preferred alternatives selected.
We weighted the different discussion stages as either 1 or 0.5. Summing these weights for a meeting gives an estimate of the discussion time needed. Keeping the sum at or below 6 should keep the workload manageable within a single meeting.
Estimating the workload in this manner for several years forward, and through final approval of projects, provides a long-term persepective on the FMP workload. Individual FMP project schedules may need to be adjusted to address future meetings if the workload rating gets too high. It will also allow us to illustrate the impacts on other projects and on future meeting workloads when projects fall behind.

## 2025-2028 WorkPlan
SAFMC 2025-2028 WORKPLAN - INCORPORATING PROJECTS UNDERWAY AND UPCOMING ASSESSMENTS
| Amend # | Amendment | SAFMC Lead | 2025-03-01 | 2025-06-01 | 2025-09-01 | 2025-12-01 | 2026-03-02 | 2026-06-01 | 2026-09-01 | 2026-12-01 | 2027-03-01 | 2027-06-01 | 2027-09-01 | 2027-12-01 | 2028-03-01 | 2028-06-01 | 2028-09-01 | 2028-12-01
UNDERWAY | SG | Long-term RS response (MSE, SG fishery management measures) | TBD | 2025-03-01: O/S; 2025-06-01: DOC; 2025-09-01: DOC; 2025-12-01: DOC; 2026-03-02: PH; 2026-06-01: DOC; 2026-09-01: DOC; 2026-12-01: A
| SG 56 | Black Sea Bass Assessment Response | Mike | 2025-03-01: PH; 2025-06-01: DOC; 2025-09-01: A
| SG 46 | Private Recreational Permitting and Education | JohnH | 2025-03-01: PH; 2025-06-01: DOC; 2025-09-01: DOC; 2025-12-01: A
| SG 44 | YT Snapper Assessment Response (S96 11/24)(Catch Levels/Allocations) | Allie | 2025-03-01: AR (AP); 2025-06-01: O/S; 2025-09-01: DOC; 2025-12-01: DOC; 2026-03-02: PH; 2026-06-01: DOC; 2026-09-01: A
| DW Reg 3 | Dolphin (Recreational Measures + MSE Response) | JohnH | 2025-03-01: Dolphin MSE; 2025-12-01: DOC; 2026-03-02: DOC; 2026-06-01: PH; 2026-09-01: DOC; 2026-12-01: A
| SG/CMP/DW | For-Hire Limited Entry | JohnH/Myra | 2025-03-01: O/S; 2025-06-01: DOC; 2025-09-01: DOC; 2025-12-01: DOC; 2026-03-02: PH; 2026-06-01: DOC; 2026-09-01: A
| SG/CMP/DW | SEFHIER Revisions | Myra/JohnH | 2025-03-01: DOC; 2025-06-01: DOC; 2025-09-01: DOC; 2025-12-01: PH; 2026-03-02: DOC; 2026-06-01: A
PLANNED | CMP | Plan AM Spanish Mackerel Assessment Response | Christina | 2025-06-01: O/S; 2025-09-01: DOC; 2025-12-01: DOC; 2026-03-02: PH; 2026-06-01: DOC; 2026-09-01: A
| SG | Mutton Snapper Assessment Response (S79, 10/24) | TBD | 2025-03-01: AR (AP); 2025-06-01: O/S; 2025-09-01: DOC; 2025-12-01: DOC; 2026-03-02: PH; 2026-06-01: DOC; 2026-09-01: A
| SG | Golden Tilefish Assement Response (S89, 7/24) | TBD | 2025-06-01: O/S; 2025-09-01: DOC; 2025-12-01: DOC; 2026-03-02: PH; 2026-06-01: DOC; 2026-09-01: A
| SG | Blueline Tilefish Assessment Response (S92, 11/24) and Align Rec DW Species Seasons | TBD | 2025-06-01: AR; 2025-12-01: O/S; 2026-03-02: DOC; 2026-06-01: DOC; 2026-09-01: PH; 2026-12-01: DOC; 2027-03-01: A
| SG | Unassessed Stocks ABC | Mike | 2025-06-01: O/S; 2025-09-01: DOC; 2025-12-01: DOC; 2026-03-02: PH; 2026-06-01: DOC; 2026-09-01: A
| SG | Hogfish Assessment Response | TBD | 2026-03-02: AR; 2026-09-01: O/S; 2026-12-01: DOC; 2027-03-01: DOC; 2027-06-01: PH; 2027-09-01: DOC; 2027-12-01: A
| SG | Black Grouper Assessment Response | TBD | 2026-06-01: AR; 2026-12-01: O/S; 2027-03-01: DOC; 2027-06-01: DOC; 2027-09-01: PH; 2027-12-01: DOC; 2028-03-01: A
| SG | Gag Assessment Response | TBD | 2027-06-01: AR; 2027-12-01: O/S; 2028-03-01: DOC; 2028-06-01: DOC; 2028-09-01: PH; 2028-12-01: DOC | A
| SG | Red Grouper Assessment Response | TBD | 2027-12-01: AR; 2028-06-01: O/S; 2028-09-01: DOC; 2028-12-01: DOC | PH | DOC | A
| SG | Vermilion Assessment Response | TBD | 2027-12-01: AR; 2028-06-01: O/S; 2028-09-01: DOC; 2028-12-01: DOC | PH | DOC | A
| SG | Snowy Grouper Assessment Response | TBD | 2028-06-01: AR; 2028-12-01: O/S | DOC | DOC | PH | DOC | A
| SG | Black Sea Bass Assessment Response | TBD | 2028-06-01: AR; 2028-12-01: O/S | DOC | DOC | PH | DOC | A
| CMP | King Mackerel Assessment Response | Christina | 2028-06-01: AR; 2028-12-01: O/S | DOC | DOC | PH | DOC | A
| DW | Dolphin Wahoo PLL Measures, Regional Management, and Other Items | JohnH | 2027-09-01: O/S; 2027-12-01: DOC; 2028-03-01: DOC; 2028-06-01: PH; 2028-09-01: DOC; 2028-12-01: A
| SG | SMZ Sunset | TBD | 2026-09-01: O/S; 2026-12-01: DOC; 2027-03-01: DOC; 2027-06-01: PH; 2027-09-01: DOC; 2027-12-01: A
| SG and Spiny Lobster | Commercial Fishery Issues | TBD | 2026-12-01: O/S; 2027-03-01: DOC; 2027-06-01: DOC; 2027-09-01: PH; 2027-12-01: DOC; 2028-03-01: A
| Coral | Deepwater Coral HAPC | Kathleen | 2027-03-01: O/S; 2027-06-01: DOC; 2027-09-01: DOC; 2027-12-01: PH; 2028-03-01: DOC; 2028-06-01: A
| SG | Scamp Assessment Response FW | TBD | 2026-12-01: O/S; 2027-03-01: DOC; 2027-06-01: PH; 2027-09-01: A
| Comprehensive | Standard Bycatch Reporting Methodology Update | TBD | 2026-09-01: DOC; 2026-12-01: O/S; 2027-03-01: DOC; 2027-06-01: PH; 2027-09-01: DOC
| TBD | Data limited IRA outcome | TBD | 2027-03-01: O/S; 2027-06-01: DOC; 2027-09-01: DOC; 2027-12-01: PH; 2028-03-01: DOC; 2028-06-01: A

## General Timeline
Generalized FMP Timeline Example
Illustrates a signficant FMP Amendment - not a framework to update ACL
Plan Code | Clock | eg mo | Council Meeting Activity | Note | More Info
AR | 1 | June | Assessment Report Presented (or FMP started formally) | Also present general fishery info - landings+effort trends, recent years, by state, season, etc; catch per trip frequency, recent mgmt changes or AMs implemented | When initiated by an AR: Provide ACL options. - there really are not that many, at least for FMPs without allocation changes. When not an AR: discuss the problem Council wishes to solve and why.
(AP),(SSC) | 4 | Oct | AP or SSC review | Include in council meet schedule to show work is progressing, explain why skipping a meeting. Deadline to Obtain official IPT dataset for analysis | Intent-bring in AP sooner, help develop response to stock condition or the problems to solve, help develop items to scope
O/S | 6 | Dec | Present Options, Approve for Scoping | Council select the preferred ACL at this meeting | Approve ACLs by this meeting - critical to the evaluations of specific actions that will follow
DOC | 9 | March | Review Actions-Alternatives | Review scoping comments, finalize range of actions and alternatives
DOC | 12 | June | Review Actions-Alternatives, Select Preferreds | Review evaluation of actions and alternatives. Select preferred options where appropriate and feasible. Need for this or an additioanl meeting of this type determined by FMP complexity and number of actions. | Consider dividing topics across meeting for a complex FMP with many actions - e.g., one meeting on rec topics, one on comm topics, so that if several meetings needed, avoid starting each meeting by discussing action 1 and going over the entire FMP in action order. May add in additional SSC or AP meetings between OS and PH as needed
PH | 15 | Sept | Review Actions-Alternatives, Select preferreds, and Approve for hearings | Review evaluation of actions and alternatives, select preferred alternatives for hearing
doc | 18 | Dec | Review hearing comments, revise preferreds
A | 21 | March | review any additional analysis, approve for submission | Need to have codified text in time to review
| 24 | June | FMP Submitted by | final draft, codified, etc - submit before the next meeting