## HOW WORKLOAD IS ESTIMATED
Example discussion level at various stages of FMP development.
And Color Coding Scheme in the following sheets
Type of Discussion | Workload Estimation Weight | Council Meeting Time
Initial Options Paper | 0.5 | 1-2h
Options discussions, review AP/SSC comments | 1 | 3-4h
Review and approve for Hearing | 1 | 3-4h
Address hearing comments | 0.5 | 1-2h
Final Approval | 0.5 | 1-2h
Council Meeting Workload Estimation and Time Management Approach
Council previously directed that 6 FMPs were the most that could be addressed in a Council meeting. Over the last several years this has proven to be an accurate estimate.
To address the current excessive workload and backlog of projects, we attempted to refine this some by considering the level of discussion that occurs at different stages of FMP development. For example, the first time the Council considers an amendment and reviews a general options paper will take less discussion time than a later discussion when actions are reviewed and preferred alternatives selected.
We weighted the different discussion stages as either 1 or 0.5. Summing these weights for a meeting gives an estimate of the discussion time needed. Keeping the sum at or below 6 should keep the workload manageable within a single meeting.
Estimating the workload in this manner for several years forward, and through final approval of projects, provides a long-term persepective on the FMP workload. Individual FMP project schedules may need to be adjusted to address future meetings if the workload rating gets too high. It will also allow us to illustrate the impacts on other projects and on future meeting workloads when projects fall behind.

## 2025 - 2027 WorkPlan
| SAFMC 2025-2027 WORKPLAN - INCORPORATING PROJECTS UNDERWAY AND UPCOMING ASSESSMENTS |  |  |  | 2025 Q3 to Q4- Revised per the Council's September 2025 Meeting
Amendments with statutory deadline
| Amendment # | Topic | SAFMC Lead | SERO Priority | 2025-12-01 | 2026-03-02 | 2026-06-03 | 2026-09-04 | 2026-12-05 | 2027-03-06 | 2027-06-07 | 2027-09-08 | 2027-12-09 |  | Amendments that do not respond to a stock assessment, change to catch level recommendations, or regulatory deadline
UNDERWAY |  | STATUTORY DEADLINE WORKLOAD SUBTOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Indicates that action is being taken but will not be discussed at the Council meeting (no time allocated toward the workload calculations)
| SG | Long-term SG response (MSE, SG management measures, aggregate rec. limits) | Chip & TBD |  | S | S | DOC | DOC | PH | DOC | A |  |  | Removed red snapper aspect since state management is being pursued. Added rec aggregate limits. Timeline and amendment documentation will vary as the MSE is further developed. Documentation early in the process will differ from the Council's typical decsion documents.
| SG Reg 37 | Black Sea Bass management measures | Mike | Primary | bar: 2025-12-01
| SG 44 | Yellowtail Snapper and Mutton Snapper assessment response (Joint w/ Gulf as lead) | Allie |  | 2025-12-01: DOC; 2026-03-02: PH; 2026-06-03: DOC; 2026-09-04: A
| SG Abv FW 5 | Blueline Tilefish assessment response | Christina |  | 2025-12-01: PH/A
| DW Reg 3 | Dolphin size limit and recreational retention limits | JohnH |  | 2026-06-03: DOC; 2026-09-04: DOC; 2026-12-05: PH; 2027-03-06: DOC; 2027-06-07: A | Timeline depends on MSE modeling results.
| Coral 11/Shrimp 12 | SFAA in Oculina HAPC northern extension | Kathleen & Allie | Secondary | bar: 2025-12-01
| SG 61 | Evaluation of species within the SG FMU | Allie & JohnH |  | 2025-12-01: DOC; 2026-03-02: DOC; 2026-06-03: PH; 2026-09-04: DOC; 2026-12-05: A
| SG 60 | SG commercial fishery amendment | MIke |  | 2025-12-01: DOC; 2026-03-02: PH; 2026-06-03: DOC; 2026-09-04: A
|  | UNDERWAY FMP WORKLOAD SUBTOTAL |  |  | 4 | 3 | 3.5 | 2.5 | 2.5 | 1 | 1 | 0 | 0
PLANNED | SG Abv FW 4 | Golden Tilefish assessment response | Mike |  | 2025-12-01: AR; 2026-03-02: PH/A
| SG | Red Snapper state management | TBD |  |  | S | DOC | DOC | PH | DOC | A |  |  | Added per Council guidance
| SG | Hogfish assessment response | TBD |  |  | AR | S | DOC | DOC | PH | DOC | A
| SG | Black Grouper assessment or MSE response | TBD |  |  |  | AR | S | DOC | DOC | PH | DOC | A
| SG | Sunsetting of SMZs | TBD |  | 2026-06-03: S; 2026-09-04: PH; 2026-12-05: A |  | Timing moved up per Council guidance
| WORKLOAD SUBTOTAL: (FMP AMs listed above. Target max. is 6.) |  |  |  | 4.5 | 4.5 | 6 | 5 | 5.5 | 3 | 3 | 1 | 0.5
| FMP ITEMS PER MEETING: Target maximum is 8 |  |  |  | 8 | 7 | 9 | 9 | 7 | 5 | 5 | 2 | 1
OTHER COUNCIL ACTIVITIES |  | EVERY MEETING - Liaison, Agency, Staff Reports |  |  | 0.25 | 0.5 | 0.25 | 0.5 | 0.25 | 0.5 | 0.25 | 0.5 | 0.25 | Every other meeting for state agency and federal LE updates
|  | AP or SSC Selection (CLOSED) | KI/JC |  | 2025-12-01: 1; 2026-06-03: 0.5; 2026-12-05: 0.5; 2027-06-07: 0.5; 2027-12-09: 0.5 | Increased to a 1 for December 2025
|  | SEDAR Committee | CC |  | 2026-03-02: 0.5; 2026-09-04: 0.5; 2027-03-06: 0.5; 2027-09-08: 0.5
|  | Citizen Science Committee | JB/MW |  | 2025-12-01: 0.5; 2026-06-03: 0.5; 2026-12-05: 0.5; 2027-06-07: 0.5; 2027-12-09: 0.5
|  | Habitat Committee (meeting time in 2025 accounted for under Coral 11/Shrimp 12) | KH |  | 2026-03-02: 0.5; 2026-09-04: 0.5; 2027-03-06: 0.5; 2027-09-08: 0.5
|  | Outreach and Communications Committee | KI/NS |  | 2026-06-03: 0.5; 2026-12-05: 0.5; 2027-06-07: 0.5; 2027-12-09: 0.5
|  | SG Commercial Sub-Committee (timing captured under AM 60) | MS |  | 2025-12-01: 0 | Added per Council guidance
|  | Headboat vessel limit amendment discussion | CC |  | 2026-03-02: 0.5
|  | Setting allocations and catch levels with the inclusion of discards | CC |  | 2026-03-02: 0.5
|  | Innovation plan for the Snapper Grouper fishery | Council Staff |  | 2025-12-01: 0.5 | Added per Council guidance
|  | Snapper Grouper SAFE report | CC |  | 2025-12-01: 0.25
|  | Snapper Grouper MSE results | CC/Blue Matter |  | 2026-12-05: 0.5
|  | Recreational Data Discussion (MRIP, EFP, state efforts, and FH reporting updates) | Council Staff |  | 2025-12-01: 0.5
|  | Standardized Bycatch Reduction Methodology (SBRM) review | TBD |  | 2026-12-05: 0.5
|  | Lines of Communication meetings summary | CW |  | 2025-12-01: 0.25; 2026-03-02: 0.5
|  | Allocation review for species meeting the review trigger policy | JH |  | 2026-03-02: 0.5
|  | Dolphin MSE feedback | SEFSC |  | 2026-03-02: 0.5; 2026-06-03: 0.5; 2026-09-04: 0.5 | Needed to discuss Council feedback for the MSE
| WORKLOAD SUBTOTAL: (Recurring and special topic activities) |  |  |  | 3.25 | 4 | 2.25 | 2 | 2.75 | 1.5 | 1.75 | 1.5 | 1.75
| WORKLOAD TOTAL: ( FMP projects + recurring & special topics. Target is max. is 8) |  |  |  | 7.75 | 8.5 | 8.25 | 7 | 8.25 | 4.5 | 4.75 | 2.5 | 2.25
Other Amendments requested or anticipated in 2025-2027
Committee | Topic | Tentative Start
Deprioritized Amendments
FC | For-Hire Reporting Improvements | TBD
FC | For-hire Limited Entry | TBD
SG | AM 46 Private Recreational Permitting and Education | TBD
SG | Yellowtail Snapper and Mutton Snapper Management Changes | Timing will be discussed once SG 44 is completed
Anticipated Amendments
MC | Spanish Mackerel Assessment Response and Port Meeting Items | TBD pending revised MRIP FES data and updated SM assessment
SG | AM 56 Black Sea Bass Assessment Response | TBD pending stock assessment review
SG | Blueline Tilefish Allocations, Deepwater Species Management Items | TBD pending outcome of discussions between the Mid and SA Councils
SG | Snowy Grouper Assessment Response | 2026-12-01
SG | Align the opening of recreational seasons for deepwater species | Part of the Blueline Tilefish Allocations and Deepwater Species AM
SG | FW AM to examine scamp retention limits | TBD
SL and SG | Spiny lobster & SG permit holder item | 2026-12-01
DW | Dolphin Wahoo Pelagic Longline Measures | Upon completion of Dolphin MSE
DW | Dolphin Wahoo regional management and other items | Upon completion of Dolphin MSE
Coral | Deepwater Coral HAPC Expansion | 2027-03-01
Other Activities
SG | Update Jacks Complex and Spadefish AMs | TBD
SERO Priority Amendments Undergoing Rulemaking
Amendment # | Amendment Name | SERO Priority
SG 55 | Scamp and Yellowmouth Grouper ACLs and Mgmt Measures | Primary
SG FW 36 | On-Demand Pot gear/Gag and Black Grouper Vessel Limits | Primary
SG 48 | Wreckfish ITQ Program Revisions | Secondary
SG 54, DW 4, CMP 35 | Joint Commercial Electronic Logbook | Secondary

## General Timeline
Generalized FMP Timeline Example
Illustrates a signficant FMP Amendment - not a framework to update ACL
Plan Code | Clock | eg mo | Council Meeting Activity | Note | More Info
AR | 1 | June | Assessment Report Presented (or FMP started formally) | Also present general fishery info - landings+effort trends, recent years, by state, season, etc; catch per trip frequency, recent mgmt changes or AMs implemented | When initiated by an AR: Provide ACL options. - there really are not that many, at least for FMPs without allocation changes. When not an AR: discuss the problem Council wishes to solve and why.
(AP),(SSC) | 4 | Oct | AP or SSC review | Include in council meet schedule to show work is progressing, explain why skipping a meeting. Deadline to Obtain official IPT dataset for analysis | Intent-bring in AP sooner, help develop response to stock condition or the problems to solve, help develop items to scope
S | 6 | Dec | Approve for Scoping | Council select the preferred ACL at this meeting | Approve ACLs by this meeting - critical to the evaluations of specific actions that will follow
DOC | 9 | March | Review Actions-Alternatives | Review scoping comments, finalize range of actions and alternatives
DOC | 12 | June | Review Actions-Alternatives, Select Preferreds | Review evaluation of actions and alternatives. Select preferred options where appropriate and feasible. Need for this or an additioanl meeting of this type determined by FMP complexity and number of actions. | Consider dividing topics across meeting for a complex FMP with many actions - e.g., one meeting on rec topics, one on comm topics, so that if several meetings needed, avoid starting each meeting by discussing action 1 and going over the entire FMP in action order. May add in additional SSC or AP meetings between OS and PH as needed
PH | 15 | Sept | Review Actions-Alternatives, Select preferreds, and Approve for hearings | Review evaluation of actions and alternatives, select preferred alternatives for hearing
doc | 18 | Dec | Review hearing comments, revise preferreds
A | 21 | March | review any additional analysis, approve for submission | Need to have codified text in time to review
| 24 | June | FMP Submitted by | final draft, codified, etc - submit before the next meeting