## Information and Education
Objective and Project Description | Cost | 2004/2005 | 2005/2006 | 2006/2007 | Status Report 2007 | Notes from 2007 Report | New developments | Status Report 2014
Objective 1: Assist in development of the Oculina Experimental Closed Area Evaluation Plan.
Project 1: Develop an outreach strategy for the Oculina Bank area. | Staff time | X |  |  | 1 | Project completed; recommend modifying document to update activities and clarify components
Objective 2. Develop a focused campaign targeting recreational/commercial fishermen in the central-eastern Florida area. (COUNCIL INITIATED PROJECTS)
Project 1. Provide SAFMC regulation brochures to area fishermen (40,000 copies) | 14000 | X |  |  | 1 | Have been printed, 40K re-printed in 2007 and distributed. Re-print as needed. | 2013 SAFMC Regulations App | Track App download stats on both platforms; FWC recreational and commercial brochures publication inclusion (POC: Alan Pierce)
Project 2. Work with fishing chart manufacturers and or vendors to improve available information for the Oculina Experimental Closed Area. | TBD |  |  |  | 0.5 | Contacts were made in 2005. Needs follow-up. |  | Jen Schull to follow-up with NOS - supplier of info for chart manuf.
Project 3. Work with Florida FWC to provide written information regarding the Oculina Experimental Closed Area in (a) their publications targeting both recreational and commercial fishermen and in (b) mailings for fishing licenses and permits. | (a) Staff time (b) $5,000 |  |  |  | 1 | Article publication in 2007 FWC Saltwater Fishing Regs; mailing of rack cards to FWC commercial permits office. Needs follow up |  | FWC can include information in recreational and commercial FWC Regulation Brochures, also can mail to commercial permit holders. Include articles in FWC Fishing Line Magazine (POC: Alan Pierce/Dan Ellinor)
* Project 4. Develop and distribute news releases to focus on law enforcement activities, research and monitoring projects, and the ecological importance of the area. | $400/yr. |  |  |  | 1 | Occurring, continue to follow-up on this project deliverable. |  | Continue to locate hook news stories; coordinate with Research for upcoming field work FY14-16 and LE pulse operations
Project 5. Develop a Powerpoint presentation about the Oculina Experimental Closed Area, distribute on CD, post at Web site, and present to fishing clubs, environmental groups, local governments etc. | Staff time |  |  |  | 0 | Incomplete |  | Develop stock power-point for OECA; state contacts (POC: Alan Pierce, Rich Abrams, Steve Blair) use for inclusion into existing ppts and talks
* Project 6. Develop and distribute posters and rack cards/brochures at area bait and tackles shops, marinas, fish houses, boating stores, fishing tournaments, boat shows, etc. | 5000 |  |  |  | 1 | Posters and rack cards printed 2006. Over 10,000 have been distributed. Distribution ongoing. |  | Re-print/update rack cards; for distribution include fishing clubs, Smithsonian Marine Station teacher kits, FWC distrubition networks (POC: Alan Pierce/Rich Abrams); state parks (i.e. Ft. Pierce & Sebastian Inlet fishing museum)
NEW project identified: Develop kiosk for target boat ramps/landings / FWC has prototype
Objective 3: Coordinate a broader media campaign with partners to reach central Florida residents and visitors using newspaper, radio, TV, Internet, and existing environmental education network (e.g. environmental centers, schools, academia, area businesses). (PARTNERSHIP PROJECTS)
* Project 1. Develop an Oculina Web site or work within the existing site to establish a comprehensive web-based outlet to include access to useful education and outreach products. Publicize availability of information from new site by having links posted on other fishing/Non-Governmental Organizations/tourism related web sites | Initial '04-'05 funds available $5,000 |  | X |  | 1 | Information housed on the SAFMC Ecosystem site; HBOI hosted 2005 research cruise's daily log reports; NOAA Teacher at Sea; project is ongoing. | New SAFMC website launched in 2013 and includes Oculina information | Coordinate web site meeting prior to SEFSC/FAU ROV research trips FY14-16 for hosting scientists' daily logs on SAFMC site; link to other agencies/sites;
Project 2. Develop education products for teachers (K-12) and informal educators, post on Web site and develop packet for distribution to science teachers. | $5,000 for material - developing workshop |  | X |  | 1 | 2005 Teacher Workshop held with partners from NOAA, HBOI, NURC and SAFMC; 2007 DW Coral Teacher Workshop held - led by NOAA | 2008 Teacher Workshop held | Continue to hold Teacher Workshops; Funding available through COSEE FL in short-term for such a project (POC: Laura Dieterick)
Project 3. Create media packet targeting ecological importance of area; packet should include popular news items about Oculina Experimental Closed Area. | $3,000 media workshop, $5,000 media packets |  | X |  | 1 | Completed for 2005 research cruise.
Project 4. Develop a traveling portable exhibit that can be displayed at fishing tournaments, tradeshows, seafood/maritime festivals, aquariums, science museums, libraries, government centers, etc. | $3,000 to $5,000 |  |  |  | 0 | Incomplete in 2007 | The portable exhibit was developed in 2009 - includes kiosk, "Revealing the Deep" film featured; this is used at SAFMC meetings, limited use by outside organizations. Needs updating.
* Project 5. Offer media excursions to the Oculina Experimental Closed Area and HAPC/ tours and interviews regarding enforcement activities onboard the CT Randall law enforcement vessel. | $2000 (fuel for 2 trips) |  |  |  | 1 | Media cruise coordinated with FWC and NOAA OLE in 2005, cxld bc of weather. Follow up with additional activity. | Media excursion held in Aug 2009. Deployed submersible; received local and national coverage, including NBC Nightly News.
Project 6. Develop TV documentaries working with environmental TVoutlets (e.g., Discovery Channel, Public TV. | 1000 |  |  |  | 0.5 | Documentary producer accompanied 2005 research cruise; film under development. Status?
Project 7. Work within existing program to deploy a real time data buoy in the Oculina Bank area to provide weather and sea-state information for boaters and fishermen and integrate information into web site. | $200 K |  |  |  | 0 | Incomplete | Information added to NOAA National Data Buoy Center Station at Ft. Pierce; directly links to SAFMC web site and Oculina Bank regulations
Project 8. Assist with the continued development of an interpretive Oculina coral display at the Smithsonian Marine Station in Ft. Pierce, Florida. |  |  |  |  | 1 | Exhibit housed at Smithsonian Marine Station **ask Laura Dieterick abt this
Objective 4: Evaluation. |  |  | X
Project 1: Develop a survey tool to assess the effectiveness of the campaign and widely distribute before, during and after majority of activities underway. | Staff Time |  |  |  | 1 | 2005 survey developed in conjunction with FL SeaGrant; limited distribution.
* Project 2: Continue to receive input from local constituents (through the database established from the June 2004 outreach meetings) regarding the development of materials and level of community awareness. | $1,200 per yr. |  |  |  | 1 | Ongoing. | Continue contact with Smithsonian Marine Station; contact w/ Canaveral Charter Captain's Assoc.; Oculina Bank business collaboration; need to better utilize community contacts.
TOTAL (level of completion) |  |  |  |  | 13
Total number of Outreach projects = 17
* = Projects intended to be ongoing 0 = Projects with no progress and are incomplete .5 = Projects in which some work has been done but are not fully complete 1 = Projects that are complete

## Research Monitoring and Assmt
Objective and Project Description | Cost | 2004/2005 | 2005/2006 | 2006/2007 | Status Report 2007 | Notes from 2007 Report | New developments | Status Report 2014
I. Develop a research, monitoring and evaluation component for the Oculina Evaluation Plan | Staff time | X |  |  | 1 | Completed
1. Will Oculina thicket habitat recover throughout the Oculina Experimental Closed Area without human intervention? What time frame will be needed for significant recovery? Will it be necessary to introduce artificial substrate to serve as an initial settlement surface? (TO BE COMPLETED BY YEAR 3) | $25-50K per year if using ROV |  |  | X
Objective 1: Identify coral/fish recruitment pathways and compare settlement, growth, and survival rates on artificial substrate relative to settlement, growth, and survival rates on nearby unconsolidated coral rubble. |  |  | X--- | X | 0.5 | 225 large concrete reefballs deployed in 2000-2001 to measure coral settlement, growth, survival. Keonig submitted proposal in 2004 to use divers to survey equipment. Sufficient resources not available. | 2008 field research was conducted to attempt to dive and assess transplant module growth/success. Divers sent down over 5-6 day period. Structures had moved. / 2011 Pisces fieldwork, during an ROV survey, scientists observed one module within the OECA (Chapman's Reef), transplanted corals had not survived, but new recruits to corals were there.
Objective 2: Model biophysical, chemical, and physiological characters. Previous studies have shown the benthic environment of the Oculina reefs to be very dynamic and widely fluctuating due to upwelling events and meandering of the Florida Current. |  |  | X--- | X | 0 | No projects on table, no funding. | Florida Atlantic University has hired 2 physical oceanographers with this research focus. Look into grants, funding opportunities.
2. Determine and monitor the effect of the Oculina Experimental Closed Area on fish distribution and status? (TO BE COMPLETED BY YEAR 10) | $143K per year
Objective 1: Assess spawning aggregations of fishery species. |  |  | X |  | 0 | Incomplete |  | Should remain a high-priority. Need to assess year-round and during known spawning events.
Objective 2: Track fish movement |  |  | X |  | 0 | Incomplete
Objective 3: Identify Oculina Experimental Closed Area fish population demographics |  |  |  |  | 0.5 | Reef fish characterization surveys 80% complete (Harter et.al) |  | Consider temporal appropriateness of surveys
Objective 4: Determine pre-closure distribution of dominant harvested species in and outside the reserve areas, in order to provide historical context for subsequent assessments. Review landings; spill over effects (i.e., identify benthic and juvenile pathways, upwelling events, spill-over between deep and shallow reefs) | TBD |  |  |  | 0 | Group consensus (from 2007 report) was this objective may not be worthwhile; well-established that fisheries were once there, objective could be met through fishermen interviews |  | Ava Lassiter published report for Gulf & SA Fisheries Foundation in 2011: Assessment of the Impacts of the Oculina Bank MPA and In-Depth Ethnographic Profile of the Fort Pierce, Florida Fishing Community
Objective 5: Determine age distribution, nursery grounds, migratory patterns, and mortality rates for dominant harvested fish stocks. | $50K per year |  |  |  | 0 | Nothing completed
3. What is the population structure of corals? (TO BE COMPLETED BY YEAR 10) | TBD
Objective 1: Research population genetics of Oculina varicosa |  |  | X--- | ----- | 0 | Incomplete |  | Sandra Brooke published report in 2008 XX
Objective 2: Identify cross-shelf relationships between shallow and deep Oculina varicosa populations. | TBD |  |  |  | 0 | Incomplete
Objective 3: Biogeography | TBD |  | X--- | ----- | 0
4. What are the stressors affecting the Oculina Experimental Closed Area? (TO BE COMPLETED BY YEAR 10) | [7 empty] | Consider this objective as high priority. Since Evaluation Team last met, considerable research on sedimentation, temperature and other stressors and their detrimental affects to corals is being done./ John Reed paper on sub-lethal effects
Objective 1: Identify natural and anthropogenic stressors (i.e., disease, gear impacts, poaching, enforcement) | TBD |  | X |  | 0 | Low priority considering other research needs
Objective 2: Determine the frequency and severity of sedimentation induced by benthic storms. | TBD |  |  |  | 0 | Low priority considering other research needs
Objective 3: Identify physiological tolerances of the coral to environmental stressors | TBD |  |  |  | 0 | Low priority considering other research needs
5. What are the key trophodynamic functional groups? (TO BE COMPLETED BY YEAR 5) |  |  | X--- | -----
Objective 1: Identify food web structure and dynamics | $80K |  | X--- | ----- | 0.5 | George et.al created a rudimentary model in 2006, further information is needed.
6. Develop index of physical and chemical parameters that characterize a healthy Oculina coral ecosystem. (TO BE COMPLETED BY YEAR 10)
Objective 1: Develop index for coral health (including structural damage, recruitment, genetics, physiology, life history) | $20K |  |  |  | 0 | Prohibitively expensive and logistically unfeasible.
Objective 2: Develop index of community health for entire biota incl. coral (biodiversity, richness, biocomplexity). | $20K |  |  |  | 0 | Prohibitively expensive and logistically unfeasible.
Objective 3: Determine indicator species that are intimately tied with Oculina (invertebrates or vertebrates) | $10K |  | X--- | ---X | 0.5 | Description of fauna associated with live Oculina colonies has been studied and status of current knowledge was published by Reed et.al (2005). Other habitats within OECA haven't been studied.
Objective 4: What is the age of the coral substrate, and geological formations (last 15,000 years) (Death rates)? Also look at associated mollusks and other biota and their changes. | $25K |  |  |  | 0.5 | Information on bioherm age was determined using a single core of an Oculina mound (Reed, 2002). Further info. needed, but low priority.
Objective 5: Are paleo-data (age) associated with past climate and oceanographic conditions? | $15K |  |  |  | 0 | Incomplete
Objective 6: Are there other paleo-data from elsewhere in the world that will give perspective on Oculina growth? (ice cores, deep-water sediment cores)? | $10K |  |  |  | 0 | Incomplete
7. Conduct research on coral feeding ecology (TO BE COMPLETED BY YEAR 10) | $20K per year
Objective 1: Define feeding dynamics |  |  |  |  | 0.5 | Brooke, unpublished study. Field sampling and lab experiments are needed to complete this objective. Low priority.
Assessment Planning Projects
1. What is the effect of management measures in the Oculina Experimental Closed Area on the status of fishery stocks? (HIGHEST PRIORITY TO BE COMPLETED BY YEAR 10) | $300K
Objective 1: Characterize (including distribution and abundance patterns, size and age distribution, spawning aggregation presence, sex ratios, etc) major fishery species within the Oculina Experimental Closed Area compared to reference sites. |  |  | X |  | 0.5 | Reef fish characterization surveys 80% complete; 2005 transect data collected at 4 stations in OECA, 4 stations in HAPC, and 4 stations outside (inshore) of closed areas. SEADESC dive summaries being created. | S. Harter pointed out that SEFSC hasn't received funding to study the Oculina Bank since 2005. However, 5 ROV dives were made in 2011 on a deep coral cruise. Pisces Cruise report from July 2011 results need to be incorporated into the Research Team's report; include images from species inside of OECA; also species composition table
Objective 2: Characterize fish communities, inside and out, including habitat utilization patterns, trophic interactions, ontogenetic changes, predator-prey relationships, etc. |  |  | X |  | 0.5 | Reef fish characterization surveys 80% complete; 2005 transect data collected at 4 stations in OECA, 4 stations in HAPC, and 4 stations outside (inshore) of closed areas. SEADESC dive summaries being created. | FY 14-16 CRCP coral grant objectives: conduct ROV dives inside OECA to complete a species and habitat characterization of the area.
Objective 3: Connectivity to the broader seascape (larval sources and sinks, spill-over effects) | $150K |  |  |  | 0 | Unaddressed.
2. What and where are the major habitat types in the Oculina Experimental Closed Area, the Oculina Bank Habitat Area of Particular Concern and adjacent hardbottom areas? (HIGHEST PRIORITY TO BE COMPLETED BY YEAR 3)
Objective 1: Complete high definition bathymetric mapping 1) within the Oculina Experimental Closed Area; 2) coral areas adjacent to the Habitat Area of Particular Concern; 3) in Habitat Area of Particular Concern within coral zone 50-100 m; 4) soft bottom habitat east of the coral zone within the Habitat Area of Particular Concern and 5) suspected and known hard coral areas north and south of the Habitat Area of Particular Concern, specifically from Cape Canaveral to the north and from St. Lucie mound and Jupiter Inlet to the south | $300K-75K year 1, 125K year 2, 100K year 3 |  | X (#1) | X (#3 & #4) | 0.5 | See above; 2005 field survey (Harter et.al) | Same as above. Some of the objectives are repetitive.
Objective 2: Complete habitat characterization 1) within the Oculina Experimental Closed Area; 2) coral areas adjacent to the Habitat Area of Particular Concern; 3) in Habitat Area of Particular Concern within coral zone 50-100 m; 4) soft bottom habitat east of the coral zone within the Habitat Area of Particular Concern and 5) suspected and known hard coral areas north and south of the Habitat Area of Particular Concern, specifically from Cape Canaveral to the north and from St. Lucie mound and Jupiter Inlet to the south | Same as above |  | Same as above | Same as above | 0.5 | See above
3. What are the magnitude and causes of changes in habitat structure and functionality over time? (TO BE COMPLETED BY YEAR 3) |  |  |  | X
Objective 1: Determine causes and timing of coral death | $20K |  |  | X | 0 | No funding. Low priority.
Objective 2: Origin and functional characterization of rubble zone | Cost associated with overall habitat charact. above |  |  | X | 0 | Incomplete. Low priority.
4. How do oceanographic conditions and episodic events affect production, coral condition, reproduction and growth? (TO BE COMPLETED BY YEAR 10) | Cost associated with dev. of OOS capabilities
Objective 1: Quantify the extent, intensity and frequency of episodic events (upwelling, storms, etc) |  |  |  |  | 0 | Unaddressed. Could be a long-term proposal with NSF IOOS funding entities.
Objective 2: Assess the impact of episodic events (upwelling, storms, etc) |  |  |  |  | 0 | Incomplete
Objective 3: Optimize design of restoration efforts |  |  | X |  | 0 | Proposed a summary (literature review) of oceanographic characters unique to Canaveral and the HAPC; proposed array of echosounders to measure Gulf Stream fluctuations and also fixed buoys with bottom mounted at Jeff's Reef; a proposal submitted but not funded.
Objective 4: Characterize impacts from anthropogenic sources of pollution (nutrients/sedimentation) |  |  |  |  | 0 | Not logistically tractable.
TOTAL (level of completion) |  |  |  |  | 6
Total number of Research projects = 33
* = Projects intended to be ongoing 0 = Projects with no progress and are incomplete .5 = Projects in which some work has been done but are not fully complete 1 = Projects that are complete
Recent Publications (since 2007) | Author/Entity
Assessment of the Impacts of the Oculina Bank MPA and In-Depth Ethnographic Profile of the Fort Pierce, Florida Fishing Community | Ava Lassiter / Gulf & SA Fisheries Foundation, October 2011
Impacts of Bottom Trawling on a Deep-water Oculina Coral Ecosystem Off Florida | J.Reed, C.Koenig, A.Shepard / Bulletin of Marine Science 2007
Assessment of fish populations and habitat on Oculina Bank, a deep-sea coral marine protected area off eastern Florida | S.Harter, M. Ribera, A. Shepard, J. Reed / Fishery Bulletin 2009
CIOERT SEADESC II Report Extreme Corals 2011: SA Deep Coral Survey Pisces cruise | NOAA DSC R/T Program, NOAA OER (J. Reed, A. David, S. Harter)
Sub-lethal coral stress: Detecting molecular responses of coral populations to environmental conditions over space and time | S. Edge, T. Shearer, M. Morgan, T. Snell ; Aquatic Toxicology 2013
Nuclear sequences reveal mid-range isolation of an imperilled deep-water coral population | R. Eytan, M. Hayes, P. Arbour-Reily, M. Miller, M. Hellberg / Molecular Ecology 2009

## Enforcement
Objective and Project Description | Cost | 2004/2005 | 2005/2006 | 2006/2007 | Status Report 2007 | Notes from 2007 Report | New developments | Status Report 2014
Council motion March 2003: (1) It is the Council’s position/policy that enforcement of the Oculina Closure is an utmost priority, (2) violation of the Oculina Experimental Closed Area is egregious and of a high and aggravated nature, and (3) that we request NOAA General Counsel revise the penalty schedule to be commensurate with the above classification.
Penalty Schedule Revised |  |  |  |  | 1 | Penalty schedule revised in June 2003 | Penalty schedule revised again in 2011; this schedule was updated in an effort to develop a national schedule, currently out for comment until April 28, 2014 *will modify the classification and range of penalties according to matrix
Council motion June 2003: Develop updated law enforcement plan within 1 year of implementation of SG Am 13A.
Updated law enforcement plan |  |  |  |  | 1 | Completed within 1 year of Snapper Grouper Amendment 13A | Current Enforcement Plan to be redeveloped using a Project Management Format
Principle I. VMS – real-time access to VMS (coordination by USCG and FWC access to VMS) |  |  |  |  | 0.5 | Continued monitoring; USCG real-time on vessels not complete; FWC direct access to VMS? | Monitoring; Intelligence operations; Planning patrol operations; and Investigations - follow-up inspections/interviews ongoing. FWC now has a mirrored access to VMS; USCG has access to VMS data through their command center only (have to call in for this information because no direct access on cutter vessels)
* Principle II. Cooperative Enforcement (USCG, FWC, OLE): patrols, investigations, intelligence sharing, meetings |  |  |  |  | 1 | Functioning | Patrols (USCG & FWC); Investigations (NOAA OLE); Intelligence (VMS, other contacts); Training operations functioning
* Principle III. Increase Enforcement Presence (patrols, 24’ rigit hull inflatable boat for surge operations) |  |  |  |  | 0.5 | Coordinated pulse operations, dedicated patrols by FWC, NOAA OLE vessel? | USCG, FWC, OLE surge operations - cooperative enforcement is utlizing each agency's assets; Patrol activity undertaken by USCG and FWC (vessels, boats, aircraft)
* Principle IV. Quarterly Enforcement Reports |  |  |  |  | 1 | Completed, ongoing | Quarterly reports presented at SAFMC meetings; OLE prepares report | Better recordkeeping by agency; timely submission of reports. Inquire with outreach/research team if enforcement report data is useful. These reports are not used within agency, but prepared soley for SAFMC. If not useful, reconsider principle.
Principle V. Support of Outreach and Education Plan specific projects
* Objective 2. Project #1. LE support of distribution of SAFMC regulations |  |  |  |  | 1 | Completed, ongoing | Ongoing at Outreach Events (fishing shows and tournament meetings); and on patrol (recreational anglers in or near OECA; commercial fishermen) | Engage in tournaments in Sebastien and Ft. Pierce (incl. Oculina rack card in captain's bags)
* Objective 2. Project #4. LE support of news releases |  |  |  |  | 1 | Ongoing
* Objective 2. Project #6. LE support of distribution of Oculina HAPC brochures |  |  |  |  | 1 | Ongoing
TOTAL (level of completion) |  |  |  |  | 8
Total number of Enforcement deliverables = 9
* = Projects intended to be ongoing 0 = Projects with no progress and are incomplete .5 = Projects in which some work has been done but are not fully complete 1 = Projects that are complete
*Recommendation by NOAA GC to change the language pertaining to OECA and snapper grouper possession restrictions = change "retain" to "possess" to be more clear and consistent with existing regulations and SA MPAs.

## Evaluation Team
Contact Information
Outreach Representatives | Affiliation
Alan Peirce | FL Fish and Wildlife Conservation Commission | alan.peirce@myfwc.com
Jennifer Schull | NOAA Southeast Fiseries Science Center | jennifer.schull@noaa.gov
Rich Abrams | FL Fish and Wildlife Conservation Commission; SAFMC Information & Education Advisory Panel member | Rich.Abrams@myfwc.com
Laura Diederick | Smithsonian Marine Station - Education specialist | diederick@si.edu
Scott Chandler | FL Sportfishing Association (recreational) | sdchandler@ft.newyorklife.com
Research and Monitoring Representatives
John Reed | Habor Branch Oceanographic Institute at Florida Atlantic University & Coral Advisory Panel member | Jreed12@fau.edu
Chris Koenig | Florida State University | koenig@bio.fsu.edu
Grant Gilmore | Estuarine, Coastal & Ocean Science, Inc. | rggilmorej@gmail.com
Andy David | NOAA Southeast Fisheries Science Center | andy.david@noaa.gov
Mandy Karnauskas | NOAA Southeast Fisheries Science Center | mandy.karnauskas@noaa.gov
Jocelyn Karazsia | NOAA Habitat Conservation Division & Coral Advisory Panel member | jocelyn.karazsia@noaa.gov
Sandra Brooke | Florida State University - Coastal Marine Lab & Coral Advisory Panel member | sbrooke@fsu.edu
Ken Lindeman | Florida Institute of Technology | lindeman@fit.edu
Steve Blair | Restoration & Enhancement Section, Miami-Dade Dept. of Regulatory and Economic Resources - Environmental Resources Mgmt; Coral Advisory Panel member (Chair) | blairs@miamidade.gov
Pat Geer | GA Department of Natural Resources - Marine Fisheries Division & Habitat Advisory Panel member (Chair) | Pat.Geer@dnr.state.ga.us
Law Enforcement Representatives
Lt. Col. Bruce Buckson | NMFS Office of Law EnforcementLE | bruce.buckson@noaa.gov
Richard Chesler | NOAA Special Agent | richard.chesler@noaa.gov
Karen Antrim Raine | NOAA General Counsel & SAFMC Law Enforcement Advisory Panel member | karen.raine@noaa.gov
Major Percy Griffin | FL Fish and Wildlife Conservation Commission - Division of Law Enforcement | percy.griffin@myfwc.com
Lt. Morgan Fowler | U.S. Coast Guard & SAFMC Member | morgan.m.fowler@uscg.mil
Col. Chisolm Frampton | SC Department of Natural Resources, Law Enforcement Division & SAFMC Law Enforcement Advisory Panel member (Chair) | Framptonc@dnr.sc.gov
Other Representatives
Beau Bryan | Ft. Pierce Sportfishing Club (recreational)
Bobby Cardin | Commercial snapper grouper fisherman | finchaser357@aol.com
Ben Hartig | Commercial fisherman & SAFMC Member (Chair) | mackattackben@att.net
Robert Johnson | Charter/Headboat & Snapper Grouper Advisory Panel member (Chair) | jlfishing@bellsouth.net
Mike Merrifield | Cape Canaveral Shrimp Co., Wild Ocean Seafood Market & Deepwater Shrimp Advisory Panel member (Chair) | mikem@wildoceanmarket.com
Council Staff - Coordination
Anna Martin | Fishery Biologist | anna.martin@safmc.net
Roger Pugliese | Sr. Fishery Biologist | roger.pugliese@safmc.net
Kim Iverson | Public Information Officer | kim.iverson@safmc.net