## Sheet1
Council's |  | 2015
Priorities | SAFMC CY 2015 SCHEDULE | Jan | Feb | Mar | Ap | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
(March 2015) | FMPS/AMENDMENTS/FRAMEWORKS
1 | Visioning Public Input |  |  | D |  |  | Ah/P | P | P | D | A |  | Ah
1 | Snapper Grouper Amendment 37 (Hogfish) |  |  | O |  |  | D/As | Ps | Ps | Ah |  | P | P/A
| Proposed Revised Timeline: |  |  | O |  | Jun: D/As; Aug: Ps; Sep: D; Dec: Ah
Snapper Grouper Amendment 41 (Mutton Snapper) | bar: Sep; Dec
2 | Snapper Grouper Amendment 36 (Spawning SMZs) |  |  | Ah | P | P | Ah |  | P | P/A |  |  | F
3 | System Management Plan for SG Amendment 14 MPAs |  |  | D |  |  | D | IP | IP | P/A |  |  | F
4 | Snapper Grouper Amendment 38 (Blueline Tilefish)(DETERMINE @ SEPTEMBER) |  |  | O | bar: Jun; Sep; Dec
4 | Joint SA/GM Charterboat Reporting Amendment (Gulf Lead) (COUNTS AS 2 AMENDMENTS) |  |  | O |  | Jun: O; Sep: Ah; Nov: P; Dec: A
5 | Snapper Grouper Regulatory Amendment 16 (BSB Pot Closure) |  |  | O |  | Jun: Ah; Aug: P; Sep: A; Dec: F/S
6 | Fishery Ecosystem Plan II |  |  | D | bar: Jun; Sep; Dec
6 | Joint SA/GM CMP Am 26 (King Mackerel ACLs/Boundary/MMSs; Gulf Lead) (2 AMENDMENTS) | Ps |  | O | bar: Jun; Sep; Dec
7 | Joint SA/GM Amendment (Issues from South Florida Committee) (Gulf Lead) (2 AMENDMENTS) |  |  | O |  | Jun: O; Sep: D; Dec: Ah??
9 | Snapper Grouper Amendment 35 (Removing species & Golden Tilefish Endorsement) |  |  | P/A |  | Jun: F/S
| Snapper Grouper Regulatory Am 23 (BSB Bag, Jacks Trip limit & GT FY Start) |  |  |  |  | Aug: Ps; Sep: D; Dec: Ah
Possible New Items for 2016: (these would delay SG RA 23 until 2016)
| Blueline Tilefish Framework (change ABC/ACL) |  |  |  |  | Sep: O; Nov: P; Dec: A/F/S
| Dolphin Framework (commercial trip limit) |  |  |  |  | Sep: O; Nov: P; Dec: A/F/S
Items for 2016:
(split from Am37) | Snapper Grouper Regulatory Amendment 24 (Multiple Species) | [5 empty] | As | Ps | Ps | Ah |  | P | P/A
10 | Snapper Grouper Regulatory Amendment 23 (Golden Tilefish) |  |  | O |  |  | D/As | Ps | Ps | Ah |  | P | P/A
13 | Comprehensive Ecosystem-Based Amendment #3 (Bycatch) |  |  | D | bar: Jun; Sep; Dec
8 | Joint SA/GM Generic Commercail Logbook Amendment
9 | Snapper Grouper Amendment 42 43 (Update Wreckfish ITQ)
11 | Coral/Shrimp Golden Crab Amendment XX (Modify GC & Establish RS Fishing Areas)
12 | Shrimp Closure Work (states can request directly to NMFS)
13 | Joint SA/GM Amendment 24 (Atlantic Spanish Mackerel Allocations)
13 | Calico Scallop FMP
Moved fm 2015 | Snapper Grouper Amendment XX (Short-term Visioning)
Moved fm 2015 | Snapper Grouper Amendment XX (Allocations from Visioning)
D = Plan development; AS = Approve for public scoping; Ps = Public Scoping
O = Develop options/review options paper; Ah = Approve for public hearing
P = Public hearing; IP = Informal public hearing; N = NMFS informal review
A = Council approve; F = Final Review; NDC = NMFS determination of complet for DEIS filing
S = Submit for Secretarial review