## Overall Schedule
| 2011 | [11 empty] | 2012 | [11 empty] | 2013 | [11 empty] | 2014
SAFMC CY 2009 SCHEDULE (with 2010-14 estimates) | Jan | Feb | Mar | Ap | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Ap | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Ap | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Ap | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
FMPS/AMENDMENTS/FRAMEWORKS
Snapper Grouper Amendment 18 (FMU ext. & other issues) - split
Snapper Grouper Amendment 18A/EIS (BSB & Data Collection) DONE |  |  |  |  | Sep: Ah; Nov: P; Dec: P/F/S; 2012 Jan: S
Snapper Grouper Amendment 18B/EA (Golden Tilefish) |  |  |  |  | Dec: Ah; 2012 Jan: P; 2012 Feb: P; 2012 Mar: A/F/S |  |  | A/F/S
Snapper Grouper Regulatory Amendment 12 (Golden Tilefish) |  |  |  |  | 2012 Jan: P; 2012 Feb: P; 2012 Mar: P/F/S
Snapper Grouper Amendment 20 (Wreckfish ITQ) - split
Snapper Grouper Amendment 20A/EA (Wreckfish ITQ - 3 Items) DONE |  |  |  |  | Sep: Ah; Nov: P; Dec: P/F/S
Snapper Grouper Amendment 20B/EA? (Wreckfish ITQ - remaining Items)???? | [17 empty] | Ah |  | P/N | A/F | S | bar: Dec; 2012 Mar
Snapper Grouper Amendment 24/EA (Red Grouper) DONE |  |  |  |  | Jun: Ah; Aug: P; Sep: A; Nov: P; Dec: P/F/S
Snapper Grouper Regulatory Amendment 11 (Deepwater Closure fm 17B) DONE |  |  |  |  | Jun: A; Aug: P/F/S
Comprehensive ACL Amendment/EIS (Amend all FMPs) DONE |  |  |  |  | Aug: F/S
Golden Crab Amendment 6 (Catch Shares) |  |  |  |  | Dec: Ah; 2012 Jan: P; 2012 Feb: P; 2012 Mar: A/F/S |  |  | F/S
Fishery Ecosystem Plan (Update #1) - start in 2014 | [35 empty] | As | Ps | Ps | O |  |  | Ah | NDC | P/N | A/F/S
Comprehensive Ecoystem-Based Amendment #3(2012), #4(2013) & #5(2014) | Ps | Ps | O |  |  | Ah | NDC | P/N | A/F/S |  |  | As | Ps | Ps | O |  |  | Ah | NDC | P/N | A/F/S |  |  | As | Ps | Ps | O |  |  | Ah | NDC | P/N | A/F/S |  |  | As | Ps | Ps | O |  |  | Ah | NDC | P/N | A/F/S
Comprehensive Ecosystem-Based Amendment #2 (Coral ACL) (DONE) | bar: Jun to Jul
Shrimp Closure Work (if required; done in 2011) |  |  | A | [23 empty] | A | [11 empty] | A | bar: 2012 Mar
Shrimp Amendment 9 (Closure process & MSST) |  |  |  |  | Sep: O; Dec: As; 2012 Jan: Ps; 2012 Feb: Ps; 2012 Mar: O |  |  | Ah | NDC | P/N | A/F/S
Joint Mackerel Amendment 18 (GMFMC Lead; ACLs/Ams) (DONE) | bar: Aug to Sep; Dec
Joint Mackerel Amendment 19 (Prohibit Bag Limit Sales & Permits) - timing | [17 empty] | Ah | NDC | P/N | A/F/S |  |  | F/S? | bar: Dec
Joint Mackerel Amendment 20 (Boundaries & Timing) - timing | [17 empty] | Ah | NDC | P/N | A/F/S |  |  | F/S? | bar: Dec
Joint Mackerel Framework (Size/Bag/Trip Limits) - timing | bar: Dec
Joint Spiny Lobster Amendment 10 (ACLs/AMs) (DONE 7/20/11 TO SOC) |  |  | Ah | NDC | May: P/N; Jun: A/F; Jul: S
Joint Spiny Lobster Amendment 11 (NMFS lead; Protected Resources Issues) |  |  |  |  | Dec: Ah; 2012 Jan: P; 2012 Feb: P; 2012 Mar: F/S
Joint GM/SA Dealer Amendment | [17 empty] | Ah | NDC | P/N | A/F/S | bar: Dec to 2012 Feb
Workshops with Fishermen - start in 2012 | bar: Dec
Calico Scallop FMP? (Separate FMP or Include in a Comprehensive FEP Am)
D = Plan development
AS = Approve for public scoping
Ps = Public scoping | bar: Dec
O = Develop options/review options paper | bar: Dec
Ah = Approve for public hearing | bar: Dec
P = Public hearing
IP = Informal public hearing
N = NMFS informal review
A = Council approve
F = Final Review
NDC = NMFS determination of completeness for DEIS Filing
S = Submit for Secretarial review
BLUE = DONE

## CEBA-3 Staff Recommendations
Objective=Finish CEBA-3 in 2012
Items Scoped for CEBA-3 | CEBA-3 | CEBA-4 | Framework | Drop
| (CY 2012) | (CY 2013) | (after 2013 assmt.)
1. Expand Coral HAPCs | 1. Expand Coral HAPCs
2. Prohibit Powerheads |  | 2. Prohibit Powerheads
3. MPAs & HAPCs for SpHind & Warsaw | 3. MPAs & HAPCs for SpHind & Warsaw
4. Snapper Ledge = MPA |  | 4. Snapper Ledge = MPA
5. Rec. tag program for deepwater sp. | 5. Rec. tag program for deepwater sp.
6. Hogfish |  |  | 6. Hogfish
7. Gray triggerfish |  |  | 7. Gray triggerfish
8. African pompano |  |  |  | 8. African pompano
9. Permits & Data reporting | 9. Permits & Data reporting
Distribution of Work
Ecosystem Committee | 1. Expand Coral HAPCs
Snapper Grouper Committee | 3. MPAs & HAPCs for SpHind & Warsaw
Data Collection Committee | 5. Rec. tag program for deepwater sp.
9. Permits & Data reporting
Golden Crab Committee | Golden Crab Amendment 6
Shrimp Committee | Shrimp Amendment 9
Items to Complete in 2012 | Comments
1. SG Reg Am 12 (Golden Tilefish) | to SOC by March 29, 2012 if approved @ March meeting
2. SG Am 18B (Golden Tilefish) | to SOC by March 29, 2012 if approved @ March meeting; June approval latest for implemetation by 1/1/13
3. Golden Crab Am 6 (Catch Share) | to SOC by March 29, 2012 if approved @ March meeting; June approval latest for implemetation by 1/1/13
4. Joint Mack Am 19 (Permits & Sale) | Approve PH June; PH Aug.; Final Sept (Dec @ latest)
5. Joint Mack Am 20 (Boundaries & Transit) | Approve PH June; PH Aug.; Final Sept (Dec @ latest)
6. Joint Dealer Amendment | Approve PH June; PH Aug.; Final Sept (must be implemented effective 1/1/13)
7. CEBA-3 | Approve PH June; PH Aug.; Final Sept (Dec @ latest)
8. Shrimp Am 9 | Approve PH June; PH Aug.; Final Sept (Dec @ latest)
9. Other Reg Amendments???? | April SSC review of MRIP so may have new OFLs & ABCs?????
Prepare very brief Regulatory Amendment/Categorical Exclusion for each FMP affected
Note: Assumes Snapper Grouper Am 20B is deferred until 2013 at least to see what happens with new, much reduced ACL.