## Recovered_Sheet1
| 2007 | [11 empty] | 2008 | [11 empty] | 2009 | [11 empty] | 2010
SAFMC CY 2008 SCHEDULE (with 2009-10 estimates) | Jan | Feb | Mar | Ap | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Ap | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Ap | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Ap | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
FMPS/AMENDMENTS/FRAMEWORKS | bar: Dec
Snapper Grouper Amendment 14 (done; 7/18/07 sent to NMFS) |  |  | A | bar: Jun to Sep; Dec; 2008 Mar
Mackerel Framework (SAFMC - changed from A18) |  |  | P/N | P/N | Jun: A; Sep: F; Oct: S
Snapper Grouper Amendment 15 (split into 3 parts 9/20/07) |  |  | O |  | Jun: O; Sep: Ah; Oct: NDC; Nov: P/N; Dec: A; 2008 Mar: F | S
Snapper Grouper Amendment 15A |  |  |  |  | Sep: Ah; Oct: NDC; Nov: P/N; Dec: P/N/A/S
Snapper Grouper Amendment 15B |  |  |  |  | Sep: Ah; Oct: NDC; Nov: P/N; Dec: P/N; 2008 Mar: A/S
Snapper Grouper Amendment 16 (Gag/Vermilion)(done; 10/21/08 sent to NMFS) |  |  |  |  | Aug: Ps; Sep: Ps/O; Dec: O; 2008 Mar: Ah | NDC/P/N | P/N | Ah |  | P/N | N/F | S
Shrimp Amendment 7 (rock shrimp & reporting) |  |  | D | [14 empty] | Ah | NDC | P/N | P/N/A/F | S | bar: Jun; Sep; Nov to 2008 Jan; 2008 Mar
Comprehensive Allocation Amendment (new) | [17 empty] | O |  |  | Ah | NDC | P/N | P/N/A |  |  | F/S | bar: Dec; 2008 Feb to 2008 Mar
Snapper Grouper Amendment 17 |  |  |  |  | Dec: AS; 2008 Feb: Ps; 2008 Mar: Ps/O |  |  | O |  |  | Ah | NDC | P/N | P/N/A |  |  | F/S
Snapper Grouper Amendment 17 | [20 empty] | O |  |  | Ah | NDC/P/N | P/N | A |  |  | F/S
Snapper Grouper Amendment XX (Red Snapper) | [16 empty] | Ps | O |  |  | O |  |  | O |  |  | Ah |  | P/N | F |  |  | S | bar: 2008 Mar
Snapper Grouper Amendment 18 (LAPPs) |  |  |  |  | Dec: AS; 2008 Feb: Ps; 2008 Mar: Ps/O |  |  | O |  |  | O |  |  | Ah | NDC | P/N | P/N/A |  |  | F | S
Comprehensive ACL Amendment (Amend all FMPs) | [23 empty] | AS | Ps | Ps | O |  |  | O |  |  | Ah | NDC | P/N | A |  |  | F/S
Comprehensive Ecoystem-Based Amendment #3 | [35 empty] | As | Ps | Ps | O |  |  | Ah | NDC | P/N | A/F/S
Comprehensive Ecosystem-Based Amendment #2 | [23 empty] | AS | Ps | Ps | O |  |  | O |  |  | Ah | NDC | P/N | A/F/S
Fishery Ecosystem Plan (PH#2) |  |  | D | [17 empty] | Ah |  |  | A |  |  | F |  |  | S | bar: Jun; Sep; Dec; 2008 Mar
Fishery Ecosystem Plan (PH#2) | [23 empty] | Ah |  |  | A/F/S | bar: Dec; 2008 Mar
Comprehensive Ecosystem-Based Amendment (PH#2) |  |  | D | [17 empty] | Ah | NDC | P/N | A/AS |  | Ps | F/O |  |  | S/Ah | NDC | P/N | P/N/A | S | bar: Jun; Sep; Dec; 2008 Mar
Comprehensive Ecosystem-Based Amendment (PH#2) | [23 empty] | Ah | NDC/P/N | P/N | A/F/S | bar: 2008 Mar
Fishery Ecosystem Plan (PH#1) |  |  | D | bar: Jun; Sep; Dec; 2008 Mar
Fishery Ecosystem Plan Comp. Amendment (PH#1) |  |  | D | [13 empty] | P | O | bar: Jun; Sep; Dec; 2008 Mar
Shrimp Closure Work (if required; none in 2007, 2008) |  |  | A | [23 empty] | A | [11 empty] | A | bar: 2008 Mar
Mackerel Amendment 18 (Gulf Lead - changed from A#16&A#19/delayed until after SEDAR 16) | [17 empty] | O |  |  | O |  |  | O |  |  | Ah | NDC | P/N | P/N/A |  |  | F | S | bar: Dec to 2008 Mar
Spiny Lobster Amendment 4/8 (CFMC Lead - imports)(done) | [17 empty] | Ah | P |  | A | S | bar: Aug; 2008 Jan; 2008 Mar
Calico Scallop FMP? (Separate FMP or Include in a Comprehensive FEP Am)
D = Plan development
AS = Approve for public scoping
Ps = Public scoping | bar: Jun; Sep; Dec; 2008 Mar
O = Develop options/review options paper | bar: Jun; Sep; Dec; 2008 Mar
Ah = Approve for public hearing | bar: Jun; Sep; Dec; 2008 Mar
P = Public hearing
IP = Informal public hearing
N = NMFS informal review
A = Council approve
F = Final Review
NDC = NMFS determination of completeness for DEIS Filing
S = Submit for Secretarial review
BLUE = DONE | bar: Aug; 2008 Mar