## Recovered_Sheet1
| 2009 | [11 empty] | 2010 | [11 empty] | 2011 | [11 empty] | 2012 | [11 empty] | 2013 | [11 empty] | 2014
SAFMC CY 2009 SCHEDULE (with 2010-14 estimates) | Jan | Feb | Mar | Ap | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Ap | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Ap | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Ap | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Ap | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Ap | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
FMPS/AMENDMENTS/FRAMEWORKS
Snapper Grouper Amendment 17A (Red Snapper) |  |  |  |  | Sep: Ah; Oct: NDC; Nov: P/N; Dec: A; 2010 Mar: F/S
Snapper Grouper Amendment 17B (rest of overfishing species) |  |  |  |  | Sep: Ah; Oct: NDC; Nov: P/N; Dec: A; 2010 Mar: F/S
Snapper Grouper Amendment 18 (FMU ext. & other issues) |  |  | O |  | Jun: O; Sep: O; Dec: Ah; 2010 Jan: NDC/P; 2010 Feb: P/N; 2010 Mar: A |  |  | F/S
Snapper Grouper Amendment 20 (Wreckfish ACL/AM/ITQ) | Ps | Ps | [15 empty] | Ah | NDC | P/N | A/F/S | bar: Jun; Sep; Dec; 2010 Mar
Comprehensive ACL Amendment (Amend all FMPs) | Ps | Ps | O | [14 empty] | Ah | NDC | P/N | A/F/S | bar: Jun; Sep; Dec; 2010 Mar
Golden Crab Amendment 5 (Catch Shares) | [17 empty] | Ah | NDC | P/N | A/F/S | bar: Jun; Sep; Dec; 2010 Mar
Fishery Ecosystem Plan (Update #1) | [59 empty] | As | Ps | Ps | O |  |  | Ah | NDC | P/N | A/F/S | bar: Jun; 2010 Mar
Comprehensive Ecoystem-Based Amendment #3-#7 |  |  |  |  | Dec: As; 2010 Jan: Ps; 2010 Feb: Ps; 2010 Mar: O |  |  | Ah | NDC | P/N | A/F/S |  |  | As | Ps | Ps | O |  |  | Ah | NDC | P/N | A/F/S |  |  | As | Ps | Ps | O |  |  | Ah | NDC | P/N | A/F/S |  |  | As | Ps | Ps | O |  |  | Ah | NDC | P/N | A/F/S |  |  | As | Ps | Ps | O |  |  | Ah | NDC | P/N | A/F/S
Comprehensive Ecosystem-Based Amendment #2 (Coral ACL) | Ps | Ps | O |  | Jun: O; Sep: O; Dec: Ah; 2010 Jan: NDC/P; 2010 Feb: P/N; 2010 Mar: A |  |  | F/S
Fishery Ecosystem Plan |  |  | A/F/S | bar: Jun; Sep; 2010 Mar
Comprehensive Ecosystem-Based Amendment #1 | NDC/P/N | P/N | A/F/S | NDC/N | Jun: F/S; Jul: NDC/N; Sep: F/S
Shrimp Closure Work (if required; none in 2009) |  |  | A | [23 empty] | A | [11 empty] | A | [11 empty] | A | [11 empty] | A | bar: 2010 Mar
Joint Mackerel Amendment 18 (GMFMC Lead; ACLs/Ams) | Ps | Ps | O |  |  | GM/Ps/O |  | GM/Ps | O | GM/Ps |  | O |  | O | O |  |  | Ah | NDC | P/N | A |  |  | F/S
Joint Spiny Lobster Amendment 9 (SAFMC lead; Delegation, ACLs/AMs) | Ps | Ps | O | [14 empty] | O |  |  | O |  |  | O |  |  | Ah | NDC | P/N | A/F/S | bar: Jun; Sep; Dec; 2010 Mar
Calico Scallop FMP? (Separate FMP or Include in a Comprehensive FEP Am)
D = Plan development
AS = Approve for public scoping
Ps = Public scoping | bar: Jun; Sep; Dec; 2010 Mar
O = Develop options/review options paper | bar: Jun; Sep; Dec; 2010 Mar
Ah = Approve for public hearing | bar: Jun; Sep; Dec; 2010 Mar
P = Public hearing
IP = Informal public hearing
N = NMFS informal review
A = Council approve
F = Final Review
NDC = NMFS determination of completeness for DEIS Filing
S = Submit for Secretarial review
BLUE = DONE | bar: 2010 Mar