## HOW WORKLOAD IS ESTIMATED
Example discussion level at various stages of FMP development.
And Color Coding Scheme in the following sheets
Type of Discussion | Workload Estimation Weight | Council Meeting Time
Initial Options Paper | 0.5 | 1-2h
Options discussions, review AP/SSC comments | 1 | 3-4h
Review and approve for Hearing | 1 | 3-4h
Address hearing comments | 0.5 | 1-2h
Final Approval | 0.5 | 1-2h
Council Meeting Workload Estimation and Time Management Approach
Council previously directed that 6 FMPs were the most that could be addressed in a Council meeting. Over the last several years this has proven to be an accurate estimate.
To address the current excessive workload and backlog of projects, we attempted to refine this some by considering the level of discussion that occurs at different stages of FMP development. For example, the first time the Council considers an amendment and reviews a general options paper will take less discussion time than a later discussion when actions are reviewed and preferred alternatives selected.
We weighted the different discussion stages as either 1 or 0.5. Summing these weights for a meeting gives an estimate of the discussion time needed. Keeping the sum at or below 6 should keep the workload manageable within a single meeting.
Estimating the workload in this manner for several years forward, and through final approval of projects, provides a long-term persepective on the FMP workload. Individual FMP project schedules may need to be adjusted to address future meetings if the workload rating gets too high. It will also allow us to illustrate the impacts on other projects and on future meeting workloads when projects fall behind.

## 2024 - 2026 WorkPlan
| SAFMC 2024-2026 WORKPLAN - INCORPORATING PROJECTS UNDERWAY AND UPCOMING ASSESSMENTS |  |  | 2024 Q4 - REVISED PER THE SEPTEMBER 2024 COUNCIL MEETING
Amendments with statutory deadline
| Amend # | Amendment | SAFMC Lead | 2024-12-02 | 2025-03-01 | 2025-06-01 | 2025-09-01 | 2025-12-01 | 2026-03-02 | 2026-06-03 | 2026-09-04 | 2026-12-05 |  |  |  | Amendments that do not respond to a stock assessment or change to catch level recommendations
UNDERWAY |  | STATUTORY DEADLINE WORKLOAD SUBTOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Indicates that action is being taken but will not be discussed at the Council meeting (no time allocated toward the workload calculations)
| SG | Long-term RS response (MSE, SG fishery management measures) | TBD |  | S | DOC | DOC | DOC | PH | DOC | DOC | A
| SG 56 | Black Sea Bass Assessment Response | Mike | DOC | DOC | DOC | PH | DOC | A
| SG 46 | Private Recreational Permitting and Education | JohnH | DOC | S: PH; DOC: DOC; DOC: A
| SG 44 | Yellowtail Snapper and Mutton Snapper Assessment Response (Joint w/ Gulf as lead) | Allie |  | (SSC) | S | DOC | DOC | PH | A
| SG ?? | Yellowtail Snapper and Mutton Snapper Managememnt Changes | ?? |  | DOC: S; A: DOC | DOC | PH | DOC | A
| DW Reg 3 | Dolphin (Recreational Measures + MSE Response) | JohnH | Dolphin MSE |  |  |  | DOC | DOC | PH | DOC | A
| SG/CMP/DW | For-Hire Limited Entry | JohnH/Myra |  | DOC | S | DOC | DOC | DOC | PH | DOC | A | Timeline depends on availability of permit data
| Coral 11/Shrimp 12 | SFAA in Oculina HAPC northern extension | Kathleen & Allie |  | DOC: S?; S: DOC; DOC: PH; DOC: A | Timeline depends on availability of permit data
| SG/CMP/DW | SEFHIER Revisions | Myra/JohnH | S? | 4 | DOC | DOC | PH | DOC | A |  |  | Timeline depends on availability of permit data
|  | UNDERWAY FMP WORKLOAD SUBTOTAL |  | 1.5 | 4.5 | 4 | 5.5 | 4.5 | 4 | 4 | 2.5 | 3
PLANNED | CMP | Plan AM Spanish Mackerel Assessment Response | Christina | Port Meetings |  | S | DOC | DOC | PH | DOC | A |  | Starts after the Mackerel Port Meetings
| SG | Golden Tilefish Assement Response | TBD | AR | (AP) | S | DOC | DOC | PH | DOC | A |  | Start date depedning on assessment approval by the SSC
| SG | Blueline Tilefish Assessment Response and Deepwater Species Management Items | TBD |  | (SSC) | AR | (AP) | S | DOC | DOC | PH | DOC | A
| SG | Unassessed Stocks ABC | Mike |  | (SSC) | AR | (AP) | S | DOC | DOC | PH | DOC | A |  | Timeline pending data availaivlity and subsequent SSC feedback. Lilely will have to move further into the workplan but the timeline is uncertain.
| SG | Hogfish Assessment Response | TBD |  | DOC: AR; PH: (AP); DOC: S; A: DOC | DOC | PH | DOC | A
| SG | Black Grouper Assessment Response | TBD |  | PH: AR; DOC: (AP); A: S | DOC | DOC | PH | DOC | A
| SG | Sunsetting of SMZs | TBD |  | DOC: O/S; A: DOC | DOC | PH | DOC | A
| WORKLOAD SUBTOTAL: FMP Projects listed Above. Target maximum is 6 |  |  | 2 | 4.5 | 6 | 7.5 | 6.5 | 8.5 | 6.5 | 6 | 6.5
| FMP ITEMS PER MEETING: Target maximum is 8 |  |  | 4 | 6 | 10 | 9 | 11 | 11 | 10 | 10 | 9
| OTHER COUNCIL ACTIVITIES |  |  | 2024-12-01 | 2025-03-01 | 2025-06-01 | 2025-09-01 | 2025-12-01 | 2026-03-02 | 2026-06-03 | 2026-09-04 | 2026-12-05
|  | EVERY MEETING - Liaison, Agency, Staff Reports |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | AP or SSC Selection (CLOSED) | KI/CC | 2024-12-01: 0.5; 2025-06-01: 0.5; 2025-12-01: 0.5; 2026-06-03: 0.5; 2026-12-05: 0.5
|  | SEDAR Committee | CC | 2024-12-01: 0.5; 2025-03-01: 0.5; 2025-09-01: 0.5; 2026-03-02: 0.5; 2026-09-04: 0.5
|  | Citizen Science Committee | JB | 2024-12-01: 1; 2025-06-01: 0.5; 2025-12-01: 0.5; 2026-06-03: 0.5; 2026-12-05: 0.5
|  | Habitat Committee (For March includes Coral 10 and AP report) | KH | 2025-03-01: 0; 2025-09-01: 0.5; 2026-03-02: 0.5; 2026-09-04: 0.5
|  | Outreach and Communications Committee | KI/NS | 2025-06-01: 0.5; 2025-12-01: 0.5; 2026-06-03: 0.5; 2026-12-05: 0.5
|  | SG Commercial Sub-Committee Feedback | MS | 2024-12-01: 0.5; 2025-06-01: 0.5
|  | Mackerel Port Meetings | CW | bar: 2025-03-01
|  | Headboat Vessel Limit Amendment Discussion | TBD | 2024-12-01: 0.5
|  | Snapper Grouper MSE Results | TBD | bar: 2024-12-01
|  | NMFS Red Snapper Secretarial Amendment | SERO | 2025-03-01: 0.5
|  | Dolphin MSE Progress (For Dec also discussion of DW Reg AM 3) | SEFSC/JH | 2024-12-01: 0.5; 2025-03-01: 0.5; 2025-06-01: 0.5; 2025-09-01: 0.5; 2025-12-01: 0.5 | Needed to discuss Council feedback for the MSE
|  | Allocation Reviews (per trigger policy) | JH | 2024-12-01: 0.5
|  | Stock Risk Rating & Assessment Review and Response Planning |  | 2024-12-01: 0.5
|  | Stakeholder Engagement Meetings Discussion | CW | 2024-12-01: 0.5
| WORKLOAD SUBTOTAL: Recurring and special topic activities |  |  | 6.5 | 3 | 3 | 2 | 2.5 | 1.5 | 2 | 1.5 | 2
| WORKLOAD TOTAL : FMP projects (Line 26) + Recurring & special topics (Line 41). Target is maximum 8 |  |  | 8.5 | 7.5 | 9 | 9.5 | 9 | 10 | 8.5 | 7.5 | 8.5
Other Amendments underway, requested, or anticipated in 2025-2027
| Committee | Amendment | Tentative Start
| SG | Snowy Grouper Assessment Response | 2026-12-01
| SL and SG | Spiny lobster & SG permit holder item | 2026-12-01
| DW | Dolphin Wahoo Pelagic Longline Measures | Completion of Dolphin MSE
| DW | Dolphin Wahoo regional management and other items | Completion of Dolphin MSE
| SG | Align the opening of recreational seasons for deepwater species | Part of Blueline Tilefish AM
| SG | FW AM to examine scamp retention limits | ?
| Coral | Deepwater Coral HAPC Expansion | 2027-03-01
Other Activities
| SG | Update Jacks Complex and Atlantic Spadefish Accountability Measures | ?
| SG | Modify Recreational Black Grouper Regulations | Part of SG MSE AM

## General Timeline
Generalized FMP Timeline Example
Illustrates a signficant FMP Amendment - not a framework to update ACL
Plan Code | Clock | eg mo | Council Meeting Activity | Note | More Info
AR | 1 | June | Assessment Report Presented (or FMP started formally) | Also present general fishery info - landings+effort trends, recent years, by state, season, etc; catch per trip frequency, recent mgmt changes or AMs implemented | When initiated by an AR: Provide ACL options. - there really are not that many, at least for FMPs without allocation changes. When not an AR: discuss the problem Council wishes to solve and why.
(AP),(SSC) | 4 | Oct | AP or SSC review | Include in council meet schedule to show work is progressing, explain why skipping a meeting. Deadline to Obtain official IPT dataset for analysis | Intent-bring in AP sooner, help develop response to stock condition or the problems to solve, help develop items to scope
S | 6 | Dec | Approve for Scoping | Council select the preferred ACL at this meeting | Approve ACLs by this meeting - critical to the evaluations of specific actions that will follow
DOC | 9 | March | Review Actions-Alternatives | Review scoping comments, finalize range of actions and alternatives
DOC | 12 | June | Review Actions-Alternatives, Select Preferreds | Review evaluation of actions and alternatives. Select preferred options where appropriate and feasible. Need for this or an additioanl meeting of this type determined by FMP complexity and number of actions. | Consider dividing topics across meeting for a complex FMP with many actions - e.g., one meeting on rec topics, one on comm topics, so that if several meetings needed, avoid starting each meeting by discussing action 1 and going over the entire FMP in action order. May add in additional SSC or AP meetings between OS and PH as needed
PH | 15 | Sept | Review Actions-Alternatives, Select preferreds, and Approve for hearings | Review evaluation of actions and alternatives, select preferred alternatives for hearing
doc | 18 | Dec | Review hearing comments, revise preferreds
A | 21 | March | review any additional analysis, approve for submission | Need to have codified text in time to review
| 24 | June | FMP Submitted by | final draft, codified, etc - submit before the next meeting