## HOW WORKLOAD IS ESTIMATED
Example discussion level at various stages of FMP development.
And Color Coding Scheme in the following sheets
Type of Discussion | Workload Estimation Weight | Council Meeting Time
Initial Options Paper | 0.5 | 1-2h
Options discussions, review AP/SSC comments | 1 | 3-4h
Review and approve for Hearing | 1 | 3-4h
Address hearing comments | 0.5 | 1-2h
Final Approval | 0.5 | 1-2h
Council Meeting Workload Estimation and Time Management Approach
Council previously directed that 6 FMPs were the most that could be addressed in a Council meeting. Over the last several years this has proven to be an accurate estimate.
To address the current excessive workload and backlog of projects, we attempted to refine this some by considering the level of discussion that occurs at different stages of FMP development. For example, the first time the Council considers an amendment and reviews a general options paper will take less discussion time than a later discussion when actions are reviewed and preferred alternatives selected.
We weighted the different discussion stages as either 1 or 0.5. Summing these weights for a meeting gives an estimate of the discussion time needed. Keeping the sum at or below 6 should keep the workload manageable within a single meeting.
Estimating the workload in this manner for several years forward, and through final approval of projects, provides a long-term persepective on the FMP workload. Individual FMP project schedules may need to be adjusted to address future meetings if the workload rating gets too high. It will also allow us to illustrate the impacts on other projects and on future meeting workloads when projects fall behind.

## 2024 - 2026 WorkPlan
| SAFMC 2025-2027 WORKPLAN - INCORPORATING PROJECTS UNDERWAY AND UPCOMING ASSESSMENTS |  |  | 2025 Q2- Revised per the Council's March 2025 Meeting
Amendments with statutory deadline
| Amend # | Amendment | SAFMC Lead | 2025-06-01 | 2025-09-01 | 2025-12-01 | 2026-03-02 | 2026-06-03 | 2026-09-04 | 2026-12-05 | 2027-03-06 |  |  | Amendments that do not respond to a stock assessment or change to catch level recommendations
UNDERWAY |  | STATUTORY DEADLINE WORKLOAD SUBTOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Indicates that action is being taken but will not be discussed at the Council meeting (no time allocated toward the workload calculations)
| SG?? | Long-term RS response (MSE, SG fishery management measures) | TBD |  | S | DOC | DOC | PH | DOC | A
| SG 56 | Black Sea Bass Assessment Response | Mike | DOC | DOC | PH | DOC | A |  |  |  | Added a meeting pending catch level recommendation
| SG 46 | Private Recreational Permitting and Education | JohnH | 2025-06-01: PH; 2025-09-01: DOC; 2025-12-01: A
| SG 44 | Yellowtail Snapper and Mutton Snapper Assessment Response (Joint w/ Gulf as lead) | Allie | 2025-06-01: S; 2025-09-01: DOC; 2025-12-01: PH; 2026-03-02: A
| SG ?? | Yellowtail Snapper and Mutton Snapper Managememnt Changes | Allie |  |  | S | DOC | DOC | PH | DOC | A | Moved up in the timeline to minimize time between amendments going final.
| SG ABV FW 4 | Golden Tilefish Assement Response | Mike | 2025-06-01: DOC; 2025-09-01: PH; 2025-12-01: A | Added a meeting per landings descrepancy
| DW Reg 3 | Dolphin (Recreational Measures + MSE Modeling) | JohnH | 2026-06-03: DOC; 2026-09-04: DOC; 2026-12-05: PH; 2027-03-06: DOC | A | Delayed pending MSE results
| Coral 11/Shrimp 12 | SFAA in Oculina HAPC northern extension | Kathleen & Allie | 2025-06-01: PH; 2025-09-01: DOC; 2025-12-01: A | Timeline depends on availability of permit data. Approval could be moved up to September
| SG/CMP/DW | For-Hire Limited Entry | JohnH/Myra |  | DOC | S | DOC | DOC | PH | DOC | A | Timeline depends on availability of permit data
| SG/CMP/DW | For-Hire Electronic Reporting Improvement | Myra/JohnH | DOC | DOC | PH | DOC | A |  |  |  | Timeline depends on availability of permit data
|  | UNDERWAY FMP WORKLOAD SUBTOTAL |  | 3.5 | 4 | 6 | 4 | 3.5 | 3 | 2.5 | 1.5
PLANNED | CMP | Plan AM Spanish Mackerel Assessment Response | Christina | S | DOC | DOC | PH | DOC | A
| SG | Blueline Tilefish Assessment Response, Deepwater Species Management Items | MIke | AR | (AP) | S | DOC | DOC | PH | DOC | A
| SG | Unassessed Stocks Catch Levels | Mike |  | (SSC) |  | AR | S | DOC | DOC | PH | DOC | A | Suggest removing from planned amendments and re-visit once revised MRIP FES estimates are available and the Council has made a decision on SG FMU species
| SG | Hogfish Assessment Response | TBD |  |  |  | AR | S | DOC | DOC | PH | DOC | A
| SG | Black Grouper Assessment or MSE Response | TBD | 2026-06-03: AR; 2026-09-04: S; 2026-12-05: DOC; 2027-03-06: DOC | PH | DOC | A
| SG 60 | SG Commercial Fishery Amendment | TBD |  |  | S | DOC | DOC | PH | DOC | A | Timeline depends on availability of permit data and finalizing ABV FW 4
| SG | Sunsetting of SMZs | TBD | 2026-09-04: S; 2026-12-05: DOC; 2027-03-06: DOC | PH | DOC | A
| WORKLOAD SUBTOTAL: FMP Projects listed Above. Target maximum is 6 |  |  | 4.5 | 5 | 7.5 | 8 | 7 | 8.5 | 6.5 | 5.5
| FMP ITEMS PER MEETING: Target maximum is 8 |  |  | 8 | 9 | 12 | 11 | 12 | 11 | 10 | 9
| OTHER COUNCIL ACTIVITIES |  |  | 2025-06-01 | 2025-09-01 | 2025-12-01 | 2026-03-02 | 2026-06-03 | 2026-09-04 | 2026-12-05 | 2026-12-06
|  | EVERY MEETING - Liaison, Agency, Staff Reports |  | 0.25 | 0.5 | 0.25 | 0.5 | 0.25 | 0.5 | 0.25 | 0.5 | Every other meeting for state agency and federal LE updates
|  | AP or SSC Selection (CLOSED) | KI/JC | 2025-06-01: 0.5; 2025-12-01: 0.5; 2026-06-03: 0.5; 2026-12-05: 0.5
|  | SEDAR Committee | CC | 2025-09-01: 0.5; 2026-03-02: 0.5; 2026-09-04: 0.5; 2026-12-06: 0.5
|  | Citizen Science Committee | JB | 2025-12-01: 0.5; 2026-06-03: 0.5; 2026-12-05: 0.5
|  | Habitat Committee (meeting time in 2025 accounted for under Coral 11/Shrimp 12) | KH | 0 | 0 |  | 0.5 |  | 0.5 |  | 0.5
|  | Outreach and Communications Committee | KI/NS | 2026-06-03: 0.5; 2026-12-05: 0.5
|  | SG Commercial Sub-Committee Feedback | MS | 2025-06-01: 0.5
|  | Headboat Vessel Limit Amendment Discussion | CC | 2025-06-01: 0.5
|  | Snapper Grouper MSE Results | CC | 2026-12-05: 0.5
|  | MSY Proxy/SPR Presentation | FWRI/SEFSC | 2025-06-01: 0.5
|  | OST presentation relating to AM 46 (meeting time accounted for under AM 46) | OST | 2025-06-01: 0
|  | Council Research and Monitoring Plan | CC | 2025-06-01: 0.5
|  | NMFS Red Snapper Secretarial Amendment Update | SERO | 2025-06-01: 0.5
|  | Evaluation of species in SG FMU | MS | 2025-06-01: 0.5
|  | Standardized Bycatch Reduction Methodology (SBRM) Review | TBD | 2026-12-05: 0.5
|  | Update on MRIP pilot study and changes to FES estimates | OST | 2025-09-01: 0.5
|  | Best Fishing Practices Update | AO/GW/CW | bar: 2025-09-01
|  | Lines of Communication Meetings Summary | CW | 2025-12-01: 0.5; 2026-03-02: 0.5
|  | Allocation review for species meeting the review trigger policy | JH | 2025-09-01: 0.5
|  | Dolphin MSE Feedback | SEFSC | 2025-09-01: 0.5; 2025-12-01: 0.5; 2026-03-02: 0.5 | Needed to discuss Council feedback for the MSE
| WORKLOAD SUBTOTAL: Recurring and special topic activities |  |  | 3.75 | 3.5 | 2.25 | 2.5 | 1.75 | 1.5 | 2.75 | 1.5
| WORKLOAD TOTAL : FMP projects (Line 26) + Recurring & special topics (Line 41). Target is maximum 8 |  |  | 8.25 | 8.5 | 9.75 | 10.5 | 8.75 | 10 | 9.25 | 7
Other Amendments requested or anticipated in 2025-2027
| Committee | Amendment | Tentative Start
| SG | Snowy Grouper Assessment Response | 2026-12-01
| SL and SG | Spiny lobster & SG permit holder item | 2026-12-01
| DW | Dolphin Wahoo Pelagic Longline Measures | Completion of Dolphin MSE
| DW | Dolphin Wahoo regional management and other items | Completion of Dolphin MSE
| SG | Align the opening of recreational seasons for deepwater species | Part of Blueline Tilefish AM
| SG | FW AM to examine scamp retention limits | ?
| Coral | Deepwater Coral HAPC Expansion | 2027-03-01
Other Activities
| SG | Update Jacks Complex and Atlantic Spadefish Accountability Measures | ?
| SG | Modify Recreational Black Grouper Regulations | After BG MSE

## General Timeline
Generalized FMP Timeline Example
Illustrates a signficant FMP Amendment - not a framework to update ACL
Plan Code | Clock | eg mo | Council Meeting Activity | Note | More Info
AR | 1 | June | Assessment Report Presented (or FMP started formally) | Also present general fishery info - landings+effort trends, recent years, by state, season, etc; catch per trip frequency, recent mgmt changes or AMs implemented | When initiated by an AR: Provide ACL options. - there really are not that many, at least for FMPs without allocation changes. When not an AR: discuss the problem Council wishes to solve and why.
(AP),(SSC) | 4 | Oct | AP or SSC review | Include in council meet schedule to show work is progressing, explain why skipping a meeting. Deadline to Obtain official IPT dataset for analysis | Intent-bring in AP sooner, help develop response to stock condition or the problems to solve, help develop items to scope
S | 6 | Dec | Approve for Scoping | Council select the preferred ACL at this meeting | Approve ACLs by this meeting - critical to the evaluations of specific actions that will follow
DOC | 9 | March | Review Actions-Alternatives | Review scoping comments, finalize range of actions and alternatives
DOC | 12 | June | Review Actions-Alternatives, Select Preferreds | Review evaluation of actions and alternatives. Select preferred options where appropriate and feasible. Need for this or an additioanl meeting of this type determined by FMP complexity and number of actions. | Consider dividing topics across meeting for a complex FMP with many actions - e.g., one meeting on rec topics, one on comm topics, so that if several meetings needed, avoid starting each meeting by discussing action 1 and going over the entire FMP in action order. May add in additional SSC or AP meetings between OS and PH as needed
PH | 15 | Sept | Review Actions-Alternatives, Select preferreds, and Approve for hearings | Review evaluation of actions and alternatives, select preferred alternatives for hearing
doc | 18 | Dec | Review hearing comments, revise preferreds
A | 21 | March | review any additional analysis, approve for submission | Need to have codified text in time to review
| 24 | June | FMP Submitted by | final draft, codified, etc - submit before the next meeting