## HOW WORKLOAD IS ESTIMATED
Example discussion level at various stages of FMP development.
And Color Coding Scheme in the following sheets
Type of Discussion | Workload Estimation Weight | Council Meeting Time
Initial Options Paper | 0.5 | 1-2h
Options discussions, review AP/SSC comments | 1 | 3-4h
Review and approve for Hearing | 1 | 3-4h
Address hearing comments | 1 | 1-2h
Final Approval | 1 | 1-2h
Council Meeting Workload Estimation and Time Management Approach
Council previously directed that 6 FMPs were the most that could be addressed in a Council meeting. Over the last several years this has proven to be an accurate estimate.
To address the current excessive workload and backlog of projects, we attempted to refine this some by considering the level of discussion that occurs at different stages of FMP development. For example, the first time the Council considers an amendment and reviews a general options paper will take less discussion time than a later discussion when actions are reviewed and preferred alternatives selected.
We weighted the different discussion stages as either 1 or 0.5. Summing these weights for a meeting gives an estimate of the discussion time needed. Keeping the sum at or below 6 should keep the workload manageable within a single meeting.
Estimating the workload in this manner for several years forward, and through final approval of projects, provides a long-term persepective on the FMP workload. Individual FMP project schedules may need to be adjusted to address future meetings if the workload rating gets too high. It will also allow us to illustrate the impacts on other projects and on future meeting workloads when projects fall behind.

## 2021-2022 WorkPlan
SAFMC 2021-2022 WORKPLAN - INCORPORATING PROJECTS UNDERWAY AND UPCOMING ASSESSMENTS
Actions to be completed prior to the scheduled Council Meeting
Amend # | Amendment | SAFMC Lead | 2020-12-20 | 2021-03-01 | 2021-06-01 | 2021-09-01 | 2021-12-01 | 2022-03-01 | 2022-06-01 | 2022-09-01 | 2022-12-01 | 2023-03-01 | 2023-06-01 | 2023-09-01
DW 10 | ACLs, Alloc., AMs, Other | JohnH | 2020-12-20: PH; 2021-03-01: DOC; 2021-06-01: A
SG 50 | Red Porgy Assess/Alloc/Rebuiding | Myra | 2020-12-20: Doc; 2021-03-01: DOC; 2021-06-01: DOC; 2021-09-01: PH; 2021-12-01: DOC; 2022-03-01: A
SGXX | Red Snapper ACL+Allocation | JohnH | 2021-06-01: AR; 2021-09-01: O/S; 2021-12-01: PH; 2022-03-01: DOC; 2022-06-01: A
SG 48 | Wreckfish ITQ Modernization | Christina | 2020-12-20: O/S; 2021-03-01: DOC; 2021-06-01: (AP?); 2021-09-01: PH; 2021-12-01: A
CMP XX | King Mack Assess Response | Christina | 2020-12-20: O/S; 2021-03-01: DOC; 2021-06-01: PH; 2021-09-01: A
SGA44 | YT Snapper Assess/Allocate/longterm | MikeS | AR | (AP) | O/S | DOC | DOC | PH | doc | A
SG XX | Greater AJ Assess/Allocate | MikeS | 2020-12-20: O; 2021-03-01: S; 2021-06-01: DOC; 2021-09-01: PH; 2021-12-01: DOC; 2022-03-01: A
CORAL 10 | Oculina Boundary | Roger | 2020-12-20: O/S; 2021-03-01: PH; 2021-06-01: A
SG45/GC11/Sa4/C11 | ABC Control Rule | MikeS | 2020-12-20: Doc; 2021-03-01: (SSC); 2021-06-01: DOC; 2021-09-01: (SSC); 2021-12-01: PH; 2022-03-01: A
| Snowy Grouper Assess/Allocate | TBD |  | AR | (AP) | O/S | DOC | DOC | PH | DOC | A
| Gag Assess/Allocate | TBD |  | (SSC) | AR | (AP) | O/S | DOC | DOC | PH | DOC | A
| golden Tilefish Assessment | TBD |  | (SSC) | AR | (AP) | O/S | DOC | PH | DOC | A
| Spanish Mackerel Assessment | TBD | 2022-03-01: (SSC); 2022-06-01: AR; 2022-09-01: (AP); 2022-12-01: O/S; 2023-03-01: DOC; 2023-06-01: PH; 2023-09-01: DOC | A
| New Project 1 |  |  |  |  | AR | (AP) | O/S | DOC | DOC | PH | doc | A
| New Project 2 |  | 2022-03-01: AR; 2022-06-01: (AP); 2022-09-01: O/S; 2022-12-01: DOC; 2023-03-01: DOC; 2023-06-01: PH; 2023-09-01: doc | A
| New Project 3 |  | 2022-09-01: AR; 2022-12-01: (AP); 2023-03-01: O/S; 2023-06-01: DOC; 2023-09-01: DOC | PH | doc | A
| Scamp Assessment |  | 2022-12-01: AR; 2023-03-01: (AP); 2023-06-01: O/S; 2023-09-01: DOC | DOC | PH | doc | A
Workload Subtotal: Current FMP Projects listed Above |  |  | 4.5 | 5.5 | 6.5 | 5 | 6.5 | 6.5 | 5 | 4.5 | 4.5 | 3.5 | 4
RECURRING & | Selection AP or SSC | Kim/MikeE | 2020-12-20: 1; 2021-06-01: 0.5; 2021-12-01: 0.5; 2022-06-01: 0.5; 2022-12-01: 0.5
| SEDAR Committee | Chip | 2021-03-01: 0.5; 2021-09-01: 0.5; 2022-03-01: 0.5; 2022-09-01: 0.5
| Citizen Science Committee | Julia | 2020-12-20: 0.5; 2021-06-01: 0.5; 2021-12-01: 0.5; 2022-06-01: 0.5; 2022-12-01: 0.5
| Habitat Committee | Roger | 2020-12-20: 0.5; 2021-03-01: 0.5; 2021-09-01: 0.5; 2022-03-01: 0.5
| Allocation Trees Blueprint | BC/JH/CW | 2020-12-20: update; 2021-03-01: Update; 2021-06-01: 0.5; 2021-09-01: 0.5
| SpeciesShifts ScenarioPlanning | Myra | 2020-12-20: Update; 2021-03-01: Update
| Joint WorkGroup Rec Sec 102 | JC | 2021-03-01: 0.5; 2021-12-01: 0.5
| Pvt SG Rec Data workgroup | Myra | 2020-12-20: Update; 2021-03-01: Update; 2021-06-01: Update; 2021-09-01: 0.5
INFO PAPER | SG EC SPECIES | MYRA | 2020-12-20: 0.5
Habitat | EwE Review | Roger | 2020-12-20: 0.5
INFO PAPER | SG 2for1 permit eval (from EO) |  | 2021-09-01: 0.5
WORKLOAD SUBTOTAL - Recurring and special topic activities |  |  | 3 | 1.5 | 1.5 | 2.5 | 1.5 | 1 | 1 | 0.5 | 1
WORKLOAD TOTAL : Current FMP projects (line 15) + recurring & special topics (Line 22) |  |  | 7.5 | 7 | 8 | 7.5 | 8 | 7.5 | 6 | 5 | 5.5
Other Amendments underway, requested, or anticipated to address assessments expected in 2022-2023 | bar: 2020-12-20 to 2021-09-01
Amend # | Amendment | Target Start | 2020-12-20: NOTE
Comp XX | Allocation, Unassessed Spp. ABC/ACL |  | 2020-12-20: Propose combining with EC species action
SL RA5 | SG1 & lobster tailing permits |  | 2020-12-20: Added 2019
SG XX | Deep water Species Allocation |  | 2020-12-20: Propose removing as stand alone action
COMPXX | SBRM Amend |  | 2020-12-20: Need TBD 9/2021
Amend XX | Com Electronic Logbooks |  | 2020-12-20: Priority 11 in EO response; Plan to start after voluntary program is running (expect in 2021) and evaluated
DW 13 | Dolphin PLL Fishery
Dolphin Regional Management
| Black Sea bass Assessment | 2023-12-01
| Vermilion Snapper Assessment | 2023-12-01
| Red Grouper Assessment | 2024-03-01
Other Activities | bar: 2020-12-20
info paper | Almaco Jack White Paper
workshop | Mackerel Port Meetings
Illustrates when new projects can come online - assuming no existing projects fall behind!

## General Timeline
Generalized FMP Timeline Example
Illustrates a signficant FMP Amendment - not a framework to update ACL
Plan Code | Clock | eg mo | Council Meeting Activity | Note | More Info
AR | 1 | June | Assessment Report Presented (or FMP started formally) | Also present general fishery info - landings+effort trends, recent years, by state, season, etc; catch per trip frequency, recent mgmt changes or AMs implemented | When initiated by an AR: Provide ACL options. - there really are not that many, at least for FMPs without allocation changes. When not an AR: discuss the problem Council wishes to solve and why.
(AP),(SSC) | 4 | Oct | AP or SSC review | Include in council meet schedule to show work is progressing, explain why skipping a meeting. Deadline to Obtain official IPT dataset for analysis | Intent-bring in AP sooner, help develop response to stock condition or the problems to solve, help develop items to scope
O/S | 6 | Dec | Present Options, Approve for Scoping | Council select the preferred ACL at this meeting | Approve ACLs by this meeting - critical to the evaluations of specific actions that will follow
DOC | 9 | March | Review Actions-Alternatives | Review scoping comments, finalize range of actions and alternatives
DOC | 12 | June | Review Actions-Alternatives, Select Preferreds | Review evaluation of actions and alternatives. Select preferred options where appropriate and feasible. Need for this or an additioanl meeting of this type determined by FMP complexity and number of actions. | Consider dividing topics across meeting for a complex FMP with many actions - e.g., one meeting on rec topics, one on comm topics, so that if several meetings needed, avoid starting each meeting by discussing action 1 and going over the entire FMP in action order. May add in additional SSC or AP meetings between OS and PH as needed
PH | 15 | Sept | Review Actions-Alternatives, Select preferreds, and Approve for hearings | Review evaluation of actions and alternatives, select preferred alternatives for hearing
doc | 18 | Dec | Review hearing comments, revise preferreds
A | 21 | March | review any additional analysis, approve for submission | Need to have codified text in time to review
| 24 | June | FMP Submitted by | final draft, codified, etc - submit before the next meeting