## HOW WORKLOAD IS ESTIMATED
Example discussion level at various stages of FMP development.
And Color Coding Scheme in the following sheets
Type of Discussion | Workload Estimation Weight | Council Meeting Time
Initial Options Paper | 0.5 | 1-2h
Options discussions, review AP/SSC comments | 1 | 3-4h
Review and approve for Hearing | 1 | 3-4h
Address hearing comments | 1 | 1-2h
Final Approval | 1 | 1-2h
Council Meeting Workload Estimation and Time Management Approach
Council previously directed that 6 FMPs were the most that could be addressed in a Council meeting. Over the last several years this has proven to be an accurate estimate.
To address the current excessive workload and backlog of projects, we attempted to refine this some by considering the level of discussion that occurs at different stages of FMP development. For example, the first time the Council considers an amendment and reviews a general options paper will take less discussion time than a later discussion when actions are reviewed and preferred alternatives selected.
We weighted the different discussion stages as either 1 or 0.5. Summing these weights for a meeting gives an estimate of the discussion time needed. Keeping the sum at or below 6 should keep the workload manageable within a single meeting.
Estimating the workload in this manner for several years forward, and through final approval of projects, provides a long-term persepective on the FMP workload. Individual FMP project schedules may need to be adjusted to address future meetings if the workload rating gets too high. It will also allow us to illustrate the impacts on other projects and on future meeting workloads when projects fall behind.

## 2021-2022 WorkPlan
SAFMC 2021-2022 WORKPLAN - INCORPORATING PROJECTS UNDERWAY AND UPCOMING ASSESSMENTS | [6 empty] | 2021 Q2 DRAFT FOR JUNE MEETING
Amend # | Amendment | SAFMC Lead | 2021-06-01 | 2021-09-01 | 2021-12-01 | 2022-03-01 | 2022-06-01 | 2022-09-01 | 2022-12-01 | 2023-03-01 | 2023-06-01 | 2023-09-01 |  |  |  | equals amendments that don't respond to a stock assessment
DW 10 | Dolphin Wahoo ACLs-AMs | JohnH | bar: 2021-06-01
SG 50 | Red Porgy Rebuilding/Allocate | Myra | 2021-06-01: DOC; 2021-09-01: PH; 2021-12-01: DOC; 2022-03-01: A
SGXX | Red Snapper Assess Response | MikeS/JohnH | AR | O/S | PH? | DOC | A? |  |  |  |  | Will receive guidance from Council in June
SG 48 | Wreckfish ITQ Modernization | Christina | (AP?) | DOC | DOC | PH | DOC | A | [7 empty] | Timeline for PH delayed by one meeting per concerns over data access and staff availabilty |  | Consider extending one meeting
CMP 34 | King Mack Assess Response | Christina | 2021-06-01: PH; 2021-09-01: DOC; 2021-12-01: A | Approval extended by one meeting
SGA44 | YT Snapper Assess/Allocate/longterm | Myra | O | O/S | DOC | DOC | PH | DOC | A |  |  | Will receive guidance from Council in June. Timeline may shift depending on whether joinlty developed amendment.
SG 49 | Greater AJ Assess/Allocate | MikeS | 2021-09-01: DOC; 2021-12-01: PH; 2022-03-01: DOC; 2022-06-01: A; 2023-09-01: Timeline to shift by one meeting pending guidance in June (add MSL action?).
CORAL 10 | Oculina Boundary | Roger | 2021-06-01: DOC; 2021-09-01: A
SG45/GC11/Sa4/C11 | ABC Control Rule | MikeS |  | DOC | DOC? | DOC | PH | DOC | A | [7 empty] | Added a meeting before PH and in December. December meeting would be an hour or less and can be bumped if need be.
| Snowy Grouper Assess Response | Allie | (AP) | O/S | DOC | DOC | PH | DOC | A
| Gag Assess Response | TBD | AR | (AP) | O/S | DOC | DOC | PH | DOC | A |  | Expect letter from NMFS that will start statutory deadline clock for rebuilding plan
| Golden Tilefish Assess Response | TBD | AR | (AP) | O/S | DOC | PH | DOC | A
CMP 32 | Gulf Cobia Amendment (Gulf is lead) | Christina | 2021-06-01: DOC; 2021-09-01: PH; 2021-12-01: A?; 2022-03-01: A? | Added for Council time budgeting
CMP 33 | Gulf King Mackerel (Gulf is lead) | Christina | 2021-12-01: DOC?; 2022-03-01: DOC? | Added for Council time budgeting
| Spanish Mackerel Assess Response | Christina |  |  |  | (SSC) | AR | (AP) | O/S | DOC | PH | DOC | A
| DOLPHIN WAHOO FRAMEWORKS (Rec Focused) | JohnH | (Plan) | INFO | O/S | AP | DOC | PH | DOC | A
| NEW 2021-1 (Dolphin LongLine) | JohnH |  |  |  | INFO | O/S | DOC | DOC | PH | DOC | A |  |  |  |  | Moved back by one meeting
| NEW 2022-1 (Com Logbooks) |  | (Plan) |  |  |  | INFO | (AP) | O/S | DOC | DOC | PH | DOC | A |  |  | Moved back by one meeting
| NEW 2022-2 |  | 2022-09-01: AR; 2022-12-01: (AP); 2023-03-01: O/S; 2023-06-01: DOC; 2023-09-01: DOC | PH | DOC | A
| Scamp Response |  | 2022-12-01: AR; 2023-03-01: (AP); 2023-06-01: O/S; 2023-09-01: DOC | DOC | PH | DOC | A
Workload Subtotal: Current FMP Projects listed Above |  |  | 6.5 | 6.5 | 7 | 7.5 | 8.5 | 5 | 6 | 4.5 | 4 | 3.5 | 3 | 1.5 | 1 | 0.5
OTHER ACTIVITIES
| Selection AP or SSC | KI/CC | 2021-06-01: 0.5; 2021-12-01: 0.5; 2022-06-01: 0.5; 2022-12-01: 0.5
| SEDAR Committee | CC | 2021-09-01: 0.5; 2022-03-01: 0.5; 2022-09-01: 0.5
| Citizen Science Committee | JB | 2021-12-01: 0.5; 2022-06-01: 0.5; 2022-12-01: 0.5
| Habitat Committee | RP | 2021-09-01: Update; 2022-03-01: 0.5; 2022-09-01: 0.5; 2023-06-01: Business OTHER than Coral 10 or Blueprint
| Law Enforcement Committee | MB | 2021-06-01: 0.5; 2021-09-01: LEOY
| Allocation Trees Blueprint | CW/JH/MS | 2021-06-01: Update; 2021-09-01: 0.5; 2021-12-01: 0.5
| SpeciesShifts ScenarioPlanning | RP | 2021-06-01: Update; 2021-09-01: Update
| Joint WorkGroup Rec Sec 102 | JC | 2021-06-01: Update; 2021-12-01: 0.5?
| SAFMC Rec Data workgroup | MB/JC | 2021-06-01: Update; 2021-09-01: 0.5; 2021-12-01: 0.5?
| SG 2for1 permit eval (from EO) | MB/CW/JH | 2021-09-01: 0.5
| Habitat Blueprint | MB/JC/RP | 2021-06-01: Update; 2021-09-01: Update; 2021-12-01: Approve
WORKLOAD SUBTOTAL - Recurring and special topic activities |  |  | 1 | 2 | 3 | 1 | 1 | 1 | 1
WORKLOAD TOTAL : Current FMP projects (line 15) + recurring & special topics (Line 22) |  |  | 7.5 | 8.5 | 10 | 8.5 | 9.5 | 6 | 7
Other Amendments underway, requested, or anticipated to address assessments expected in 2022-2023 | bar: 2021-06-01 to 2021-12-01
Committee | Amendment | Target Start
SG | Unassessed ABC-ACL-EC | ? | 2021-06-01: Include Almaco Jack and request clarification if intent is to start after ABC CR Amendment
SPL | SG1 & lobster tailing permits | ? | 2021-06-01: Request clarification if still needed
COMP | SBRM Amend | ?
DW | Dolphin Regional Management | ? | 2021-06-01: Request clarification if still needed
SG | Black Sea bass Assessment | 2023-12-01
SG | Vermilion Snapper Assessment | 2023-12-01
SG | Red Grouper Assessment | 2024-03-01
SG | Mutton Assessment | 2023-06-01
Other Activities
workshop | Mackerel Port Meetings | ?

## General Timeline
Generalized FMP Timeline Example
Illustrates a signficant FMP Amendment - not a framework to update ACL
Plan Code | Clock | eg mo | Council Meeting Activity | Note | More Info
AR | 1 | June | Assessment Report Presented (or FMP started formally) | Also present general fishery info - landings+effort trends, recent years, by state, season, etc; catch per trip frequency, recent mgmt changes or AMs implemented | When initiated by an AR: Provide ACL options. - there really are not that many, at least for FMPs without allocation changes. When not an AR: discuss the problem Council wishes to solve and why.
(AP),(SSC) | 4 | Oct | AP or SSC review | Include in council meet schedule to show work is progressing, explain why skipping a meeting. Deadline to Obtain official IPT dataset for analysis | Intent-bring in AP sooner, help develop response to stock condition or the problems to solve, help develop items to scope
O/S | 6 | Dec | Present Options, Approve for Scoping | Council select the preferred ACL at this meeting | Approve ACLs by this meeting - critical to the evaluations of specific actions that will follow
DOC | 9 | March | Review Actions-Alternatives | Review scoping comments, finalize range of actions and alternatives
DOC | 12 | June | Review Actions-Alternatives, Select Preferreds | Review evaluation of actions and alternatives. Select preferred options where appropriate and feasible. Need for this or an additioanl meeting of this type determined by FMP complexity and number of actions. | Consider dividing topics across meeting for a complex FMP with many actions - e.g., one meeting on rec topics, one on comm topics, so that if several meetings needed, avoid starting each meeting by discussing action 1 and going over the entire FMP in action order. May add in additional SSC or AP meetings between OS and PH as needed
PH | 15 | Sept | Review Actions-Alternatives, Select preferreds, and Approve for hearings | Review evaluation of actions and alternatives, select preferred alternatives for hearing
doc | 18 | Dec | Review hearing comments, revise preferreds
A | 21 | March | review any additional analysis, approve for submission | Need to have codified text in time to review
| 24 | June | FMP Submitted by | final draft, codified, etc - submit before the next meeting