## master
partner | heading | topic | status | status 2023 | status 2025 | Comments | 2023 update | Any Link (to publications, webpage, etc) | 2025 update | new links
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | • Operational assessment for Spanish Mackerel, mid-2020: | ongoing | completed | completed | cancelled | Completed | https://sedarweb.org/documents/sedar-78-stock-assessment-report-south-atlantic-spanish-mackerel-revised-july-2022/
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Updated maturity data from both sexes for fish below 275mm FL. | ongoing | ongoing | delayed | SCDNR SEAMAP Coastal Trawl Survey samples taken since the previous assessment have already been staged and there is an expectation that these samples will be taken and staged histologically moving forward. |  |  | no progress
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Evaluate stock structure using updated data and modern techniques, such as genetics. In particular evaluate if there is newer data available on steepness from other analyses of S-R for pelagic stocks with similar reproductive strategies. | delayed | delayed | delayed | lack of resources |  |  | no progress
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | • Operational assessment for Gag, mid-2020: | completed | completed | completed |  | Completed | https://sedarweb.org/documents/sedar-71-stock-assessment-report-south-atlantic-gag/
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Explore larval transport and modeling efforts associated with development of an IOOS to gain insight into larval connectivity and transport. | ongoing | completed | completed | Karnauskas, M, K Shertzer, CB Paris, N Farmer, T Switzer, S Loweree-Barbieri, GT Kellison, R He, AC Vaz. 2022. Source-sink recruitment of red snapper: Connectivity between the Gulf of Mexico and Atlantic Ocean. Fisheries Oceanography. https://doi.org/10.1111/fog.12607 Brothers JR, Shertzer KW, Karnauskas M, Vaz AC, Bacheler NM, Paris CB (2024) Connectivity of scamp Mycteroperca phenax populations in the United States Gulf of Mexico and Atlantic Ocean. Mar Ecol Prog Ser 750:133-152. https://doi.org/10.3354/meps14728 | A model-driven assessment of red snapper connectivity between Gulf and South Atlantic regions has been published. Assessments of regional connectivity for scamp have been submitted for publication. | https://onlinelibrary.wiley.com/doi/full/10.1111/fog.12607
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Develop a solution to address species mis-identification with Black Grouper. | completed | completed | completed | this was addressed as part of the Sedar 71 gag assessment (POC: Vivian Matter) but may need additional attention
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | • Red Snapper Operational Assessment, 2021: | completed | completed | completed |  | Completed | http://sedarweb.org/sedar-73-stock-assessment-report-south-atlantic-red-snapper
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Improved and updated bycatch mortality estimates | completed | completed | completed | completed as part of the stock assessment
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | • Gray Triggerfish Research Track Assessment 2022: | delayed | ongoing | completed |  | entering assessment phase as of 5/2023 | https://sedarweb.org/assessments/sedar-82/ | abandoned
SEFSC/SCDNR | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Address age determination issues for Gray Triggerfish by January 2020 so age structures can be evaluated for a research track assessment tentatively scheduled for 2021, including re-aging of the spines by the start of the RT. | delayed | ongoing | completed |  | The NMFS age validation study was completed (ms in journal review) and results shared with SCDNR, the other primary age data contributor. The study resulted in an update to the age reading methodology. The updated method was applied to a set of spines from Gulf of Mexico gray triggerfish which had validated age readings from otoliths compared to bomb radiocarbon (Chamberlin and Patterson, UFL). The new spine reading method produced ages for the GOM GTF consistent with the bomb radiocarbon levels; thus, the spine ages were validated. |  | aging issues unresolved
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | • Black Sea Bass Operational Assessment 2021: | delayed | completed | completed |  | Completed | https://sedarweb.org/documents/sedar-76-stock-assessment-report-south-atlantic-black-sea-bass/
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Investigate discard mortality due to hooks in shallow waters (<10m). | ongoing | completed | completed | addressed potential changes to discard mortality rates in the most recent stock assessment | addressed potential changes to discard mortality rates in the most recent stock assessment
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Recommend the use of more direct methods of estimating M, such as Tag-Recapture studies. | delayed | delayed | delayed | No effort toward this |  |  | no effort towards this
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | • Red Grouper Operational Assessment 2021: | delayed | ongoing | delayed | Red Grouper was put back on the SEDAR schedule to be completed as a benchmark assessment |  | https://sedarweb.org/assessments/sedar-86/ | abandoned due to 2 stock issue
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Evaluate sample size cutoffs for using age and length compositions. What should be the minimum standards, and how does this interplay with the number of age and length classes modeled in the assessment? | completed | completed | completed | see notes on Dirichlet multinomial
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Conduct a simulation study to evaluate the performance of the various likelihood formulations that have been used for fitting age and length composition data under sampling conditions realistic in the southeast U.S. | completed | completed | completed | models now use Dirichlet multinomial as best practice; Paper in review right now (lead author =Nick Fisch, UFL, NOAA pop dyn fellow)
FWRI | I. Short Term research needs for stock assessments to be completed in 2020-2023 | • Mutton Snapper Assessment, 2021: | ongoing | ongoing | completed | FWRI partners |  | https://sedarweb.org/assessments/sedar-79/
FWRI | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Evaluate the discard mortality estimates for Mutton Snapper and conduct studies to either confirm or refine these estimates. | ongoing | ongoing | completed | FWRI partners |  |  |  | https://sedarweb.org/documents/sedar-79-rd06-s74-ap-01-a-meta-analysis-of-red-snapper-lutjanus-campechanus-discard-mortality-in-the-gulf-of-mexico/
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Evaluate the conversion factors used to convert landed weight to whole weight. Preliminary comparisons suggest a lower percentage difference between gutted weight and whole weight at comparable sizes than is currently used. | ongoing | ongoing | ongoing | For which species...just mutton snapper? Though the task of updating W-W conversions would belong to the LH group, there is currently an FIS proposal for a morphometric database that once developed could be used to at least house the different conversions along with the metadata behind the conversions (year range, geographic range, sample sizes, etc). This would be a first step to evaluating existing conversion factors and would include all assessed stocks. Leadership could indicate support for this effort to FIS by the priority given to this project in PIMS. (VM)
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | • White Grunt Research Track Assessment, 2023 | delayed | delayed | delayed | delayed indefinitely |  |  | delayed indefinitely | 0
SCDNR | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Conduct stock identification studies for White Grunt. | delayed | delayed | delayed | O'Donnell et al. (2019) using genetic methods found that White Grunt should be separated into 2 stocks in the Atlantic (Carolinas and Southeast Florida including the Keys). O'Donnell, TP, Reichert, MJM, and Darden, TL. Genetic Population Structure of White Grunt in the Southeastern United States. North American Journal of Fisheries Management. 39(4): 725-737. |  |  | delayed indefinitely
SAFMC Research and Monitoring Prioritization
SEFSC/SCDNR | I. Short Term research needs for stock assessments to be completed in 2020-2023 | SERFS indices available for most species | completed | completed | completed | Trap- and video-based indices for priority species are generated and updated annually by SCDNR and SEFSC, respectively. Video indies can be viewed via the SEAFiSh data visualizer. |  | https://www.fisheries.noaa.gov/data-tools/southeast-abundance-fish-and-shrimp-data-visualizer | completed through 2024 for trap catches
II. Long Term research needs for stock assessments to be developed within the next 5 years.
• General assessment topics
SEFSC | II. Long Term research needs for stock assessments to be developed within the next 5 years. | o Evaluate assessment projection performance, considering their ability to estimate landings, recruitment, and biomass levels. | ongoing | ongoing | delayed | delayed - no devoted resources | see catch level working group recommendations.
SEFSC |  | o Research needs for Protogynous stocks, particularly groupers and Black Sea Bass:
SEFSC | II. Long Term research needs for stock assessments to be developed within the next 5 years. |  Investigate possible effects of hermaphroditism on the steepness parameter. | delayed | delayed | delayed | delayed - no devoted resources
SEFSC | II. Long Term research needs for stock assessments to be developed within the next 5 years. |  Investigate temporal patterns in sexual transition and develop explanations for any patterns identified. | delayed | delayed | delayed | delayed - no devoted resources
SEFSC | II. Long Term research needs for stock assessments to be developed within the next 5 years. |  Investigate methods for incorporating the dynamics of sexual transition in assessment models. | delayed | delayed | delayed | delayed - no devoted resources
• Spanish Mackerel
SEFSC | II. Long Term research needs for stock assessments to be developed within the next 5 years. | o Need observer coverage of fisheries that catch Spanish Mackerel (gillnets, castnets, handlines, poundnets, and shrimp trawls) for bycatch estimates. | delayed | delayed | delayed | lack of resources
SEFSC | II. Long Term research needs for stock assessments to be developed within the next 5 years. | o Examine how schooling or migratory dynamics may influence the catchability of the species. In particular, research the assumption of the hyperstability of indices that sample the schooling portion of the stock. | delayed | delayed | delayed | lack of resources
• Gag
SEFSC | II. Long Term research needs for stock assessments to be developed within the next 5 years. | o Evaluate otolith chemistry as an approach to define Gag population structure. | delayed | delayed | delayed | lack of resources
SEFSC | II. Long Term research needs for stock assessments to be developed within the next 5 years. | o Compare genetics of spawning Gag captured by commercial fishermen to juveniles collected in different areas in subsequent months to determine the source of recruits. Consider expanding research to include samples from Mexico to explore gene flow and connectivity. | delayed | delayed | delayed | lack or resources
• Red Snapper
SEFSC/GADNR | II. Long Term research needs for stock assessments to be developed within the next 5 years. | o Additional acoustic and traditional tagging is needed on known spawning locations to document spawning migrations or aggregations and return of fish to non-spawning areas. | ongoing | ongoing | ongoing | We currently are maintaining our offshore acoustic array capable of detecting acoustically tagged Red Snapper (and other species of interest). We are not independently tagging Red Snapper at this time. We have submitted a proposal in conjunction with Gray’s Reef NMS and the Georgia Aquarium to establish an acoustic receiver array on Gray’s Reef and adjacent state artificial reefs to monitor reef habitat usage and fish movement. As part of the study, we will be tagging several species with acoustic tags, including Red Snapper and Black Sea Bass, along with other state species of interest and some coastal sharks. If approved, the project would commence in Fall 2021.
SEFSC | II. Long Term research needs for stock assessments to be developed within the next 5 years. | o Evaluate the effects of environmental variation on the changes in recruitment and survivorship. | ongoing | ongoing | ongoing | Lost post-doc that was hired to focus on this. |  |  | mostly delayed due to loss of staff
SCDNR | II. Long Term research needs for stock assessments to be developed within the next 5 years. | o Investigate possible historical changes in sexual maturity. The current estimate of age of sexual maturity is low and unusual for other Lutjanids. | ongoing | ongoing | completed | 2019 MARFIN • Making Full Use of Biological Samples: Obtaining Age and Reproductive Information for Reef Fish Species from Previously Obtained Samples |  |  | completed and presented at SEDAR90-Red Snapper. Potential sample size issues and spatial collections in earlier time periods (prior to 2010 when SEFIS came onboard) due to abundance and/or changes in survey universe and density of sampling | https://sedarweb.org/documents/sedar-90-dw-22-update-of-red-snapper-lutjanus-campechanus-reproductive-life-history-from-the-marmap-serfs-program/
• Black Sea Bass
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Investigate the potential for a range shift in the black sea bass population, and the potential causes, such as climate change. | ongoing | ongoing | ongoing | The potential for range shift is addressed in South Atlantic Climate Vulnerability Assessment and a related Craig et al. manuscript that has been accepted for publication. An analysis of change in spatial distribution over time of black sea bass is included in Cao, Jie, J. Kevin Craig, and Matthew D. Damiano. 2024. Spatiotemporal Dynamics of Atlantic Reef Fishes off the Southeastern U.S. Coast. Ecosphere 15(6): e4868. https://doi.org/10.1002/ecs2.4868 |  |  | lacking summarization and final report. SCDNR has collected black sea bass fin clips from Massachusetts through Florida to explore spatial and temporal population structuring in the Atlantic waters along the eastern United States. This was funded by the SAFMC. Sample collection is complete, processing is nearing completion, with analysis soon to follow.
Red Grouper
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Evaluate the frequency and magnitude of recruitment coming from the Gulf of Mexico and south. | ongoing | ongoing | ongoing | Model-driven assessments of red snapper and scamp connectivity between Gulf and South Atlantic regions have been completed - see publications cited below. Connectivity has been evaluated but is not yet published for black sea bass, gag, and red grouper (Brothers et al). Karnauskas, M, K Shertzer, CB Paris, N Farmer, T Switzer, S Loweree-Barbieri, GT Kellison, R He, AC Vaz. 2022. Source-sink recruitment of red snapper: Connectivity between the Gulf of Mexico and Atlantic Ocean. Fisheries Oceanography. https://doi.org/10.1111/fog.12607 Brothers JR, Shertzer KW, Karnauskas M, Vaz AC, Bacheler NM, Paris CB (2024) Connectivity of scamp Mycteroperca phenax populations in the United States Gulf of Mexico and Atlantic Ocean. Mar Ecol Prog Ser 750:133-152. https://doi.org/10.3354/meps14728. |  | https://onlinelibrary.wiley.com/doi/10.1111/fog.12607
• Mutton Snapper
FWRI | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Design a multi-year study to collect age and gonad samples at spawning sites during the spawning season. This should entail identifying the diurnal usage patterns at spawning sites during the year. | delayed | delayed | delayed |  |  |  | lack of resources
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Collect more information on commercial and recreational discards, including some validation using at-sea sampling. | ongoing | ongoing | delayed | lack of resources resulitng in reduced sampling in the South Atlantic |  |  | lack of resources
III. Short Term Needs for Spawning Special Management Zones to be completed in the next 5 years.
| III. Short Term Needs for Spawning Special Management Zones to be completed in the next 5 years. | • Document spawning within Spawning SMZs by priority species in the Snapper Grouper complex. | delayed | delayed | delayed | no efforts currently underway to measure spawning within SMZs
SCDNR | III. Short Term Needs for Spawning Special Management Zones to be completed in the next 5 years. | • Collect baseline data for Spawning SMZs. | ongoing | ongoing | ongoing | SERFS sampling sites occur in several Spawning SMZs, resulting in sample collections relevant for late spring/summer spawners. For those SMZs, we have a limited time series of data that can be explored to examine temporal changes. |  |  | ongoing and assisting TNC with life history processing and staging/ageing
SCDNR | III. Short Term Needs for Spawning Special Management Zones to be completed in the next 5 years. | • Evaluate the sampling program of the Spawning SMZs. The evaluation should review data on compliance, spawning, and determine if current sampling targets are sufficient. | ongoing | ongoing | ongoing | SERFS sampling sites occur in several Spawning SMZs, resulting in sample collections relevant for late spring/summer spawners. For those SMZs, we have a limited time series of data that can be explored to examine temporal changes.
SEFSC | III. Short Term Needs for Spawning Special Management Zones to be completed in the next 5 years. | • Develop methods for incorporating the impacts of Spawning SMZs on management actions and stock status. | ongoing | ongoing | ongoing | Models have been developed and analyses are continuing (Brothers and Vaz)
SEFSC | III. Short Term Needs for Spawning Special Management Zones to be completed in the next 5 years. | • Use hydrodynamic modeling to look at connectivity between SMZs and other habitats. | ongoing | ongoing | ongoing | Models have been developed and analyses are continuing (Brothers and Vaz) | Biological data are being compiled and simulations will be run in late 2023 | https://onlinelibrary.wiley.com/doi/10.1111/fog.12607 | Models have been developed and analyses are continuing
IV. Short Term Needs for MPA monitoring to be completed within the next 5 years.
SCNDR | IV. Short Term Needs for MPA monitoring to be completed within the next 5 years. | • Maintain annual monitoring to collect data inside and outside the MPAs to characterize MPAs and enable comparison to reference sites. Identify fish population demographics (e.g. size and age structure, sex ratio, species use of habitat by life stage, spawning activities, etc.) within and adjacent to the MPAs. | ongoing | ongoing | ongoing | SERFS sampling sites occur in several MPAsresulting in a limited time series of data that can be explored to examine temporal changes. The SAB MPA project targeted this data need with respect to species identification and number, but used non-destructive sampling and therefore does not address age, sex ratio or spawning. It began 5 years before the closure of the MPAs and has been a priority task for SEFSC from the SAFMC. However, 2021 was the final year for the project as CRCP no longer funds projects in waters >50m and the SEFSC does not have funds to continue the work. SCDNR collaborators published the following paper in 2021, based on data from the SEFSC-funded South Atlantic trap-video survey: No effect of marine protected areas on managed reef fish species in the southeastern United States Atlantic Ocean. |  |  | Continued chevron video trap sampling of MPAs and adjacent areas.
SEFSC | IV. Short Term Needs for MPA monitoring to be completed within the next 5 years. | • Characterize spawning by managed species within the MPAs. | delayed | delayed | delayed | no efforts currently underway to measure spawning within MPAs
NOS/SEFSC | IV. Short Term Needs for MPA monitoring to be completed within the next 5 years. | • Complete multibeam surveys of the MPAs. | ongoing | ongoing | ongoing | All MPAs have, at a minimum, been partially mapped. There are unmapped areas in the deeper portions of several MPAs which are beyond the range of sensors currently available on NOAA vessels used for the survey. There is good coordination between SEFSC projects that conduct multibeam bathymetric mapping to avoid duplication and close gaps.
SEFSC | IV. Short Term Needs for MPA monitoring to be completed within the next 5 years. | • Evaluate the sampling program of the SAFMC MPAs. The evaluation should review data on compliance, species abundance and diversity, and determine if current sampling targets are sufficient. | delayed | delayed | delayed
SEFSC | IV. Short Term Needs for MPA monitoring to be completed within the next 5 years. | • Develop methods for incorporating the impacts of MPA on management actions and stock status. | delayed | delayed | delayed
FWRI | IV. Short Term Needs for MPA monitoring to be completed within the next 5 years. | • Use hydrodynamic modeling to look at connectivity between MPAs and other habitats. | ongoing | ongoing | ongoing | Models have been developed and analyses are continuing (Vaz & Brothers); FWRI works with partners from Louisiana State University and UCLouvain to model coral disease dispersal and coral larval dispersal using the SLIM hydrodynamic connectivity model.
V. Long Term Needs to be developed within the next 5 years.
SEFSC/NCSU/GADNR | V. Long Term Needs to be developed within the next 5 years. | • Consider acoustic tagging projects for addressing area-based management research and monitoring needs as noted in the SSMZ and MPA sections. | ongoing | ongoing | ongoing | See, for example, the following acoustic-tagging based publications: https://www.nature.com/articles/s41598-018-37527-1 https://www.nature.com/articles/s41598-021-88806-3 |  | https://www.nature.com/articles/s41598-021-88806-3 | acoustic tagging of red snapper is part of the SARSP
SEFSC/SCDNR | V. Long Term Needs to be developed within the next 5 years. | • Obtain life history traits for all species listed as either Level 1 or 2 in Table 1, including von Bertalanffy growth parameters, maturity, and reproductive rates. | ongoing | ongoing | ongoing | 2019 MARFIN Making Full Use of Biological Samples: Obtaining Age and Reproductive Information for Reef Fish Species from Previously Obtained Samples | NMFS currently has a FT-NIRS project underway to age white grunt from both stocks in the South Atlantic. Red hind updated age, growth and mortlaity estimates are complete (ms in review). |  | ongoing | All historic (prior to 2023) reproduction samples have been staged and all species but Vermilion Snapper have been completed for age estimates, with those expected by the end of 2025
SEFSC/SCDNR | V. Long Term Needs to be developed within the next 5 years. | • Initiate long-term continuous monitoring of age structures in the South Atlantic for all species listed as either Level 1 or 2 in Table 1. | ongoing | ongoing | ongoing | 2019 MARFIN (3) Making Full Use of Biological Samples: Obtaining Age and Reproductive Information for Reef Fish Species from Previously Obtained Samples • Expansion of a fishery-independent, deep-water snapper-grouper survey to optimize abundance and life history information provided to stock assessments in the South Atlantic region • Developing indices of relative abundance and size/age composition for the assessment of Red Snapper and other reef fishes in the U.S. South Atlantic using data from a fishery-independent hooked-gear survey |  |  | ongoing | All historic (prior to 2023) otoliths have been staged except for Vermilion Snapper, with those expected by the end of 2025
SEFSC | V. Long Term Needs to be developed within the next 5 years. | • Develop models to predict changes to shrimp, shallow water and deepwater coral, Snapper Grouper, Dolphin Wahoo, and Mackerel populations due to climate change, including changes to species’ distribution, movements, and reproductive patterns. | ongoing | ongoing | ongoing | Climate Fisheries Initiative, Climate Regional Action Plans | 7y | https://www.st.nmfs.noaa.gov/Assets/ecosystems/climate/documents/raps/tech_memos/Draft_South_Atlantic_Regional_Action_Plan_for_public_review%202.14.17.pdf
SEFSC | V. Long Term Needs to be developed within the next 5 years. | • Evaluate the cumulative economic and social impacts of existing regulations on the multi-species Snapper Grouper fishery in the South Atlantic. | ongoing | ongoing | ongoing | economics state of the SG fishery presented to Council at June 2019 |  | https://repository.library.noaa.gov/view/noaa/19802
SEFSC | V. Long Term Needs to be developed within the next 5 years. | • Evaluate management strategies to reduce discard mortality in the multi-species Snapper Grouper fishery. | ongoing | ongoing | ongoing | Vecchio, Julie, Dominique Lazarre, Beverly Sauls. 2020. Utility and Usage of Descender Devices in the Red Snapper Recreational Fishery in the South Atlantic. SEDAR73-WP15. SEDAR, North Charleston, SC. 16 pp. Rudershausen PJ, Runde BJ, Tharp RM, Merrell JH, Bacheler NM, Patterson III WF, Buckel JA. 2025. Discard mortality rates of red snapper after barotrauma and hook trauma: Insights from using acoustic telemetry in the U.S. South Atlantic. North American Journal of Fisheries Management 00:1-13. https://doi.org/10.1093/najfmt/vqaf012 | Scott Crosson et al manuscript on in review | http://sedarweb.org/docs/wpapers/SEDAR73_WP15_Utility%20and%20Usage%20of%20Descender%20Devices%20in%20the%20Red%20Snapper%20Recreational%20Fishery%20in%20the%20South%20Atlantic_revised12.4.2020.pdf
SEFSC/GADNR | V. Long Term Needs to be developed within the next 5 years. | • Validate age determination for species in the Snapper-Grouper FMP. | ongoing | ongoing | ongoing | Age validation of Red Porgy has been completed. Age validation studies of Gray Triggerfish, Black Sea Bass and Vermilion Snapper are ongoing - GADNR We are collaborating with Florida FWC to age our Red Snapper otoliths collected through carcass donations from the recreational fishery during the season. | NMFS age validation of gray triggerfish is complete. Expanding use of the GTF updated age reading methodology in collaboration with Gulf of Mexico study by Drs. Chamberlin and Patterson at UFL. Age validation study of black sea bass and vermilion snapper are ongoing. | http://sedarweb.org/docs/wpapers/S60_WP03_Potts_etal_NMFSAgeReadingChanges_12.21.2018_0.pdf
SEFSC | V. Long Term Needs to be developed within the next 5 years. | • Provide an evaluation of the independent survey and biological sampling information available for all SAFMC managed stocks that are currently unassessed. This evaluation should document past sampling intensity and current sampling targets and provide guidance on the type of stock assessments feasible given currently available data. | ongoing | ongoing | ongoing | A species-specific assessment of the degree of information provided, by fishery-independent survey, will be initiated in 2021 for South Atlantic species. | (Todd's comment: who is the lead on the species-specific assessment referenced in cell F71? I think the assessment would be relatively straightforward to complete.)
SEFSC/GADNR/NCSU | V. Long Term Needs to be developed within the next 5 years. | • Conduct tagging studies of Snapper Grouper species, including the Mid-Atlantic, Gulf, and SA regions, to evaluate movements and estimate demographic rates between regions. | ongoing | ongoing | ongoing | 2019 MARFIN • Developing indices of relative abundance and size/age composition for the assessment of Red Snapper and other reef fishes in the U.S. South Atlantic using data from a fishery-independent hooked-gear survey GA DNR We currently are maintaining our offshore acoustic array capable of detecting acoustically tagged Red Snapper (and other species of interest). We are not independently tagging Red Snapper at this time. - We have submitted a proposal in conjunction with Gray’s Reef NMS and the Georgia Aquarium to establish an acoustic receiver array on Gray’s Reef and adjacent state artificial reefs to monitor reef habitat usage and fish movement. As part of the study, we will be tagging several species with acoustic tags, including Red Snapper and Black Sea Bass, along with other state species of interest and some coastal sharks. If approved, the project would commence in Fall 2021 | Part of the FY23 SATL reef fish spend plan | https://www.nature.com/articles/s41598-021-88806-3
SCDNR | V. Long Term Needs to be developed within the next 5 years. | • Update reproductive biology work on shallow water groupers (Red Grouper), to determine latitudinal variation in spawning periodicity and habits. | ongoing | ongoing | ongoing | 2019 MARFIN Making Full Use of Biological Samples: Obtaining Age and Reproductive Information for Reef Fish Species from Previously Obtained Samples - |  |  | ongoing | sample collection and life history processing continues
SEFSC | V. Long Term Needs to be developed within the next 5 years. | • Investigate juvenile habitat and abundance of shallow water groupers (such as Gag and Red Grouper), to evaluate the effectiveness of current regulations in protecting these species, by looking at changes in abundance and frequency of occurrence. | delayed | delayed | delayed
FWRI | V. Long Term Needs to be developed within the next 5 years. | • Develop a program for monitoring/evaluating compliance with the use of descending/venting devices. | ongoing | ongoing | ongoing | Vechio et al | Part of the FY23 SATL reef fish spend plan | http://sedarweb.org/docs/wpapers/SEDAR73_WP15_Utility%20and%20Usage%20of%20Descender%20Devices%20in%20the%20Red%20Snapper%20Recreational%20Fishery%20in%20the%20South%20Atlantic_revised12.4.2020.pdf
VI. Habitat Research and Monitoring Needs
SEFSC/FWRI/NOS | VI. Habitat Research and Monitoring Needs | • Map coral distribution in the South Atlantic region. | ongoing | ongoing | ongoing | CRCP-funded deep-reef mapping and analysis is ongoing for the SE Florida and FL Keys region | Deeper-water multibeam mapping of coral reef habitats is planned or ongoing in the upper FL Keys and southeast FL region (Matt Johnson = SEFSC POC).
NOS/FWRI/SEFSC/USF/UM/AOML | VI. Habitat Research and Monitoring Needs | • Monitor health of coral reef systems. | ongoing | ongoing | ongoing | NCRMP bi-annual (even years) coral reef fish and habitat sampling in SE Florida and the FL Keys. FWRI participates in regional mapping prioritization projects led by the University of South Florida and the Florida Institute of Oceanography to guide future mapping efforts. FWRI manages several coral disease and water quality dashboards to monitor coral reef systems in the South Atlantic region. https://coastalscience.noaa.gov/project/state-coral-reef-ecosystems-united-states-pacific-freely-associated-states/ | The annual NOAA-led NCRMP surveys directly address this need, as do ESA-listed coral monitoring efforts in the FL Keys led by SEFSC personnel (Ladd et al.).
VII. Specific Monitoring Priorities
? | VII. Specific Monitoring Priorities | Increase funding for fisheries independent monitoring in the South Atlantic. Specific needs include:
? | VII. Specific Monitoring Priorities | o Restoring MARMAP funding to a minimum of $850,000 annually. | ongoing | ongoing | ongoing | with level funding and rising costs make this a challenge | 230K sent to SCNDR from the 1.8M reef fish funds
? | VII. Specific Monitoring Priorities | o Funding MARMAP sufficiently to support reinitiating long bottom longline sampling that provides the only abundance information for deepwater stocks such as Tilefish. | ongoing | completed | completed | SADL | The SADL survey is now established as an annual survey and will undergo SSC review in 2023. | see SADL presentation: https://drive.google.com/drive/folders/1diRhsnsJZY0rn75vyXed3nB3uxVZuaso
? | VII. Specific Monitoring Priorities | o Maintaining funding for SEAMAP at levels sufficient to support long-term fishery independent survey operations. | ongoing | ongoing | ongoing | with level funding and rising costs make this a challenge
? | VII. Specific Monitoring Priorities | o Maintaining funding for SEFIS to support video survey work. | ongoing | ongoing | ongoing | with level funding and rising costs make this a challenge |  | Bacheler et al. recent publication: https://www.int-res.com/abstracts/meps/v698/p111-123/
? | VII. Specific Monitoring Priorities | o Increasing funding for SEFIS to support the use of stereo cameras, or other such technology, to measure fish length during the video survey. | ongoing | ongoing | ongoing | with level funding and rising costs make this a challenge
? | VII. Specific Monitoring Priorities | o Providing funding for the MPA/SMZ monitoring needs noted above. | ongoing | ongoing | ongoing | with level funding and rising costs make this a challenge
SEFSC/AOML | VII. Specific Monitoring Priorities | • Monitor the mixing rates of Gulf and South Atlantic King Mackerel. Mixing rates may change over time and should therefore be regularly evaluated, although annual monitoring may not be necessary. | ongoing | completed | completed | genomic approaches to stock mixing | see report on KMK omics | Matt Lauretta project
FWRI/SEFSC | VII. Specific Monitoring Priorities | • Implement a monitoring and research program to address issues relevant to ecosystem management. Topics include trophic interactions, food preferences, predator-prey relationships, and ecosystem connectivity. | ongoing | ongoing | ongoing | A South Atlantic Ecosystem Status Report (ESR) was finalized in 2021; an update ins planned but not yet iniitiated. The SAFMC funds FWRI to develop a regional ecosystem model that incorporates trophic interactions, diet information, predator-prey relationships, and ecosystem connectivity.
SEFSC/NCSU | VII. Specific Monitoring Priorities | • Develop monitoring programs for Dolphin and Golden Crab that can support future quantitative stock assessments for these stocks. | ongoing | ongoing | ongoing | Dolphin-Wahoo stakeholder workshops, MARFIN • Development and application of a management strategy evaluation tool: tradeoffs between the management objective of recreational and commercial fisheriesDolphin MSE (Jie Cao and Matt Damiano) | ongoing MSE for dolphin
SEFSC/OST/ACCSP | VII. Specific Monitoring Priorities | • Develop and implement new methods for decreasing uncertainty of recreational catch estimates for federally managed offshore species, including but not limited to enhancements to the MRIP survey, add-on surveys, and new methods for collecting recreational catch data. | ongoing | ongoing | ongoing | S&T research and development in this area: 1) At some point in 2019/2020, S&T was able to increase the annual APAIS funding for the Atlantic coast in the ACCSP region (so not just NC-GA) by $900K and are working with ACCSP and the state partners on sample allocations to improve precision on estimates for managed species. They were also able to increase the APAIS funding for GulfFIN by a similar amount, so FL would be included in addition to NC-GA. 2) As part of the MRIP Rare Event Working Group, MRIP consultants completed a preliminary internal report evaluating several multi-year average approaches to estimation for several rare event species. This working group has not met in some time (most due to COVID disruptions and issues stemming from Gulf red snapper), but S&T suspects the group will likely reengage at some point this year. 3) S&T is also collaborating on the SEFHIER catch validation sampling, primarily by integrating that sampling into the APAIS sample draw process. This work has focused mostly on the Gulf region to date, but the development work will apply to the South Atlantic as well. |  | https://safmc.net/download/BB%20RecWorkgroup%20Feb2021/A3b_MRIP_Presentation_Rare_Events.pdf
SEFSC | VII. Specific Monitoring Priorities | • Maintain/improve the ability to document commercial and recreational landings and discards. | ongoing | ongoing | ongoing | 2020 CRP: Functional electronic monitoring of the Gulf of Mexico reef fish fishery, Phase II:Tactical assessment of bycatch, discards, and community structure including highly migratory |  | http://sedarweb.org/docs/wpapers/S68_DW_13_MRIP_metadata.pdf
VIII. SPECIFIC ANNUAL REPORTING REQUESTS
SEFSC | VIII. SPECIFIC ANNUAL REPORTING REQUESTS | • Provide by June 1 annually, SAFE reports that provide stock status including OFL and MSY, an evaluation of the management program including whether ACLs were met or AMs triggered and addressing reasons for such, results of independent fisheries monitoring, complete landings and discard losses in weight and numbers of fish, fishery dependent monitoring statistics, and measures of effort and economic value for all managed stocks. | delayed | ongoing | ongoing | Recreational data and documentation used in SAFE report last provided in June 2020. (VM) | draft safe reports are available
SEFSC | VIII. SPECIFIC ANNUAL REPORTING REQUESTS | • Provide by October 1 annually, a report on the SEFIS program that addresses survey sampling effort, biological sampling intensity, and survey findings for assessed species. This should include updated abundance index trends for all stocks sampled | delayed | delayed | completed
SEFSC | VIII. SPECIFIC ANNUAL REPORTING REQUESTS | • Provide annual progress reports, by the SEFSC at the June Council meeting, detailing efforts to implement the research recommendations noted in Council Research and Monitoring Plans. | delayed | ongoing | completed

## delays
partner | heading | topic | status
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | • Operational assessment for Spanish Mackerel, mid-2020: | ongoing
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Updated maturity data from both sexes for fish below 275mm FL. | ongoing
SEFSC | I. Short Term stock assessments need 2020-2023 | o (Spanish mackerel) Evaluate stock structure using updated data and modern techniques, such as genetics. In particular evaluate if there is newer data available on steepness from other analyses of S-R for pelagic stocks with similar reproductive strategies. | delayed
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | • Operational assessment for Gag, mid-2020: | completed
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Explore larval transport and modeling efforts associated with development of an IOOS to gain insight into larval connectivity and transport. | ongoing
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Develop a solution to address species mis-identification with Black Grouper. | completed
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | • Red Snapper Operational Assessment, 2021: | completed
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Improved and updated bycatch mortality estimates | completed
SEFSC | I. Short Term stock assessments need 2020-2023 | • Gray Triggerfish Research Track Assessment 2022: | delayed | A
SEFSC/SCDNR | I. Short Term stock assessments need 2020-2023 | o Address age determination issues for Gray Triggerfish by January 2020 so age structures can be evaluated for a research track assessment tentatively scheduled for 2021, including re-aging of the spines by the start of the RT. | delayed | A
SEFSC | I. Short Term stock assessments need 2020-2023 | • Black Sea Bass Operational Assessment 2021: | delayed | A
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Investigate discard mortality due to hooks in shallow waters (<10m). | ongoing
SEFSC | I. Short Term stock assessments need 2020-2023 | o Recommend the use of more direct methods of estimating M, such as Tag-Recapture studies. | delayed | A
SEFSC | I. Short Term stock assessments need 2020-2023 | • Red Grouper Operational Assessment 2021: | delayed | A
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Evaluate sample size cutoffs for using age and length compositions. What should be the minimum standards, and how does this interplay with the number of age and length classes modeled in the assessment? | completed
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Conduct a simulation study to evaluate the performance of the various likelihood formulations that have been used for fitting age and length composition data under sampling conditions realistic in the southeast U.S. | completed
FWRI | I. Short Term research needs for stock assessments to be completed in 2020-2023 | • Mutton Snapper Assessment, 2021: | ongoing
FWRI | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Evaluate the discard mortality estimates for Mutton Snapper and conduct studies to either confirm or refine these estimates. | ongoing
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Evaluate the conversion factors used to convert landed weight to whole weight. Preliminary comparisons suggest a lower percentage difference between gutted weight and whole weight at comparable sizes than is currently used. | ongoing
SEFSC | I. Short Term stock assessments need 2020-2023 | • White Grunt Research Track Assessment, 2023 | delayed | A
SCDNR | I. Short Term stock assessments need 2020-2023 | o Conduct stock identification studies for White Grunt. | delayed | A
SEFSC/SCDNR | I. Short Term research needs for stock assessments to be completed in 2020-2023 | SERFS indices available for most species (Todd's note / addition: suggest changing the comment to something like "Trap-based indices have been generated and updated annually by SCDNR. Video-based indices have been developed for SEDAR-assessed species. Development of updated annual video indices for all managed species effectively sampled in the trap-video survey is ongoing / in progress". SCDNR currently produces annual indices of abundance from SERFS chevron trap sampling for all species caught in abundance in their annual trends report. The only species I am aware of that did not use the whole MARMAP time series was Red Snapper due to the center of distribution being in areas that are now more densely sampled since the creation of SEFIS. | completed
SEFSC | II. Long Term research needs for stock assessments to be developed within the next 5 years. | o Evaluate assessment projection performance, considering their ability to estimate landings, recruitment, and biomass levels. | ongoing
SEFSC | II. Long Term research stock assessments needs 5 years. |  Investigate possible effects of hermaphroditism on the steepness parameter. | delayed
SEFSC | II. Long Term research stock assessments needs 5 years. |  Investigate temporal patterns in sexual transition and develop explanations for any patterns identified. | delayed
SEFSC | II. Long Term research stock assessments needs 5 years. |  Investigate methods for incorporating the dynamics of sexual transition in assessment models. | delayed
SEFSC | II. Long Term research stock assessments needs 5 years. | o Need observer coverage of fisheries that catch Spanish Mackerel (gillnets, castnets, handlines, poundnets, and shrimp trawls) for bycatch estimates. | delayed
SEFSC | II. Long Term research stock assessments needs 5 years. | o Examine how schooling or migratory dynamics may influence the catchability of the species. In particular, research the assumption of the hyperstability of indices that sample the schooling portion of the stock. | delayed
SEFSC | II. Long Term research stock assessments needs 5 years. | o Evaluate otolith chemistry as an approach to define Gag population structure. | delayed
SEFSC | II. Long Term research stock assessments needs 5 years. | o Compare genetics of spawning Gag captured by commercial fishermen to juveniles collected in different areas in subsequent months to determine the source of recruits. Consider expanding research to include samples from Mexico to explore gene flow and connectivity. | delayed
SEFSC/GADNR | II. Long Term research needs for stock assessments to be developed within the next 5 years. | o Additional acoustic and traditional tagging is needed on known spawning locations to document spawning migrations or aggregations and return of fish to non-spawning areas. | ongoing
SEFSC | II. Long Term research needs for stock assessments to be developed within the next 5 years. | o Evaluate the effects of environmental variation on the changes in recruitment and survivorship. | ongoing
SCDNR | II. Long Term research needs for stock assessments to be developed within the next 5 years. | o Investigate possible historical changes in sexual maturity. The current estimate of age of sexual maturity is low and unusual for other Lutjanids. | ongoing
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Investigate the potential for a range shift in the black sea bass population, and the potential causes, such as climate change. | ongoing
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Evaluate the frequency and magnitude of recruitment coming from the Gulf of Mexico and south. | ongoing
FWRI | III. Short Term Spawning Special Management Zones 5 years. | o Design a multi-year study to collect age and gonad samples at spawning sites during the spawning season. This should entail identifying the diurnal usage patterns at spawning sites during the year. | delayed
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Collect more information on commercial and recreational discards, including some validation using at-sea sampling. | ongoing
| III. Short Term Spawning Special Management Zones 5 years. | • Document spawning within Spawning SMZs by priority species in the Snapper Grouper complex. | delayed
SCDNR | III. Short Term Needs for Spawning Special Management Zones to be completed in the next 5 years. | • Collect baseline data for Spawning SMZs. | ongoing
SCDNR | III. Short Term Needs for Spawning Special Management Zones to be completed in the next 5 years. | • Evaluate the sampling program of the Spawning SMZs. The evaluation should review data on compliance, spawning, and determine if current sampling targets are sufficient. | ongoing
SEFSC | III. Short Term Needs for Spawning Special Management Zones to be completed in the next 5 years. | • Develop methods for incorporating the impacts of Spawning SMZs on management actions and stock status. | ongoing
SEFSC | III. Short Term Needs for Spawning Special Management Zones to be completed in the next 5 years. | • Use hydrodynamic modeling to look at connectivity between SMZs and other habitats. | ongoing
| IV. Short Term Needs for MPA monitoring to be completed within the next 5 years. | • Maintain annual monitoring to collect data inside and outside the MPAs to characterize MPAs and enable comparison to reference sites. Identify fish population demographics (e.g. size and age structure, sex ratio, species use of habitat by life stage, spawning activities, etc.) within and adjacent to the MPAs. | ongoing
| IV. Short Term MPA monitoring 5 years. | • Characterize spawning by managed species within the MPAs. | delayed
| IV. Short Term Needs for MPA monitoring to be completed within the next 5 years. | • Complete multibeam surveys of the MPAs. | ongoing
? | IV. Short Term MPA monitoring 5 years. | • Evaluate the sampling program of the SAFMC MPAs. The evaluation should review data on compliance, species abundance and diversity, and determine if current sampling targets are sufficient. | delayed
? | IV. Short Term MPA monitoring 5 years. | • Develop methods for incorporating the impacts of MPA on management actions and stock status. | delayed
FWRI | IV. Short Term Needs for MPA monitoring to be completed within the next 5 years. | • Use hydrodynamic modeling to look at connectivity between MPAs and other habitats. | ongoing
SEFSC/NCSU/GADNR | V. Long Term Needs to be developed within the next 5 years. | • Consider acoustic tagging projects for addressing area-based management research and monitoring needs as noted in the SSMZ and MPA sections. | ongoing
SEFSC/SCDNR | V. Long Term Needs to be developed within the next 5 years. | • Obtain life history traits for all species listed as either Level 1 or 2 in Table 1, including von Bertalanffy growth parameters, maturity, and reproductive rates. | ongoing
SEFSC/SCDNR | V. Long Term Needs to be developed within the next 5 years. | • Initiate long-term continuous monitoring of age structures in the South Atlantic for all species listed as either Level 1 or 2 in Table 1. | ongoing
SEFSC | V. Long Term Needs to be developed within the next 5 years. | • Develop models to predict changes to shrimp, shallow water and deepwater coral, Snapper Grouper, Dolphin Wahoo, and Mackerel populations due to climate change, including changes to species’ distribution, movements, and reproductive patterns. | ongoing
SEFSC | V. Long Term Needs to be developed within the next 5 years. | • Evaluate the cumulative economic and social impacts of existing regulations on the multi-species Snapper Grouper fishery in the South Atlantic. | ongoing
SEFSC | V. Long Term Needs to be developed within the next 5 years. | • Evaluate management strategies to reduce discard mortality in the multi-species Snapper Grouper fishery. | ongoing
SEFSC/GADNR | V. Long Term Needs to be developed within the next 5 years. | • Validate age determination for species in the Snapper-Grouper FMP. | ongoing
SEFSC | V. Long Term Needs to be developed within the next 5 years. | • Provide an evaluation of the independent survey and biological sampling information available for all SAFMC managed stocks that are currently unassessed. This evaluation should document past sampling intensity and current sampling targets and provide guidance on the type of stock assessments feasible given currently available data. | ongoing
SEFSC/GADNR/NCSU | V. Long Term Needs to be developed within the next 5 years. | • Conduct tagging studies of Snapper Grouper species, including the Mid-Atlantic, Gulf, and SA regions, to evaluate movements and estimate demographic rates between regions. | ongoing
SCDNR | V. Long Term Needs to be developed within the next 5 years. | • Update reproductive biology work on shallow water groupers (Red Grouper), to determine latitudinal variation in spawning periodicity and habits. | ongoing
? | V. Long Term other Needs 5 years. | • Investigate juvenile habitat and abundance of shallow water groupers (such as Gag and Red Grouper), to evaluate the effectiveness of current regulations in protecting these species, by looking at changes in abundance and frequency of occurrence. | delayed
FWRI | V. Long Term Needs to be developed within the next 5 years. | • Develop a program for monitoring/evaluating compliance with the use of descending/venting devices. | ongoing
SEFSC/FWRI | VI. Habitat Research and Monitoring Needs | • Map coral distribution in the South Atlantic region. | ongoing
NOS/FWRI/SEFSC | VI. Habitat Research and Monitoring Needs | • Monitor health of coral reef systems. | ongoing
? | VII. Specific Monitoring Priorities | Increase funding for fisheries independent monitoring in the South Atlantic. Specific needs include: | ongoing
? | VII. Specific Monitoring Priorities | o Restoring MARMAP funding to a minimum of $850,000 annually. | ongoing
? | VII. Specific Monitoring Priorities | o Funding MARMAP sufficiently to support reinitiating long bottom longline sampling that provides the only abundance information for deepwater stocks such as Tilefish. | ongoing
? | VII. Specific Monitoring Priorities | o Maintaining funding for SEAMAP at levels sufficient to support long-term fishery independent survey operations. | ongoing
? | VII. Specific Monitoring Priorities | o Maintaining funding for SEFIS to support video survey work. | ongoing
? | VII. Specific Monitoring Priorities | o Increasing funding for SEFIS to support the use of stereo cameras, or other such technology, to measure fish length during the video survey. | ongoing
? | VII. Specific Monitoring Priorities | o Providing funding for the MPA/SMZ monitoring needs noted above. | ongoing
SEFSC/AOML | VII. Specific Monitoring Priorities | • Monitor the mixing rates of Gulf and South Atlantic King Mackerel. Mixing rates may change over time and should therefore be regularly evaluated, although annual monitoring may not be necessary. | ongoing
FWRI/SEFSC | VII. Specific Monitoring Priorities | • Implement a monitoring and research program to address issues relevant to ecosystem management. Topics include trophic interactions, food preferences, predator-prey relationships, and ecosystem connectivity. | ongoing
SEFSC/NCSU | VII. Specific Monitoring Priorities | • Develop monitoring programs for Dolphin and Golden Crab that can support future quantitative stock assessments for these stocks. | ongoing
SEFSC/OST/ACCSP | VII. Specific Monitoring Priorities | • Develop and implement new methods for decreasing uncertainty of recreational catch estimates for federally managed offshore species, including but not limited to enhancements to the MRIP survey, add-on surveys, and new methods for collecting recreational catch data. | ongoing
SEFSC | VII. Specific Monitoring Priorities | • Maintain/improve the ability to document commercial and recreational landings and discards. | ongoing
SEFSC | VIII. SPECIFIC ANNUAL REPORTING REQUESTS | • Provide by June 1 annually, SAFE reports that provide stock status including OFL and MSY, an evaluation of the management program including whether ACLs were met or AMs triggered and addressing reasons for such, results of independent fisheries monitoring, complete landings and discard losses in weight and numbers of fish, fishery dependent monitoring statistics, and measures of effort and economic value for all managed stocks. | delayed
SEFSC | VIII. SPECIFIC ANNUAL REPORTING REQUESTS | • Provide by October 1 annually, a report on the SEFIS program that addresses survey sampling effort, biological sampling intensity, and survey findings for assessed species. This should include updated abundance index trends for all stocks sampled | delayed
SEFSC | VIII. SPECIFIC ANNUAL REPORTING REQUESTS | • Provide annual progress reports, by the SEFSC at the June Council meeting, detailing efforts to implement the research recommendations noted in Council Research and Monitoring Plans. | delayed

## Pivot Table 2023
status 2023
need | complete | delayed/not planned | ongoing: research in progress or routine | total | status 2023 | status 2022
I. Short Term needs for stock assessments in 2020-2023 | 11 | 5 | 10 | 26 | 80.77% | 61.54%
II. Long Term needs for stock assessments within the next 5 years. |  | 7 | 4 | 11 | 36.36% | 36.36%
III. Short Term Needs for Spawning Special Management Zones in next 5 years. |  | 1 | 4 | 5 | 80% | 80%
IV. Short Term Needs for MPA monitoring within the next 5 years. |  | 3 | 3 | 6 | 50% | 50%
V. Long Term Needs to be developed within the next 5 years. |  | 1 | 11 | 12 | 91.67% | 91.67%
VI. Habitat Research and Monitoring Needs |  |  | 2 | 2 | 100% | 100%
VII. Specific Monitoring Priorities | 2 |  | 9 | 11 | 100% | 100%
VIII. SPECIFIC ANNUAL REPORTING REQUESTS |  | 1 | 2 | 3 | 66.67% | 0%
total | 13 | 18 | 45 | 77 | 75.32% | 67.53%

## Pivot Table 2025
status 2025
Subject | Completed | Delayed/not planned | Ongoing: research in progress or routine | Total | Status 2025 (% completed and ongoing) | Status 2023 (% completed and ongoing)
I. Short Term needs for stock assessments in 2020-2023 | 15 | 8 | 3 | 26 | 69.23% | 80.77%
II. Long Term needs for stock assessments within the next 5 years. | 1 | 8 | 2 | 11 | 27.27% | 36.36%
III. Short Term Needs for Spawning Special Management Zones in next 5 years. |  | 1 | 4 | 5 | 80% | 80%
IV. Short Term Needs for MPA monitoring within the next 5 years. |  | 3 | 3 | 6 | 50% | 50%
V. Long Term Needs to be developed within the next 5 years. |  | 1 | 11 | 12 | 91.67% | 91.67%
VI. Habitat Research and Monitoring Needs |  |  | 2 | 2 | 100% | 100%
VII. Specific Monitoring Priorities | 2 |  | 9 | 11 | 100% | 100%
VIII. Specific Annual Reporting Requests | 2 |  | 1 | 3 | 100% | 66.67%
TOTAL (2025) | 20 | 21 | 35 | 76 | 72.37% | 75.32%
TOTAL (2023) | 13 | 18 | 45 | 77

## partners
Leads | projects | Row Labels | completed | delayed | ongoing | (blank) | Grand Total
FWRI | 5 | ? |  | 3 | 7 |  | 10 | 0.7
FWRI/SEFSC | 1 | FWRI |  | 1 | 4 |  | 5 | 0.8
NOS/FWRI/SEFSC | 1 | FWRI/SEFSC |  |  | 1 |  | 1 | 1
SCDNR | 5 | NOS/FWRI/SEFSC |  |  | 1 |  | 1 | 1
SEFSC | 39 | SCDNR |  | 1 | 4 |  | 5 | 0.8
SEFSC/AOML | 1 | SEFSC | 6 | 17 | 16 |  | 39 | 0.5641
SEFSC/FWRI | 1 | SEFSC/AOML |  |  | 1 |  | 1 | 1
SEFSC/GADNR | 2 | SEFSC/FWRI |  |  | 1 |  | 1 | 1
SEFSC/GADNR/NCSU | 1 | SEFSC/GADNR |  |  | 2 |  | 2 | 1
SEFSC/NCSU | 1 | SEFSC/GADNR/NCSU |  |  | 1 |  | 1 | 1
SEFSC/NCSU/GADNR | 1 | SEFSC/NCSU |  |  | 1 |  | 1 | 1
SEFSC/OST/ACCSP | 1 | SEFSC/NCSU/GADNR |  |  | 1 |  | 1 | 1
SEFSC/SCDNR | 4 | SEFSC/OST/ACCSP |  |  | 1 |  | 1 | 1
unknown/no lead identified | 10 | SEFSC/SCDNR | 1 | 1 | 2 |  | 4 | 0.75
|  | (blank) |  | 2 | 2 |  | 4 | 0.5
|  | Grand Total | 7 | 25 | 45 |  | 77

## pivot
needs | complete | ongoing: research in progress or routine | delayed/not planned | total | complete or ongoing rate
I. Short Term stock assessments need 2020-2023 | 7 | 9 | 10 | 26 | 61.54%
II. Long Term research stock assessments needs 5 years. |  | 4 | 7 | 11 | 36.36%
III. Short Term Spawning Special Management Zones 5 years. |  | 4 | 1 | 5 | 80%
IV. Short Term MPA monitoring 5 years. |  | 3 | 3 | 6 | 50%
V. Long Term other Needs 5 years. |  | 11 | 1 | 12 | 91.67%
VI. Habitat Research and Monitoring Needs |  | 2 |  | 2 | 100%
VII. Specific Monitoring Priorities |  | 12 |  | 12 | 100%
VIII. SPECIFIC ANNUAL REPORTING REQUESTS |  |  | 3 | 3 | 0%
(blank)
total | 7 | 45 | 25 | 77 | 67.53%

## shortlist
partner | heading | topic | status
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | • Operational assessment for Spanish Mackerel, mid-2020: | ongoing
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Updated maturity data from both sexes for fish below 275mm FL. | ongoing
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Evaluate stock structure using updated data and modern techniques, such as genetics. In particular evaluate if there is newer data available on steepness from other analyses of S-R for pelagic stocks with similar reproductive strategies. | delayed
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | • Operational assessment for Gag, mid-2020: | completed
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Explore larval transport and modeling efforts associated with development of an IOOS to gain insight into larval connectivity and transport. | ongoing
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Develop a solution to address species mis-identification with Black Grouper. | completed
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | • Red Snapper Operational Assessment, 2021: | completed
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Improved and updated bycatch mortality estimates | completed
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | • Gray Triggerfish Research Track Assessment 2022: | delayed
SEFSC/SCDNR | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Address age determination issues for Gray Triggerfish by January 2020 so age structures can be evaluated for a research track assessment tentatively scheduled for 2021, including re-aging of the spines by the start of the RT. | delayed
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | • Black Sea Bass Operational Assessment 2021: | delayed
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Investigate discard mortality due to hooks in shallow waters (<10m). | ongoing
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Recommend the use of more direct methods of estimating M, such as Tag-Recapture studies. | delayed
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | • Red Grouper Operational Assessment 2021: | delayed
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Evaluate sample size cutoffs for using age and length compositions. What should be the minimum standards, and how does this interplay with the number of age and length classes modeled in the assessment? | completed
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Conduct a simulation study to evaluate the performance of the various likelihood formulations that have been used for fitting age and length composition data under sampling conditions realistic in the southeast U.S. | completed
FWRI | I. Short Term research needs for stock assessments to be completed in 2020-2023 | • Mutton Snapper Assessment, 2021: | ongoing
FWRI | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Evaluate the discard mortality estimates for Mutton Snapper and conduct studies to either confirm or refine these estimates. | ongoing
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Evaluate the conversion factors used to convert landed weight to whole weight. Preliminary comparisons suggest a lower percentage difference between gutted weight and whole weight at comparable sizes than is currently used. | ongoing
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | • White Grunt Research Track Assessment, 2023 | delayed
SCDNR | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Conduct stock identification studies for White Grunt. | delayed
SEFSC/SCDNR | I. Short Term research needs for stock assessments to be completed in 2020-2023 | SERFS indices available for most species (Todd's note / addition: suggest changing the comment to something like "Trap-based indices have been generated and updated annually by SCDNR. Video-based indices have been developed for SEDAR-assessed species. Development of updated annual video indices for all managed species effectively sampled in the trap-video survey is ongoing / in progress". SCDNR currently produces annual indices of abundance from SERFS chevron trap sampling for all species caught in abundance in their annual trends report. The only species I am aware of that did not use the whole MARMAP time series was Red Snapper due to the center of distribution being in areas that are now more densely sampled since the creation of SEFIS. | completed
SEFSC | II. Long Term research needs for stock assessments to be developed within the next 5 years. | o Evaluate assessment projection performance, considering their ability to estimate landings, recruitment, and biomass levels. | ongoing
SEFSC | II. Long Term research needs for stock assessments to be developed within the next 5 years. |  Investigate possible effects of hermaphroditism on the steepness parameter. | delayed
SEFSC | II. Long Term research needs for stock assessments to be developed within the next 5 years. |  Investigate temporal patterns in sexual transition and develop explanations for any patterns identified. | delayed
SEFSC | II. Long Term research needs for stock assessments to be developed within the next 5 years. |  Investigate methods for incorporating the dynamics of sexual transition in assessment models. | delayed
SEFSC | II. Long Term research needs for stock assessments to be developed within the next 5 years. | o Need observer coverage of fisheries that catch Spanish Mackerel (gillnets, castnets, handlines, poundnets, and shrimp trawls) for bycatch estimates. | delayed
SEFSC | II. Long Term research needs for stock assessments to be developed within the next 5 years. | o Examine how schooling or migratory dynamics may influence the catchability of the species. In particular, research the assumption of the hyperstability of indices that sample the schooling portion of the stock. | delayed
SEFSC | II. Long Term research needs for stock assessments to be developed within the next 5 years. | o Evaluate otolith chemistry as an approach to define Gag population structure. | delayed
SEFSC | II. Long Term research needs for stock assessments to be developed within the next 5 years. | o Compare genetics of spawning Gag captured by commercial fishermen to juveniles collected in different areas in subsequent months to determine the source of recruits. Consider expanding research to include samples from Mexico to explore gene flow and connectivity. | delayed
SEFSC/GADNR | II. Long Term research needs for stock assessments to be developed within the next 5 years. | o Additional acoustic and traditional tagging is needed on known spawning locations to document spawning migrations or aggregations and return of fish to non-spawning areas. | ongoing
SEFSC | II. Long Term research needs for stock assessments to be developed within the next 5 years. | o Evaluate the effects of environmental variation on the changes in recruitment and survivorship. | ongoing
SCDNR | II. Long Term research needs for stock assessments to be developed within the next 5 years. | o Investigate possible historical changes in sexual maturity. The current estimate of age of sexual maturity is low and unusual for other Lutjanids. | ongoing
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Investigate the potential for a range shift in the black sea bass population, and the potential causes, such as climate change. | ongoing
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Evaluate the frequency and magnitude of recruitment coming from the Gulf of Mexico and south. | ongoing
FWRI | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Design a multi-year study to collect age and gonad samples at spawning sites during the spawning season. This should entail identifying the diurnal usage patterns at spawning sites during the year. | delayed
SEFSC | I. Short Term research needs for stock assessments to be completed in 2020-2023 | o Collect more information on commercial and recreational discards, including some validation using at-sea sampling. | ongoing
| III. Short Term Needs for Spawning Special Management Zones to be completed in the next 5 years. | • Document spawning within Spawning SMZs by priority species in the Snapper Grouper complex. | delayed
SCDNR | III. Short Term Needs for Spawning Special Management Zones to be completed in the next 5 years. | • Collect baseline data for Spawning SMZs. | ongoing
SCDNR | III. Short Term Needs for Spawning Special Management Zones to be completed in the next 5 years. | • Evaluate the sampling program of the Spawning SMZs. The evaluation should review data on compliance, spawning, and determine if current sampling targets are sufficient. | ongoing
SEFSC | III. Short Term Needs for Spawning Special Management Zones to be completed in the next 5 years. | • Develop methods for incorporating the impacts of Spawning SMZs on management actions and stock status. | ongoing
SEFSC | III. Short Term Needs for Spawning Special Management Zones to be completed in the next 5 years. | • Use hydrodynamic modeling to look at connectivity between SMZs and other habitats. | ongoing
| IV. Short Term Needs for MPA monitoring to be completed within the next 5 years. | • Maintain annual monitoring to collect data inside and outside the MPAs to characterize MPAs and enable comparison to reference sites. Identify fish population demographics (e.g. size and age structure, sex ratio, species use of habitat by life stage, spawning activities, etc.) within and adjacent to the MPAs. | ongoing
| IV. Short Term Needs for MPA monitoring to be completed within the next 5 years. | • Characterize spawning by managed species within the MPAs. | delayed
| IV. Short Term Needs for MPA monitoring to be completed within the next 5 years. | • Complete multibeam surveys of the MPAs. | ongoing
? | IV. Short Term Needs for MPA monitoring to be completed within the next 5 years. | • Evaluate the sampling program of the SAFMC MPAs. The evaluation should review data on compliance, species abundance and diversity, and determine if current sampling targets are sufficient. | delayed
? | IV. Short Term Needs for MPA monitoring to be completed within the next 5 years. | • Develop methods for incorporating the impacts of MPA on management actions and stock status. | delayed
FWRI | IV. Short Term Needs for MPA monitoring to be completed within the next 5 years. | • Use hydrodynamic modeling to look at connectivity between MPAs and other habitats. | ongoing
SEFSC/NCSU/GADNR | V. Long Term Needs to be developed within the next 5 years. | • Consider acoustic tagging projects for addressing area-based management research and monitoring needs as noted in the SSMZ and MPA sections. | ongoing
SEFSC/SCDNR | V. Long Term Needs to be developed within the next 5 years. | • Obtain life history traits for all species listed as either Level 1 or 2 in Table 1, including von Bertalanffy growth parameters, maturity, and reproductive rates. | ongoing
SEFSC/SCDNR | V. Long Term Needs to be developed within the next 5 years. | • Initiate long-term continuous monitoring of age structures in the South Atlantic for all species listed as either Level 1 or 2 in Table 1. | ongoing
SEFSC | V. Long Term Needs to be developed within the next 5 years. | • Develop models to predict changes to shrimp, shallow water and deepwater coral, Snapper Grouper, Dolphin Wahoo, and Mackerel populations due to climate change, including changes to species’ distribution, movements, and reproductive patterns. | ongoing
SEFSC | V. Long Term Needs to be developed within the next 5 years. | • Evaluate the cumulative economic and social impacts of existing regulations on the multi-species Snapper Grouper fishery in the South Atlantic. | ongoing
SEFSC | V. Long Term Needs to be developed within the next 5 years. | • Evaluate management strategies to reduce discard mortality in the multi-species Snapper Grouper fishery. | ongoing
SEFSC/GADNR | V. Long Term Needs to be developed within the next 5 years. | • Validate age determination for species in the Snapper-Grouper FMP. | ongoing
SEFSC | V. Long Term Needs to be developed within the next 5 years. | • Provide an evaluation of the independent survey and biological sampling information available for all SAFMC managed stocks that are currently unassessed. This evaluation should document past sampling intensity and current sampling targets and provide guidance on the type of stock assessments feasible given currently available data. | ongoing
SEFSC/GADNR/NCSU | V. Long Term Needs to be developed within the next 5 years. | • Conduct tagging studies of Snapper Grouper species, including the Mid-Atlantic, Gulf, and SA regions, to evaluate movements and estimate demographic rates between regions. | ongoing
SCDNR | V. Long Term Needs to be developed within the next 5 years. | • Update reproductive biology work on shallow water groupers (Red Grouper), to determine latitudinal variation in spawning periodicity and habits. | ongoing
? | V. Long Term Needs to be developed within the next 5 years. | • Investigate juvenile habitat and abundance of shallow water groupers (such as Gag and Red Grouper), to evaluate the effectiveness of current regulations in protecting these species, by looking at changes in abundance and frequency of occurrence. | delayed
FWRI | V. Long Term Needs to be developed within the next 5 years. | • Develop a program for monitoring/evaluating compliance with the use of descending/venting devices. | ongoing
SEFSC/FWRI | VI. Habitat Research and Monitoring Needs | • Map coral distribution in the South Atlantic region. | ongoing
NOS/FWRI/SEFSC/USF/UM | VI. Habitat Research and Monitoring Needs | • Monitor health of coral reef systems. | ongoing
? | VII. Specific Monitoring Priorities | Increase funding for fisheries independent monitoring in the South Atlantic. Specific needs include: | ongoing
? | VII. Specific Monitoring Priorities | o Restoring MARMAP funding to a minimum of $850,000 annually. | ongoing
? | VII. Specific Monitoring Priorities | o Funding MARMAP sufficiently to support reinitiating long bottom longline sampling that provides the only abundance information for deepwater stocks such as Tilefish. | ongoing
? | VII. Specific Monitoring Priorities | o Maintaining funding for SEAMAP at levels sufficient to support long-term fishery independent survey operations. | ongoing
? | VII. Specific Monitoring Priorities | o Maintaining funding for SEFIS to support video survey work. | ongoing
? | VII. Specific Monitoring Priorities | o Increasing funding for SEFIS to support the use of stereo cameras, or other such technology, to measure fish length during the video survey. | ongoing
? | VII. Specific Monitoring Priorities | o Providing funding for the MPA/SMZ monitoring needs noted above. | ongoing
SEFSC/AOML | VII. Specific Monitoring Priorities | • Monitor the mixing rates of Gulf and South Atlantic King Mackerel. Mixing rates may change over time and should therefore be regularly evaluated, although annual monitoring may not be necessary. | ongoing
FWRI/SEFSC | VII. Specific Monitoring Priorities | • Implement a monitoring and research program to address issues relevant to ecosystem management. Topics include trophic interactions, food preferences, predator-prey relationships, and ecosystem connectivity. | ongoing
SEFSC/NCSU | VII. Specific Monitoring Priorities | • Develop monitoring programs for Dolphin and Golden Crab that can support future quantitative stock assessments for these stocks. | ongoing
SEFSC/OST/ACCSP | VII. Specific Monitoring Priorities | • Develop and implement new methods for decreasing uncertainty of recreational catch estimates for federally managed offshore species, including but not limited to enhancements to the MRIP survey, add-on surveys, and new methods for collecting recreational catch data. | ongoing
SEFSC | VII. Specific Monitoring Priorities | • Maintain/improve the ability to document commercial and recreational landings and discards. | ongoing
SEFSC | VIII. SPECIFIC ANNUAL REPORTING REQUESTS | • Provide by June 1 annually, SAFE reports that provide stock status including OFL and MSY, an evaluation of the management program including whether ACLs were met or AMs triggered and addressing reasons for such, results of independent fisheries monitoring, complete landings and discard losses in weight and numbers of fish, fishery dependent monitoring statistics, and measures of effort and economic value for all managed stocks. | delayed
SEFSC | VIII. SPECIFIC ANNUAL REPORTING REQUESTS | • Provide by October 1 annually, a report on the SEFIS program that addresses survey sampling effort, biological sampling intensity, and survey findings for assessed species. This should include updated abundance index trends for all stocks sampled | delayed
SEFSC | VIII. SPECIFIC ANNUAL REPORTING REQUESTS | • Provide annual progress reports, by the SEFSC at the June Council meeting, detailing efforts to implement the research recommendations noted in Council Research and Monitoring Plans. | delayed

## any figures
Age validation of Red Porgy (manuscript in prep)
Figure 1. One year old Red Porgy. Left image of otolith section with white light. Right image of otolith section with epi-fluorescent light showing chemical mark near the first annulus.
Figure 2. One year old Red Porgy showing a strong opaque check mark inside of the true first annulus. Left image of otolith section with white light. Right image of otolith section with epi-fluorescent light showing chemical mark near the first annulus.
Figure 3. 9 year old Red porgy. Otolith section picture taken with white and epi-fluorescent lights simultaneously. Chemical mark is associated with the 7th annulus (opaque zone) with two annuli following - last annulus on margin. Fish was aheld for 2.0 years after marking.