## HOW WORKLOAD IS ESTIMATED
Example discussion level at various stages of FMP development.
And Color Coding Scheme in the following sheets
Type of Discussion | Workload Estimation Weight | Council Meeting Time
Initial Options Paper | 0.5 | 1-2h
Options discussions, review AP/SSC comments | 1 | 3-4h
Review and approve for Hearing | 1 | 3-4h
Address hearing comments | 0.5 | 1-2h
Final Approval | 0.5 | 1-2h
Council Meeting Workload Estimation and Time Management Approach
Council previously directed that 6 FMPs were the most that could be addressed in a Council meeting. Over the last several years this has proven to be an accurate estimate.
To address the current excessive workload and backlog of projects, we attempted to refine this some by considering the level of discussion that occurs at different stages of FMP development. For example, the first time the Council considers an amendment and reviews a general options paper will take less discussion time than a later discussion when actions are reviewed and preferred alternatives selected.
We weighted the different discussion stages as either 1 or 0.5. Summing these weights for a meeting gives an estimate of the discussion time needed. Keeping the sum at or below 6 should keep the workload manageable within a single meeting.
Estimating the workload in this manner for several years forward, and through final approval of projects, provides a long-term persepective on the FMP workload. Individual FMP project schedules may need to be adjusted to address future meetings if the workload rating gets too high. It will also allow us to illustrate the impacts on other projects and on future meeting workloads when projects fall behind.

## 2022-2024 WorkPlan
| SAFMC 2023-2025 WORKPLAN - INCORPORATING PROJECTS UNDERWAY AND UPCOMING ASSESSMENTS |  |  | 2023 Q4 - December Meeting REVISED
Amendments with statutory deadline
| Amend # | Amendment | SAFMC Lead | 2023-12-02 | 2024-03-01 | 2024-06-01 | 2024-09-01 | 2024-12-02 | 2025-03-01 | 2025-06-01 | 2025-09-01 | 2025-12-01 |  |  | Amendments that do not respond to a stock assessment or change to catch level recommendations
UNDERWAY | SG 55 | Scamp and Yellowmouth Grouper Assessment Response | Allie | 2023-12-02: DOC; 2024-03-01: PH; 2024-06-01: DOC; 2024-09-01: A
| SG 56 | Black Sea Bass Assessment Response | Mike |  | AR | O/S | DOC | DOC | PH | DOC | A |  |  | Timeline pending SSC feedback
|  | STATUTORY DEADLINE WORKLOAD SUBTOTAL |  | 0.5 | 1.5 | 1 | 1.5 | 0.5 | 1 | 0.5 | 0.5 | 0
| SG | Long-term RS response (MSE, SG fishery management measures) | TBD | 2023-12-02: Snapper Grouper MSE; 2025-03-01: O/S; 2025-06-01: DOC; 2025-09-01: DOC; 2025-12-01: DOC | PH | DOC | DOC | A
| SG 48 | Wreckfish ITQ Modernization | Christina | 2023-12-02: DOC; 2024-03-01: DOC; 2024-06-01: A |  | May need to be extended, depending on Council and AP feedback
| SG 46 | Private Recreational Permitting and Education | JohnH | 2023-12-02: DOC; 2024-03-01: DOC; 2024-06-01: PH; 2024-09-01: DOC; 2024-12-02: A |  | Adjusted per SG Committee discussion
| SG 44 | YT Snapper Assessment Response (Catch Levels/Allocations) | Allie | 2024-12-02: DOC; 2025-03-01: PH; 2025-06-01: DOC; 2025-09-01: A |  | Timeline depends on feedback from FL FWC, SA SSC, and Gulf SSC
| SG Reg 36 | Gag and Black Grouper Rec Vessel Limit/BSB Ropeless Pot Gear | Mike | 2023-12-02: O/S; 2024-03-01: DOC; 2024-06-01: PH; 2024-09-01: A
| DW Reg 3 | Dolphin (Recreational Measures) | JohnH | Dolphin MSE (through mid-2025) |  |  |  | DOC | DOC | PH | DOC | A |  | Moved to December 2024 per DW Committee guidance in June 2023
| CMP 13 | FW AM Spanish Mackerel Assessment Response | Christina | 2023-12-02: DOC; 2024-03-01: PH; 2024-06-01: A
|  | UNDERWAY FMP WORKLOAD SUBTOTAL |  | 3.5 | 4.5 | 4 | 2.5 | 2 | 3.5 | 3 | 2.5 | 1.5
PLANNED | CMP | Plan AM Spanish Mackerel Assessment Response | Christina | 2024-03-01: Mackerel Port Meetings; 2025-06-01: O/S; 2025-09-01: DOC; 2025-12-01: DOC | PH | DOC | A |  | Starts after the Mackerel Port Meetings
| SG | Vermilion Snapper Interim Assessment or Com. Trip Limit Adjustment | TBD | 2024-03-01: AR; 2024-06-01: O/S; 2024-09-01: PH; 2024-12-02: DOC; 2025-03-01: A
| SG | Mutton Snapper Assessment Response | TBD |  |  |  | (SSC) | AR | (AP) | O/S | DOC | DOC | PH | DOC | A |  | Start date depending on assessment approval by the SSC
| SG | Golden Tilefish Assement Response | TBD |  |  |  | (SSC) | AR | (AP) | O/S | DOC | DOC | PH | DOC | A |  | Start date depedning on assessment approval by the SSC
| SG | Unassessed Stocks ABC | Mike |  |  |  | (SSC) | AR | (AP) | O/S | DOC | DOC | PH | DOC | A |  | Timeline pending SSC feedback
| WORKLOAD SUBTOTAL: FMP Projects listed Above. Target maximum is 6 |  |  | 3.5 | 5 | 4.5 | 3 | 4 | 4 | 5.5 | 6.5 | 3.5
| FMP ITEMS PER MEETING: Target maximum is 8 |  |  | 5 | 7 | 7 | 5 | 8 | 5 | 8 | 8 | 6
| OTHER COUNCIL ACTIVITIES |  |  | 2023-12-01 | 2024-03-01 | 2024-06-01 | 2024-09-01 | 2024-12-01 | 2025-03-01 | 2025-06-01 | 2025-09-01 | 2025-12-01
|  | EVERY MEETING - Liaison, Agency, Staff Reports |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | AP or SSC Selection | KI/CC | 2023-12-01: 0.5; 2024-06-01: 0.5; 2024-12-01: 0.5; 2025-06-01: 0.5; 2025-12-01: 0.5
|  | SEDAR Committee | CC | 2023-12-01: 0.5; 2024-03-01: 0.5; 2024-09-01: 0.5; 2025-03-01: 0.5; 2025-09-01: 0.5
|  | Citizen Science Committee | JB | 2023-12-01: 0.5; 2024-06-01: 0.5; 2024-12-01: 0.5; 2025-06-01: 0.5; 2025-12-01: 0.5
|  | Habitat Committee (Upcoming Blueprint and EFH Review) | KH | 2023-12-01: 0.5; 2024-06-01: 0.5; 2024-09-01: 0.5; 2025-03-01: 0.5; 2025-09-01: 0.5 |  | Added to December to discuss AP report, AP workplan, and EFH update. Dropped for March.
|  | Outreach and Communications Committee | KI/NS | 2024-06-01: 0.5; 2024-12-01: 0.5; 2025-06-01: 0.5; 2025-12-01: 0.5
| SUGGEST PICK ONE FOR MARCH | SG Commercial Permit Discussion (SG Unlimited 2 for 1 topic and SG 225 Limited Permits) | TBD | 2024-03-01: 0.5 |  | Added per Snapper Grouper Committee
|  | For-Hire Limited Entry Discussion | TBD | 2024-03-01: 0.5 |  | Added per Snapper Grouper Committee
|  | Coral HAPC Expansion Discussion | KH | 2024-06-01: 0.5 |  | Added per Habitat Committee
|  | Coral 10 IPT report | KH | 2024-03-01: 0.5 |  | Added per Habitat Committee
|  | Mackerel Port Meetings | CW | 2023-12-01: 0.5; 2024-03-01: 0.5; 2025-03-01: 1
|  | Dolphin MSE Progress Update | SEFSC | 2023-12-01: 0.5; 2024-06-01: 0.5
|  | Dolphin MSE Report | SEFSC | 2024-12-01: 0.5
|  | SG Reg 35 Related Discussion | MS | [10 empty] | Added per Snapper Grouper Committee | bar: 2023-12-01 to 2024-03-01
|  | Allocation Reviews (per trigger policy) | JH | [10 empty] | Added in response to revised trigger policy | bar: 2024-09-01
|  | SG Discard White Paper | TBD
| WORKLOAD SUBTOTAL: Recurring and special topic activities |  |  | 5 | 4 | 3.5 | 2.5 | 2.5 | 2.5 | 2 | 1.5 | 2
| WORKLOAD TOTAL : FMP projects (Line 26) + Recurring & special topics (Line 41). Target is maximum 8 |  |  | 9 | 9 | 8 | 5.5 | 6.5 | 6.5 | 7.5 | 8 | 5.5
Other Amendments underway, requested, or anticipated in 2024-2026
| Committee | Amendment | Target Start
| SG | Blueline Tilefish Assessment Response | 2025-06-01
| SG | Gray Triggerfish Assessment Response | 2026-06-01
| SG | Address sunsetting of Spawning SMZs | ?
| SL and SG | Spiny lobster & SG permit holder item | Late 2025
| DW | Dolphin Wahoo Pelagic Longline Measures | Upon completion of MSE
| DW | Dolphin Wahoo regional management and other items | ?
| Coral | Coral AM 10 | ?
Other Activities

## General Timeline
Generalized FMP Timeline Example
Illustrates a signficant FMP Amendment - not a framework to update ACL
Plan Code | Clock | eg mo | Council Meeting Activity | Note | More Info
AR | 1 | June | Assessment Report Presented (or FMP started formally) | Also present general fishery info - landings+effort trends, recent years, by state, season, etc; catch per trip frequency, recent mgmt changes or AMs implemented | When initiated by an AR: Provide ACL options. - there really are not that many, at least for FMPs without allocation changes. When not an AR: discuss the problem Council wishes to solve and why.
(AP),(SSC) | 4 | Oct | AP or SSC review | Include in council meet schedule to show work is progressing, explain why skipping a meeting. Deadline to Obtain official IPT dataset for analysis | Intent-bring in AP sooner, help develop response to stock condition or the problems to solve, help develop items to scope
O/S | 6 | Dec | Present Options, Approve for Scoping | Council select the preferred ACL at this meeting | Approve ACLs by this meeting - critical to the evaluations of specific actions that will follow
DOC | 9 | March | Review Actions-Alternatives | Review scoping comments, finalize range of actions and alternatives
DOC | 12 | June | Review Actions-Alternatives, Select Preferreds | Review evaluation of actions and alternatives. Select preferred options where appropriate and feasible. Need for this or an additioanl meeting of this type determined by FMP complexity and number of actions. | Consider dividing topics across meeting for a complex FMP with many actions - e.g., one meeting on rec topics, one on comm topics, so that if several meetings needed, avoid starting each meeting by discussing action 1 and going over the entire FMP in action order. May add in additional SSC or AP meetings between OS and PH as needed
PH | 15 | Sept | Review Actions-Alternatives, Select preferreds, and Approve for hearings | Review evaluation of actions and alternatives, select preferred alternatives for hearing
doc | 18 | Dec | Review hearing comments, revise preferreds
A | 21 | March | review any additional analysis, approve for submission | Need to have codified text in time to review
| 24 | June | FMP Submitted by | final draft, codified, etc - submit before the next meeting