## HOW WORKLOAD IS ESTIMATED
Example discussion level at various stages of FMP development.
And Color Coding Scheme in the following sheets
Type of Discussion | Workload Estimation Weight | Council Meeting Time
Initial Options Paper | 0.5 | 1-2h
Options discussions, review AP/SSC comments | 1 | 3-4h
Review and approve for Hearing | 1 | 3-4h
Address hearing comments | 1 | 1-2h
Final Approval | 1 | 1-2h
Council Meeting Workload Estimation and Time Management Approach
Council previously directed that 6 FMPs were the most that could be addressed in a Council meeting. Over the last several years this has proven to be an accurate estimate.
To address the current excessive workload and backlog of projects, we attempted to refine this some by considering the level of discussion that occurs at different stages of FMP development. For example, the first time the Council considers an amendment and reviews a general options paper will take less discussion time than a later discussion when actions are reviewed and preferred alternatives selected.
We weighted the different discussion stages as either 1 or 0.5. Summing these weights for a meeting gives an estimate of the discussion time needed. Keeping the sum at or below 6 should keep the workload manageable within a single meeting.
Estimating the workload in this manner for several years forward, and through final approval of projects, provides a long-term persepective on the FMP workload. Individual FMP project schedules may need to be adjusted to address future meetings if the workload rating gets too high. It will also allow us to illustrate the impacts on other projects and on future meeting workloads when projects fall behind.

## 2021-2022 WorkPlan
| SAFMC 2021-2022 WORKPLAN - INCORPORATING PROJECTS UNDERWAY AND UPCOMING ASSESSMENTS | [5 empty] | 2021 Q4 DRAFT - December Meeting Revised
| Amend # | Amendment | SAFMC Lead | 2021-12-01 | 2022-03-01 | 2022-06-01 | 2022-09-01 | 2022-12-01 | 2023-03-01 | 2023-06-01 | 2023-09-01 | 2023-12-02 |  |  | Amendments with statutory deadline
UNDERWAY | SG 50 | Red Porgy Rebuilding/Allocate | Myra | 2021-12-01: DOC; 2022-03-01: A |  |  | Amendments that do not respond to a stock assessment
| SG 51 | Snowy Grouper Assess Response | Allie | 2021-12-01: DOC; 2022-03-01: DOC; 2022-06-01: PH; 2022-09-01: DOC; 2022-12-01: A
| SG 52 | Gag Assess Response | Allie | O/S | DOC | DOC | PH | DOC | A
|  | MUST DO WORKLOAD SUBTOTAL |  | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 0.5
|  | Short-term FW AM (gear, area and seasonal closures, size limit) | Mike | O/S | DOC | DOC | PH | DOC | A?
|  | Long-term RS response (MSE, RS reference points) | TBD | 2022-03-01: (MSE and scoping begins); 2022-12-01: (Public Input and AP); 2023-06-01: DOC; 2023-09-01: DOC; 2023-12-02: DOC | DOC | PH | DOC | A? |  | Amendment would begon upon completion of the MSE
| SG 48 | Wreckfish ITQ Modernization | Christina | SKIP | DOC | SKIP | PH? | SKIP | DOC | SKIP | A |  |  | Every other meeting per Council guidance. Extended 6 months.
| SG 44 | YT Snapper Assess/Allocate/longterm | Myra | 2021-12-01: DOC; 2022-03-01: DOC; 2022-06-01: PH; 2022-09-01: DOC; 2022-12-01: A
| SG 49 | Greater AJ Assess/Allocate | Mike | 2021-12-01: PH; 2022-03-01: DOC; 2022-06-01: A
| SG 53 | Golden Tilefish Assess Response | Roger | 2021-12-01: O/S; 2022-03-01: DOC; 2022-06-01: PH; 2022-09-01: DOC; 2022-12-01: A
| CMP 34 | King Mack Assess Response | Christina | 2021-12-01: DOC; 2022-03-01: A
| CMP 32 | Gulf Cobia Amendment (Gulf is lead) | Christina | bar: 2021-12-01
| CMP 33 | Gulf King Mackerel (Gulf is lead) | Christina | 2021-12-01: DOC; 2022-03-01: SKIP; 2022-06-01: PH; 2022-09-01: A
| SG 45/GC 11/Sa 4/C 11 | ABC Control Rule | Mike/Judd | 2021-12-01: SKIP; 2022-03-01: DOC; 2022-06-01: PH; 2022-09-01: DOC; 2022-12-01: A
|  | Dolphin Wahoo (Recreational Measures) | JohnH | SKIP | O/S | DOC | PH | DOC | A
PLANNED |  | Assessment response - must do
|  | Spanish Mackerel Assess Response (04/22) | Christina |  |  | (SSC) | AR | (AP) | O/S | DOC | DOC | PH | DOC | A |  |  | Moved due to delay in assessment
|  | Scamp OA Response (10/22) | TBD | 2022-12-01: AR; 2023-03-01: (AP); 2023-06-01: O/S; 2023-09-01: DOC; 2023-12-02: DOC | PH | DOC | A
|  | Mutton Assess Response (01/23) | TBD | 2023-03-01: (SSC); 2023-06-01: AR; 2023-09-01: (AP); 2023-12-02: O/S | DOC | DOC | PH | DOC | A
|  | Black Sea Bass Assess Response (03/23) | TBD | 2023-03-01: (SSC); 2023-06-01: AR; 2023-09-01: (AP); 2023-12-02: O/S | DOC | DOC | PH | DOC | A
|  | Vermlion Snapper Assess Response (03/23) | TBD | 2023-03-01: (SSC); 2023-06-01: AR; 2023-09-01: (AP); 2023-12-02: O/S | DOC | DOC | PH | DOC | A
|  | FMP WORKLOAD SUBTOTAL |  | 5.5 | 7 | 6.5 | 6.5 | 4.5 | 3 | 4.5 | 3.5 | 3.5
|  | NEW 2022 (Dolphin LongLine) | JohnH |  | O/S | DOC | DOC | DOC | PH | DOC | A |  |  |  |  | Timeline depends on updated Biological Opinion
|  | NEW 2022 (Com E-Logbooks) | TBD | 2022-06-01: O/S; 2022-09-01: PH; 2022-12-01: A
| SG 46 | NEW 2022 (Rec Reporting Restart?) | TBD |  |  |  | AR | (AP) | O/S | DOC | DOC | PH | DOC | A
| WORKLOAD SUBTOTAL: FMP Projects listed Above. Target is 6 |  |  | 5.5 | 7.5 | 7.5 | 8 | 6 | 4.5 | 5.5 | 5 | 4.5
| FMP ITEMS PER MEETING: Target is 8 |  |  | 10 | 12 | 11 | 13 | 10 | 7 | 8 | 6 | 7
| OTHER COUNCIL ACTIVITIES |  |  | 2021-12-01 | 2022-03-01 | 2022-06-01 | 2022-09-01 | 2022-12-01 | 2023-03-01 | 2023-06-01 | 2023-09-01 | 2023-12-01
|  | Selection AP or SSC | KI/CC | 2021-12-01: 0.5; 2022-06-01: 0.5; 2022-12-01: 0.5; 2023-06-01: 0.5; 2023-12-01: 0.5
|  | SEDAR Committee | CC | 2021-12-01: 0.5; 2022-03-01: 0.5; 2022-09-01: 0.5; 2023-03-01: 0.5; 2023-09-01: 0.5 |  | Moved to December meeting
|  | Citizen Science Committee | JB | 0.5 | Update | 0.5 | Update | 0.5 | Update | 0.5 | Update | 0.5
|  | Habitat Committee | RP | 2022-03-01: 0.5; 2022-09-01: 0.5; 2023-03-01: 0.5; 2023-09-01: 0.5 |  | Moved to March: Business OTHER than Coral 10 or Blueprint
|  | Law Enforcement Committee | MB | 2021-12-01: LEOY; 2022-06-01: 0.5; 2022-09-01: LEOY; 2023-06-01: 0.5; 2023-09-01: LEOY
|  | Outreach and Communitcations Committee | CR | 0.5 | Update | 0.5 | Update | 0.5 | Update | 0.5 | Update | 0.5
|  | Allocation Decision Tree Blueprint | CW/JH/MS | 2021-12-01: *; 2022-03-01: 0.5 |  | *Suggest review at special meeting in Jan or Feb. Placeholder for follow up at the March meeting
|  | Species Shift Scenario Planning | RP | 2021-12-01: Update; 2022-03-01: Update; 2022-06-01: Update; 2022-09-01: Update; 2022-12-01: Update
|  | Joint WorkGroup Rec Sec 102 | JC | 2021-12-01: Update |  | Will be tied in with SG Omnibus discussion
|  | SAFMC Rec Data workgroup | MB/JC | 2021-12-01: Update; 2022-03-01: 0.5
|  | SG 2for1 permit eval (from EO) | MS/AI/MB/CW/JH | 2021-12-01: 0.5 |  | Added to December meeting per Council's discussion
|  | Habitat Blueprint | MB/JC/RP | [10 empty] | **Suggest review at special meeting Fall 2022 | bar: 2022-09-01
|  | SBRM Approval | SERO | 2021-12-01: 0.5
|  | 5-year review of EFH | TBD | 2022-09-01: 0.5; 2022-12-01: 0.5
| WORKLOAD SUBTOTAL: Recurring and special topic activities |  |  | 3 | 2 | 2 | 1.5 | 2 | 1 | 2 | 1 | 1.5
| WORKLOAD TOTAL : Current FMP projects (line 15) + recurring & special topics (Line 22). Target is 8 |  |  | 8.5 | 9.5 | 9.5 | 9.5 | 8 | 5.5 | 7.5 | 6 | 6
Other Amendments underway, requested, or anticipated to address assessments expected in 2022-2024
| Committee | Amendment | Target Start
| SG | Unassessed ABC-ACL-EC | ? | 2021-12-01: Suggest to start after ABC CR Amendment (June or December 2023)
| DW | Dolphin Wahoo regional management and other items | ? | 2021-12-01: Amendment could address regional management, limited access for com. permit, and FH baglimit slales
| SG | Red Grouper Assessment Response | 2024-06-01
| SG | Gray Triggerfish Assessment Response | 2024-12-01
| SG | Golden Tilefish Assessment Response | 2024-12-01
| SG | Blueline Tilefish Assessment Response | 2024-12-01
| SG | Recreational AMs (SG 31) | Work suspended
Other Activities
| Workshop | Mackerel Port Meetings | ? | 2021-12-01: Suggest to start after SM assessment
Note on C27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Do we need this here? Moved up from "other amendments"

## General Timeline
Generalized FMP Timeline Example
Illustrates a signficant FMP Amendment - not a framework to update ACL
Plan Code | Clock | eg mo | Council Meeting Activity | Note | More Info
AR | 1 | June | Assessment Report Presented (or FMP started formally) | Also present general fishery info - landings+effort trends, recent years, by state, season, etc; catch per trip frequency, recent mgmt changes or AMs implemented | When initiated by an AR: Provide ACL options. - there really are not that many, at least for FMPs without allocation changes. When not an AR: discuss the problem Council wishes to solve and why.
(AP),(SSC) | 4 | Oct | AP or SSC review | Include in council meet schedule to show work is progressing, explain why skipping a meeting. Deadline to Obtain official IPT dataset for analysis | Intent-bring in AP sooner, help develop response to stock condition or the problems to solve, help develop items to scope
O/S | 6 | Dec | Present Options, Approve for Scoping | Council select the preferred ACL at this meeting | Approve ACLs by this meeting - critical to the evaluations of specific actions that will follow
DOC | 9 | March | Review Actions-Alternatives | Review scoping comments, finalize range of actions and alternatives
DOC | 12 | June | Review Actions-Alternatives, Select Preferreds | Review evaluation of actions and alternatives. Select preferred options where appropriate and feasible. Need for this or an additioanl meeting of this type determined by FMP complexity and number of actions. | Consider dividing topics across meeting for a complex FMP with many actions - e.g., one meeting on rec topics, one on comm topics, so that if several meetings needed, avoid starting each meeting by discussing action 1 and going over the entire FMP in action order. May add in additional SSC or AP meetings between OS and PH as needed
PH | 15 | Sept | Review Actions-Alternatives, Select preferreds, and Approve for hearings | Review evaluation of actions and alternatives, select preferred alternatives for hearing
doc | 18 | Dec | Review hearing comments, revise preferreds
A | 21 | March | review any additional analysis, approve for submission | Need to have codified text in time to review
| 24 | June | FMP Submitted by | final draft, codified, etc - submit before the next meeting