## Overall Schedule
Council's |  | 2012 | [11 empty] | 2013 | [11 empty] | 2014
Priorities | SAFMC CY 2012-13 SCHEDULE | Jan | Feb | Mar | Ap | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Ap | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Ap | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
(as of March 2013) | FMPS/AMENDMENTS/FRAMEWORKS
Done | Snapper Grouper Regulatory Amendment 13 Adj ACLs MRFSS/MRIP Calibration |  |  |  |  | Dec: P/F/S
2 | Snapper Grouper Regulatory Amendment 14 Multiple Species | [17 empty] | Ah |  | P | A/F/S | bar: Sep; 2013 Mar
Done | Emergency Rule for Yellowtail Snapper | bar: Sep
Done | Snapper Grouper Regulatory Amendment 15 Yellowtail Snapper, Gag Trigger & Red Snapper |  |  |  |  | Dec: P/F; 2013 Jan: S
5 | SG Reg Am 16 Golden Tilefish (2wk on & 2 off) Remove BSB Pot Closure | [17 empty] | Ah |  |  | O |  |  | P/A | bar: 2013 Mar
8 | Snapper Grouper Regulatory Amendment 17 MPAs Speckled Hind/Warsaw | [20 empty] | O | bar: Dec; 2013 Mar
Done | Snapper Grouper Regulatory Amendment 18 (Vermilion & Red Porgy) |  |  |  |  | Dec: O; 2013 Mar: P/F/S
1 (Done) | Snapper Grouper Regulatory Amendment 19 Black Sea Bass | [16 empty] | P/F/S
Done | Generic Amendment: For-Hire Reporting in South Atlantic Only |  |  |  |  | Dec: A; 2013 Mar: P/F/S
10 | Snapper Grouper Amendment 22 (Tags to track catches of Red Snapper, Golden Tile, Snowy & Wreckfish) | [17 empty] | O |  |  | O | bar: Sep
Done | Snapper Grouper Amendment 27 Blue Runner/Yellowtail & Mutton Management |  |  |  |  | Dec: Ah; 2013 Jan: P; 2013 Mar: A/F/S
Done | Snapper Grouper Amendment 28 Red Snapper Framework |  |  |  |  | Dec: P/F; 2013 Jan: S
9 | Snapper Grouper Am 29 & D-W Am X (Allocations, ORCS revisions to Control Rule) 2014 | [17 empty] | Discuss | [5 empty] | As | Ps | Ps | O
7 | Snapper Grouper Amendment 30 (VMS) | [15 empty] | P? | P? | A/F/S | bar: Dec; 2013 Mar
6 | Dolphin/Wahoo Amendment 5 (Fmwk, ABC/ACL adj, Alloc) |  |  |  |  | Dec: AS; 2013 Jan: Ps; 2013 Mar: O |  |  | Ah |  | P | A/F/S
work halted | Golden Crab Amendment 6 (Catch Shares) | P | P |  |  | 2013 Mar: Discuss
13 | Fishery Ecosystem Plan (Update #1) - start in 2014 | [23 empty] | As | Ps | Ps | O |  |  | Ah | NDC | P/N | A/F/S
14 | Comprehensive Ecoystem-Based Amendment #3(2012), #4(2013) & #5(2014) - Bycatch | Ps | Ps | O |  | Jun: Ah; Jul: NDC; Aug: P/N; 2013 Mar: A/F/S | [8 empty] | As | Ps | Ps | O |  |  | Ah | NDC | P/N | A/F/S
12 | Coral Amendment 8 (Coral HAPCs & Transit thru Oculina Bank HAPC) | [17 empty] | Ah |  | P | A/F/S | bar: 2013 Mar
| Shrimp Closure Work (if required; done in 2011) |  |  | A | [23 empty] | A | bar: 2013 Mar
Done | Shrimp Amendment 9 (Closure process & MSST) | Ps | Ps | O |  | Jun: Ah; Jul: NDC; Aug: P/N; Sep: A/F/S
4 | Joint Mackerel Amendment 19 (Prohibit Bag Limit Sales & Permits) | [17 empty] | Ah |  | P | A/F/S
9 | Joint Mackerel Amendment 20 (Boundaries & Timing) | [17 empty] | Ah |  | P | A/F/S
11 | South Atlantic CMP Framework (Size/Bag/Trip Limits) | [17 empty] | Ah |  | P | A/F/S | bar: 2013 Mar
3 | Joint SA/GM Amendment (Commercial Logbooks) - timing needs to be determined
| Gulf Regulatory Amendment (Headboat Reporting in Gulf of Mexico only) |  |  |  |  | 2013 Mar: P/F/S
| Joint Spiny Lobster Amendment 11 (NMFS lead; Protected Resources Issues) | P | P | F/S
| Generic Amendment to Re-Examine Sector Allocations (2014) | [23 empty] | As | Ps | Ps | O
| Joint GM/SA Dealer Amendment | Ps | Ps |  |  | Jun: Ah; Jul: NDC; Aug: P/N; Sep: A/F; Oct: S; 2013 Mar: P/F/S
Workshops with Fishermen - start in 2012
Calico Scallop FMP? (Separate FMP or Include in a Comprehensive FEP Am)
Red = New Amendments added during December 2012 meeting
D = Plan development
AS = Approve for public scoping
Ps = Public scoping
O = Develop options/review options paper
Ah = Approve for public hearing
P = Public hearing
IP = Informal public hearing
N = NMFS informal review
A = Council approve
F = Final Review
NDC = NMFS determination of completeness for DEIS Filing
S = Submit for Secretarial review
BLUE = DONE

## Council Decisions March 2012
Objective=Finish CEBA-3 in 2012
Items Scoped for CEBA-3 | CEBA-3 | CEBA-4 | Framework | Drop
| (CY 2012) | (CY 2013) | (after 2013 assmt.)
1. Expand Coral HAPCs | 1. Expand Coral HAPCs
2. Prohibit Powerheads |  | 2. Prohibit Powerheads
3. MPAs & HAPCs for SpHind & Warsaw | 3. MPAs & HAPCs for SpHind & Warsaw
4. Snapper Ledge = MPA |  | 4. Snapper Ledge = MPA
5. Rec. tag program for deepwater sp. |  | 5. Rec. tag program for deepwater sp.
6. Hogfish |  |  | 6. Hogfish
7. Gray triggerfish |  |  | 7. Gray triggerfish
8. African pompano |  |  |  | 8. African pompano
9. Permits & Data reporting | 9. Permits & Data reporting
Distribution of Work
Ecosystem Committee | 1. Expand Coral HAPCs
Snapper Grouper Committee | 3. MPAs & HAPCs for SpHind & Warsaw
Data Collection Committee | 5. Rec. tag program for deepwater sp.
9. Permits & Data reporting
Golden Crab Committee | Golden Crab Amendment 6
Shrimp Committee | Shrimp Amendment 9
Items to Complete in 2012 - MARCH MEETING | Comments
1. CEBA-3 - FINISH IN DECEMBER? | Approve PH June; PH Aug.; Final Sept (Dec @ latest)
2. SG Reg Am 12 (Golden Tilefish) - DONE | to SOC by March 29, 2012 if approved @ March meeting
3. Comprehensive ACL/Allocation Amendment | develop alternatives
4. Golden Crab Am 6 (Catch Share) - RESOLVED SEPT? | preferreds @ March; final @ June
5. Joint Mack Am 19 (Permits & Sale) | Approve PH June; PH Aug.; Final Sept (Dec @ latest)
6. SG Am 18B (Golden Tilefish) - DONE | alternatives @ March, PH June; final approval June
7. Joint Dealer Amendment - DONE SEPTEMBER | Approve PH June; PH Aug.; Final Sept (must be implemented effective 1/1/13)
8. Joint Mack Am 20 (Boundaries & Transit) | Approve PH June; PH Aug.; Final Sept (Dec @ latest)
9. Shrimp Am 9 - DONE | Approve PH June; PH Aug.; Final Sept (Dec @ latest)
10. Analysis of Voluntary IFQ
9. Other Reg Amendments???? | April SSC review of MRIP so may have new OFLs & ABCs?????
Prepare very brief Regulatory Amendment/Categorical Exclusion for each FMP affected
Note: Assumes Snapper Grouper Am 20B is deferred until 2013 at least to see what happens with new, much reduced ACL.

## Council Decisions Sept 2012
Items to Complete in 2012/13 - SEPTEMBER MEETING | Comments

## Council Ranking 2012-13
| HIGH | MED | LOW | RANK | ORDER
SAFMC CY 2012/13 SCHEDULE
FMPS/AMENDMENTS/FRAMEWORKS
Snapper Grouper Regulatory Amendment 13 Adj ACLs MRFSS/MRIP Calibration | 13 |  |  | 39 | 1
Snapper Grouper Regulatory Amendment 14 Multiple Species | 5 | 5 | 4 | 29 | 5
Emergency Rule for Yellowtail Snapper | 12 | 1 |  | 38 | 2
Snapper Grouper Regulatory Amendment 15 Yellowtail Snapper, Gag Trigger & Red Snapper | 6 | 4 | 1 | 27 | 6
Snapper Grouper Amendment XX Yellowtail & Mutton (SAFMC Management) | 1 | 5 | 2 | 15 | 14
Snapper Grouper Regulatory Amendment 16 Golden Tilefish (2wk on & 2 off) | 4 | 6 | 2 | 26 | 7
Snapper Grouper Regulatory Amendment 17 MPAs Speckled Hind/Warsaw |  | 7 | 6 | 20 | 10
Emergency Rule to remove Gag triggering closure of all shallow water groupers | 9 | 2 | 1 | 32 | 3
Snapper Grouper Amendment 22 (Tag Program Golden Tilefish, Snowy & Wreckfish) |  | 4 | 9 | 17 | 12
Snapper Grouper Amendment 26 (Allocations, ORCS revisions?) | 3 | 6 | 3 | 24 | 9
Snapper Grouper Amendment 27 Blue runner
Dolphin/Wahoo Amendment X (Fmwk, ABC/ACL adj, Alloc) | 1 | 4 | 8 | 19 | 11
Golden Crab Amendment 6 (Catch Shares) | 0 | 3 | 10 | 16 | 13
Fishery Ecosystem Plan (Update #1) - start in 2014 | 1 | 3 | 8 | 17 | 12
Comprehensive Ecoystem-Based Amendment #3(2012), #4(2013) & #5(2014) | 1 | 5 | 4 | 17 | 12
Coral Amendment 7 (Coral HAPCs & Transit thru Oculina Bank HAPC)
Shrimp Closure Work (if required; done in 2011) | 1 |  |  | 3 | 16
Shrimp Amendment 9 (Closure process & MSST) | 1 |  |  | 3 | 16
Joint Mackerel Amendment 19 (Prohibit Bag Limit Sales & Permits) - timing | 4 | 9 | 0 | 30 | 4
Joint Mackerel Amendment 20 (Boundaries & Timing) - timing | 1 | 11 | 1 | 26 | 7
Joint Mackerel Framework (Size/Bag/Trip Limits) - timing | 0 | 12 | 1 | 25 | 8
Joint Spiny Lobster Amendment 11 (NMFS lead; Protected Resources Issues) |  |  | 1 | 1 | 17
Joint GM/SA Dealer Amendment | 6 | 4 | 1 | 27 | 6
Workshops with Fishermen - start in 2012 | 1 | 8 | 1 | 20 | 10
Calico Scallop FMP? (Separate FMP or Include in a Comprehensive FEP Am) |  |  | 11 | 11 | 15

## Major Council Actions
| Sent to | Public
Council Decebmer 2012 | NMFS | Hearings
SG Reg Am 13 (Adj ACLs MRFSS/MRIP) | 2012-12-14
SG Am 28 (Red Snapper Framework) | 2013-01-24
SG Reg Am 15 (Yellowtail & Gag Trigger) | ?
Council March 2013
SG Reg Am 18 (Vermilion & Red Porgy) | ?
SG Am 27 (Nassau, Blue runner, fmwk, bag) | ?
Joint SA/GM Headboat Reporting SA Only | ?
CEBA 3 (Bycatch) | ?
SG Am 30 (VMS) |  | April/May
Council June 2013
SG Am 30 (VMS) | ?
SG Reg Am 14 (multiple items) |  | August
SG Reg Am 16 (golden tilefish; 2 wks on, 2 off) |  | August
Mack Am 19 (Bag sales & Permits) |  | August
Mack Am 20 (Boundaries, Timing & Cobia) |  | August
Mack Am 19/20 and Framework |  | August
Dolphin/Wahoo Amendment 5 (ACLs, others) |  | August
Coral Amendment 8 (HAPCs) |  | August

## Ranking March 2013
| ORDER | HIGH | MED | LOW | RANK | ORDER
SAFMC CY 2012/13 SCHEDULE | (9/12) |  |  |  |  | (3/13)
FMPS/AMENDMENTS/FRAMEWORKS
Snapper Grouper Regulatory Amendment 13 Adj ACLs MRFSS/MRIP Calibration | 1
Snapper Grouper Regulatory Amendment 14 Multiple Species | 5
Emergency Rule for Yellowtail Snapper | 2
Snapper Grouper Regulatory Amendment 15 Yellowtail Snapper, Gag Trigger & Red Snapper | 6
Snapper Grouper Amendment XX Yellowtail & Mutton (SAFMC Management) | 14
Snapper Grouper Regulatory Amendment 16 Golden Tilefish (2wk on & 2 off) | 7
Snapper Grouper Regulatory Amendment 17 MPAs Speckled Hind/Warsaw | 10
Snapper Grouper Regulatory Amendment 18 Vermilion & Red Porgy
Emergency Rule to remove Gag triggering closure of all shallow water groupers | 3
Snapper Grouper Amendment 22 (Tag Program Golden Tilefish, Snowy & Wreckfish & Red snapper) | 12
Snapper Grouper Amendment 27 Blue runner, Nassau, bag & fmwk | 9
Snapper Grouper Amendment 28 Red Snapper Framework
Snapper Grouper Amendment 26 29 (Allocations, ORCS revisions?)
Dolphin/Wahoo Amendment X 5 (Fmwk, ABC/ACL adj, Alloc) | 11
Golden Crab Amendment 6 (Catch Shares) | 13
Fishery Ecosystem Plan (Update #1) - start in 2014 | 12
Comprehensive Ecoystem-Based Amendment #3(2012), #4(2013) & #5(2014) (Bycatch only) | 12
Generic SG, DW & CMP For-Hire Reporting (SA Only)
Generic Commercial Logbook Reporting
Snapper Grouper Amendment 30 (VMS)
Coral Amendment 7 8 (Coral HAPCs & Transit thru Oculina Bank HAPC)
Shrimp Closure Work (if required; done in 2011) | 16
Shrimp Amendment 9 (Closure process & MSST) | 16
Joint Mackerel Amendment 19 (Prohibit Bag Limit Sales & Permits) - timing | 4
Joint Mackerel Amendment 20 (Boundaries & Timing) - timing | 7
Joint Mackerel Framework (Size/Bag/Trip Limits) - timing | 8
Joint Spiny Lobster Amendment 11 (NMFS lead; Protected Resources Issues) | 17
Joint GM/SA Dealer Amendment | 6
Workshops with Fishermen - start in 2012 | 10
Calico Scallop FMP? (Separate FMP or Include in a Comprehensive FEP Am) | 15