## Overall Schedule
| 2012 | [11 empty] | 2013 | [11 empty] | 2014
SAFMC CY 2012-13 SCHEDULE | Jan | Feb | Mar | Ap | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Ap | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Ap | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
FMPS/AMENDMENTS/FRAMEWORKS
Snapper Grouper Regulatory Amendment 13 Adj ACLs MRFSS/MRIP Calibration |  |  |  |  | Dec: P/F/S
Snapper Grouper Regulatory Amendment 14 Multiple Species | [17 empty] | Ah |  | P | A/F/S | bar: Sep; 2013 Mar
Emergency Rule for Yellowtail Snapper | bar: Sep; Dec
Snapper Grouper Regulatory Amendment 15 Yellowtail Snapper, Gag Trigger & Red Snapper |  |  |  |  | Dec: P/F/S; 2013 Jan: P; 2013 Mar: A/F/S
Snapper Grouper Regulatory Amendment 16 Golden Tilefish (2wk on & 2 off) | [17 empty] | Ah |  | P | A/F/S | bar: 2013 Mar
Snapper Grouper Regulatory Amendment 17 MPAs Speckled Hind/Warsaw | bar: Dec; 2013 Mar
Snapper Grouper Regulatory Amendment 18 (Vermilion & Red Porgy) |  |  |  |  | Dec: O; 2013 Mar: P/F/S
Generic Snapper Grouper, Dolphin Wahoo & Coastal Migratory Pelagics Am (For-Hire Reporting) |  |  |  |  | Dec: A; 2013 Mar: P/F/S
Snapper Grouper Amendment 22 (Tags to track catches of Red Snapper, Golden Tile, Snowy & Wreckfish) | [17 empty] | O |  |  | O | bar: Sep; Dec
Snapper Grouper Amendment 27 Blue Runner/Yellowtail & Mutton Management |  |  |  |  | Dec: Ah; 2013 Jan: P; 2013 Mar: A/F/S
Snapper Grouper Amendment 29 (Allocations, ORCS revisions?) | [17 empty] | Discuss | bar: Dec
Snapper Grouper Amendment 30 (VMS) | [15 empty] | P? | P? | A/F/S | bar: Dec; 2013 Mar
Dolphin/Wahoo Amendment 5 (Fmwk, ABC/ACL adj, Alloc) |  |  |  |  | Dec: AS; 2013 Jan: Ps; 2013 Mar: O |  |  | Ah |  | P | A/F/S
Golden Crab Amendment 6 (Catch Shares) | P | P | A/F/S |  | Jun: F/S; Sep: F/S; 2013 Mar: Discuss
Fishery Ecosystem Plan (Update #1) - start in 2014 | [23 empty] | As | Ps | Ps | O |  |  | Ah | NDC | P/N | A/F/S
Comprehensive Ecoystem-Based Amendment #3(2012), #4(2013) & #5(2014) - Bycatch | Ps | Ps | O |  | Jun: Ah; Jul: NDC; Aug: P/N; Sep: A/F/S; Dec: A/F/S; 2013 Mar: A/F/S | [8 empty] | As | Ps | Ps | O |  |  | Ah | NDC | P/N | A/F/S
Coral Amendment 8 (Coral HAPCs & Transit thru Oculina Bank HAPC) |  |  |  |  | Sep: F/S; Dec: F/S; 2013 Mar: A |  |  | Ah |  |  | A/F/S
Shrimp Closure Work (if required; done in 2011) |  |  | A | [23 empty] | A | bar: 2013 Mar
Shrimp Amendment 9 (Closure process & MSST) | Ps | Ps | O |  | Jun: Ah; Jul: NDC; Aug: P/N; Sep: A/F/S
Joint Mackerel Amendment 19 (Prohibit Bag Limit Sales & Permits) |  |  |  |  | Dec: Ah; 2013 Jan: P/N; 2013 Mar: A/F/S |  |  | Ah |  | P | A/F/S
Joint Mackerel Amendment 20 (Boundaries & Timing) |  |  |  |  | Dec: Ah; 2013 Jan: P/N; 2013 Mar: A/F/S |  |  | Ah |  | P | A/F/S
Joint Mackerel Framework (Size/Bag/Trip Limits) | [17 empty] | Ah |  | P | A/F/S | bar: Dec; 2013 Mar
Joint SA/GM Amendment (Commercial Logbooks) - timing determined after GMFMC 2/13 meeting | bar: Dec
Joint SA/GM Amendment (Headboat Reporting) - timing determined after GMFMC 2/13 meeting | bar: Dec
Joint Spiny Lobster Amendment 11 (NMFS lead; Protected Resources Issues) | P | P | F/S | bar: Dec
Joint GM/SA Dealer Amendment | Ps | Ps |  |  | Jun: Ah; Jul: NDC; Aug: P/N; Sep: A/F; Oct: S
Workshops with Fishermen - start in 2012 | bar: Dec
Calico Scallop FMP? (Separate FMP or Include in a Comprehensive FEP Am)
D = Plan development
AS = Approve for public scoping
Ps = Public scoping | bar: Dec
O = Develop options/review options paper | bar: Dec
Ah = Approve for public hearing | bar: Dec
P = Public hearing
IP = Informal public hearing
N = NMFS informal review
A = Council approve
F = Final Review
NDC = NMFS determination of completeness for DEIS Filing
S = Submit for Secretarial review
BLUE = DONE | bar: 2013 Mar

## Council Decisions March 2012
Objective=Finish CEBA-3 in 2012
Items Scoped for CEBA-3 | CEBA-3 | CEBA-4 | Framework | Drop
| (CY 2012) | (CY 2013) | (after 2013 assmt.)
1. Expand Coral HAPCs | 1. Expand Coral HAPCs
2. Prohibit Powerheads |  | 2. Prohibit Powerheads
3. MPAs & HAPCs for SpHind & Warsaw | 3. MPAs & HAPCs for SpHind & Warsaw
4. Snapper Ledge = MPA |  | 4. Snapper Ledge = MPA
5. Rec. tag program for deepwater sp. |  | 5. Rec. tag program for deepwater sp.
6. Hogfish |  |  | 6. Hogfish
7. Gray triggerfish |  |  | 7. Gray triggerfish
8. African pompano |  |  |  | 8. African pompano
9. Permits & Data reporting | 9. Permits & Data reporting
Distribution of Work
Ecosystem Committee | 1. Expand Coral HAPCs
Snapper Grouper Committee | 3. MPAs & HAPCs for SpHind & Warsaw
Data Collection Committee | 5. Rec. tag program for deepwater sp.
9. Permits & Data reporting
Golden Crab Committee | Golden Crab Amendment 6
Shrimp Committee | Shrimp Amendment 9
Items to Complete in 2012 - MARCH MEETING | Comments
1. CEBA-3 - FINISH IN DECEMBER? | Approve PH June; PH Aug.; Final Sept (Dec @ latest)
2. SG Reg Am 12 (Golden Tilefish) - DONE | to SOC by March 29, 2012 if approved @ March meeting
3. Comprehensive ACL/Allocation Amendment | develop alternatives
4. Golden Crab Am 6 (Catch Share) - RESOLVED SEPT? | preferreds @ March; final @ June
5. Joint Mack Am 19 (Permits & Sale) | Approve PH June; PH Aug.; Final Sept (Dec @ latest)
6. SG Am 18B (Golden Tilefish) - DONE | alternatives @ March, PH June; final approval June
7. Joint Dealer Amendment - DONE SEPTEMBER | Approve PH June; PH Aug.; Final Sept (must be implemented effective 1/1/13)
8. Joint Mack Am 20 (Boundaries & Transit) | Approve PH June; PH Aug.; Final Sept (Dec @ latest)
9. Shrimp Am 9 - DONE | Approve PH June; PH Aug.; Final Sept (Dec @ latest)
10. Analysis of Voluntary IFQ
9. Other Reg Amendments???? | April SSC review of MRIP so may have new OFLs & ABCs?????
Prepare very brief Regulatory Amendment/Categorical Exclusion for each FMP affected
Note: Assumes Snapper Grouper Am 20B is deferred until 2013 at least to see what happens with new, much reduced ACL.

## Council Decisions Sept 2012
Items to Complete in 2012/13 - SEPTEMBER MEETING | Comments

## Council Ranking 2012-13
| HIGH | MED | LOW | RANK | ORDER
SAFMC CY 2012/13 SCHEDULE
FMPS/AMENDMENTS/FRAMEWORKS
Snapper Grouper Regulatory Amendment 13 Adj ACLs MRFSS/MRIP Calibration | 13 |  |  | 39 | 1
Snapper Grouper Regulatory Amendment 14 Multiple Species | 5 | 5 | 4 | 29 | 5
Emergency Rule for Yellowtail Snapper | 12 | 1 |  | 38 | 2
Snapper Grouper Regulatory Amendment 15 Yellowtail Snapper, Gag Trigger & Red Snapper | 6 | 4 | 1 | 27 | 6
Snapper Grouper Amendment XX Yellowtail & Mutton (SAFMC Management) | 1 | 5 | 2 | 15 | 14
Snapper Grouper Regulatory Amendment 16 Golden Tilefish (2wk on & 2 off) | 4 | 6 | 2 | 26 | 7
Snapper Grouper Regulatory Amendment 17 MPAs Speckled Hind/Warsaw |  | 7 | 6 | 20 | 10
Emergency Rule to remove Gag triggering closure of all shallow water groupers | 9 | 2 | 1 | 32 | 3
Snapper Grouper Amendment 22 (Tag Program Golden Tilefish, Snowy & Wreckfish) |  | 4 | 9 | 17 | 12
Snapper Grouper Amendment 26 (Allocations, ORCS revisions?) | 3 | 6 | 3 | 24 | 9
Snapper Grouper Amendment 27 Blue runner
Dolphin/Wahoo Amendment X (Fmwk, ABC/ACL adj, Alloc) | 1 | 4 | 8 | 19 | 11
Golden Crab Amendment 6 (Catch Shares) | 0 | 3 | 10 | 16 | 13
Fishery Ecosystem Plan (Update #1) - start in 2014 | 1 | 3 | 8 | 17 | 12
Comprehensive Ecoystem-Based Amendment #3(2012), #4(2013) & #5(2014) | 1 | 5 | 4 | 17 | 12
Coral Amendment 7 (Coral HAPCs & Transit thru Oculina Bank HAPC)
Shrimp Closure Work (if required; done in 2011) | 1 |  |  | 3 | 16
Shrimp Amendment 9 (Closure process & MSST) | 1 |  |  | 3 | 16
Joint Mackerel Amendment 19 (Prohibit Bag Limit Sales & Permits) - timing | 4 | 9 | 0 | 30 | 4
Joint Mackerel Amendment 20 (Boundaries & Timing) - timing | 1 | 11 | 1 | 26 | 7
Joint Mackerel Framework (Size/Bag/Trip Limits) - timing | 0 | 12 | 1 | 25 | 8
Joint Spiny Lobster Amendment 11 (NMFS lead; Protected Resources Issues) |  |  | 1 | 1 | 17
Joint GM/SA Dealer Amendment | 6 | 4 | 1 | 27 | 6
Workshops with Fishermen - start in 2012 | 1 | 8 | 1 | 20 | 10
Calico Scallop FMP? (Separate FMP or Include in a Comprehensive FEP Am) |  |  | 11 | 11 | 15