## Overall Schedule
Council's |  | 2012 | [11 empty] | 2013 | 2013 | 2013 | 2013 | 2013 | 2013 | 2013 | 2013 | 2013 | 2013 | 2013 | 2013 | 2014
Priorities | SAFMC CY 2012-13 SCHEDULE | Jan | Feb | Mar | Ap | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Ap | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Ap | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
(as of March 2013) | FMPS/AMENDMENTS/FRAMEWORKS
Done | Snapper Grouper Regulatory Amendment 13 Adj ACLs MRFSS/MRIP Calibration |  |  |  |  | Dec: P/F/S
2 | Snapper Grouper Regulatory Amendment 14 Multiple Species | [17 empty] | Ah |  | P | A/F/S | bar: Sep; 2013 Mar
Done | Emergency Rule for Yellowtail Snapper | bar: Sep
Done | Snapper Grouper Regulatory Amendment 15 Yellowtail Snapper, Gag Trigger & Red Snapper |  |  |  |  | Dec: P/F; 2013 Jan: S
5 | SG Reg Am 16 Golden Tilefish (2wk on & 2 off) Remove BSB Pot Closure | [17 empty] | Ah |  |  | O |  |  | P/A | bar: 2013 Mar
8 | Snapper Grouper Regulatory Amendment 17 MPAs Speckled Hind/Warsaw | [20 empty] | O | bar: Dec; 2013 Mar
Done | Snapper Grouper Regulatory Amendment 18 (Vermilion & Red Porgy) |  |  |  |  | Dec: O; 2013 Mar: P/F/S
1 (Done) | Snapper Grouper Regulatory Amendment 19 Black Sea Bass | [16 empty] | P/F/S
Done | Generic Amendment: For-Hire Reporting in South Atlantic Only |  |  |  |  | Dec: A; 2013 Mar: P/F/S
10 | Snapper Grouper Amendment 22 (Tags to track catches of Red Snapper, Golden Tile, Snowy & Wreckfish) | [17 empty] | O |  |  | O | bar: Sep
Done | Snapper Grouper Amendment 27 Blue Runner/Yellowtail & Mutton Management |  |  |  |  | Dec: Ah; 2013 Jan: P; 2013 Mar: A/F/S
Done | Snapper Grouper Amendment 28 Red Snapper Framework |  |  |  |  | Dec: P/F; 2013 Jan: S
9 | Snapper Grouper Am 29 & D-W Am X (Allocations, ORCS revisions to Control Rule) 2014 | [17 empty] | Discuss | [5 empty] | As | Ps | Ps | O
7 | Snapper Grouper Amendment 30 (VMS) | [15 empty] | P |  | A/F/S | bar: Dec; 2013 Mar
6 (Done) | Dolphin/Wahoo Amendment 5 (Fmwk, ABC/ACL adj, Alloc) |  |  |  |  | Dec: AS; 2013 Jan: Ps; 2013 Mar: O |  |  | Ah |  | P | A/F/S
work halted | Golden Crab Amendment 6 (Catch Shares) | P | P |  |  | 2013 Mar: Discuss
13 | Fishery Ecosystem Plan (Update #1) - start in 2014 | [23 empty] | As | Ps | Ps | O |  |  | Ah | NDC | P/N | A/F/S
14 | Comprehensive Ecoystem-Based Amendment #3(2012), #4(2013) & #5(2014) - Bycatch | Ps | Ps | O |  | Jun: Ah; Jul: NDC; Aug: P/N; 2013 Mar: A/F/S | [8 empty] | As | Ps | Ps | O |  |  | Ah | NDC | P/N | A/F/S
12 (Done) | Coral Amendment 8 (Coral HAPCs & Transit thru Oculina Bank HAPC) | [17 empty] | Ah |  | P | A/F/S | bar: 2013 Mar
| Shrimp Closure Work (if required; done in 2011) |  |  | A | [23 empty] | A | bar: 2013 Mar
Done | Shrimp Amendment 9 (Closure process & MSST) | Ps | Ps | O |  | Jun: Ah; Jul: NDC; Aug: P/N; Sep: A/F/S
4 (Done) | Joint Mackerel Amendment 19(20A) (Prohibit Bag Limit Sales & Permits) | [17 empty] | Ah |  | P | A/F/S
9 | Joint Mackerel Amendment 20(20B) (Boundaries & Timing) | [17 empty] | Ah |  | P | A/F/S
11 | South Atlantic CMP Framework (Size/Bag/Trip Limits) | [17 empty] | Ah |  | P | A/F/S | bar: 2013 Mar
3 | Joint SA/GM Amendment (Commercial Logbooks) - on hold pending pilot project
Done | Gulf Regulatory Amendment (Headboat Reporting in Gulf of Mexico only) |  |  |  |  | 2013 Mar: P/F/S |  |  | A/F/S
| Joint Spiny Lobster Amendment 11 (NMFS lead; Protected Resources Issues) | P | P | F/S
| Generic Amendment to Re-Examine Sector Allocations (2014) | [23 empty] | As | Ps | Ps | O
Done | Joint GM/SA Dealer Amendment | Ps | Ps |  |  | Jun: Ah; Jul: NDC; Aug: P/N; Sep: A/F; Oct: S; 2013 Mar: P/F/S | [5 empty] | P/F/S
Workshops with Fishermen - start in 2012
Calico Scallop FMP? (Separate FMP or Include in a Comprehensive FEP Am)
Red = New Amendments added during December 2012 meeting
D = Plan development
AS = Approve for public scoping
Ps = Public scoping
O = Develop options/review options paper
Ah = Approve for public hearing
P = Public hearing
IP = Informal public hearing
N = NMFS informal review
A = Council approve
F = Final Review
NDC = NMFS determination of completeness for DEIS Filing
S = Submit for Secretarial review
BLUE = DONE

## Council Ranking 2012-13
| HIGH | MED | LOW | RANK | ORDER
SAFMC CY 2012/13 SCHEDULE
FMPS/AMENDMENTS/FRAMEWORKS
Snapper Grouper Regulatory Amendment 13 Adj ACLs MRFSS/MRIP Calibration | 13 |  |  | 39 | 1
Snapper Grouper Regulatory Amendment 14 Multiple Species | 5 | 5 | 4 | 29 | 5
Emergency Rule for Yellowtail Snapper | 12 | 1 |  | 38 | 2
Snapper Grouper Regulatory Amendment 15 Yellowtail Snapper, Gag Trigger & Red Snapper | 6 | 4 | 1 | 27 | 6
Snapper Grouper Amendment XX Yellowtail & Mutton (SAFMC Management) | 1 | 5 | 2 | 15 | 14
Snapper Grouper Regulatory Amendment 16 Golden Tilefish (2wk on & 2 off) | 4 | 6 | 2 | 26 | 7
Snapper Grouper Regulatory Amendment 17 MPAs Speckled Hind/Warsaw |  | 7 | 6 | 20 | 10
Emergency Rule to remove Gag triggering closure of all shallow water groupers | 9 | 2 | 1 | 32 | 3
Snapper Grouper Amendment 22 (Tag Program Golden Tilefish, Snowy & Wreckfish) |  | 4 | 9 | 17 | 12
Snapper Grouper Amendment 26 (Allocations, ORCS revisions?) | 3 | 6 | 3 | 24 | 9
Snapper Grouper Amendment 27 Blue runner
Dolphin/Wahoo Amendment X (Fmwk, ABC/ACL adj, Alloc) | 1 | 4 | 8 | 19 | 11
Golden Crab Amendment 6 (Catch Shares) | 0 | 3 | 10 | 16 | 13
Fishery Ecosystem Plan (Update #1) - start in 2014 | 1 | 3 | 8 | 17 | 12
Comprehensive Ecoystem-Based Amendment #3(2012), #4(2013) & #5(2014) | 1 | 5 | 4 | 17 | 12
Coral Amendment 7 (Coral HAPCs & Transit thru Oculina Bank HAPC)
Shrimp Closure Work (if required; done in 2011) | 1 |  |  | 3 | 16
Shrimp Amendment 9 (Closure process & MSST) | 1 |  |  | 3 | 16
Joint Mackerel Amendment 19 (Prohibit Bag Limit Sales & Permits) - timing | 4 | 9 | 0 | 30 | 4
Joint Mackerel Amendment 20 (Boundaries & Timing) - timing | 1 | 11 | 1 | 26 | 7
Joint Mackerel Framework (Size/Bag/Trip Limits) - timing | 0 | 12 | 1 | 25 | 8
Joint Spiny Lobster Amendment 11 (NMFS lead; Protected Resources Issues) |  |  | 1 | 1 | 17
Joint GM/SA Dealer Amendment | 6 | 4 | 1 | 27 | 6
Workshops with Fishermen - start in 2012 | 1 | 8 | 1 | 20 | 10
Calico Scallop FMP? (Separate FMP or Include in a Comprehensive FEP Am) |  |  | 11 | 11 | 15

## Ranking March 2013
| ORDER | HIGH | MED | LOW | RANK | ORDER
SAFMC CY 2012/13 SCHEDULE | (9/12) |  |  |  |  | (3/13)
FMPS/AMENDMENTS/FRAMEWORKS
Snapper Grouper Regulatory Amendment 13 Adj ACLs MRFSS/MRIP Calibration | 1
Snapper Grouper Regulatory Amendment 14 Multiple Species | 5
Emergency Rule for Yellowtail Snapper | 2
Snapper Grouper Regulatory Amendment 15 Yellowtail Snapper, Gag Trigger & Red Snapper | 6
Snapper Grouper Amendment XX Yellowtail & Mutton (SAFMC Management) | 14
Snapper Grouper Regulatory Amendment 16 Golden Tilefish (2wk on & 2 off) | 7
Snapper Grouper Regulatory Amendment 17 MPAs Speckled Hind/Warsaw | 10
Snapper Grouper Regulatory Amendment 18 Vermilion & Red Porgy
Emergency Rule to remove Gag triggering closure of all shallow water groupers | 3
Snapper Grouper Amendment 22 (Tag Program Golden Tilefish, Snowy & Wreckfish & Red snapper) | 12
Snapper Grouper Amendment 27 Blue runner, Nassau, bag & fmwk | 9
Snapper Grouper Amendment 28 Red Snapper Framework
Snapper Grouper Amendment 26 29 (Allocations, ORCS revisions?)
Dolphin/Wahoo Amendment X 5 (Fmwk, ABC/ACL adj, Alloc) | 11
Golden Crab Amendment 6 (Catch Shares) | 13
Fishery Ecosystem Plan (Update #1) - start in 2014 | 12
Comprehensive Ecoystem-Based Amendment #3(2012), #4(2013) & #5(2014) (Bycatch only) | 12
Generic SG, DW & CMP For-Hire Reporting (SA Only)
Generic Commercial Logbook Reporting
Snapper Grouper Amendment 30 (VMS)
Coral Amendment 7 8 (Coral HAPCs & Transit thru Oculina Bank HAPC)
Shrimp Closure Work (if required; done in 2011) | 16
Shrimp Amendment 9 (Closure process & MSST) | 16
Joint Mackerel Amendment 19 (Prohibit Bag Limit Sales & Permits) - timing | 4
Joint Mackerel Amendment 20 (Boundaries & Timing) - timing | 7
Joint Mackerel Framework (Size/Bag/Trip Limits) - timing | 8
Joint Spiny Lobster Amendment 11 (NMFS lead; Protected Resources Issues) | 17
Joint GM/SA Dealer Amendment | 6
Workshops with Fishermen - start in 2012 | 10
Calico Scallop FMP? (Separate FMP or Include in a Comprehensive FEP Am) | 15

## Ranking Dec 2013
| ORDER | HIGH (3) | MED (2) | LOW (1) | RANK
SAFMC CY 2014 SCHEDULE
FMPS/AMENDMENTS/FRAMEWORKS
Snapper Grouper Regulatory Amendment 16 (Remove BSB Pot Closure)
Snapper Grouper Regulatory Amendment 17 MPAs for Speckled Hind/Warsaw
Snapper Grouper Regulatory Amendment 20 Snowy Grouper & Mutton Snapper
Snapper Grouper Regulatory Amendment 21 (MSST Revisions & Blueline Tilefish ACL)
Snapper Grouper Amendment 13A (Oculina Experimental Closed Area 10 Year Evaluation)
Snapper Grouper Amendment 21 (Outcome of Visioning)
Snapper Grouper Amendment 22 (Recreational Tag Program to Track Harvest)
Snapper Grouper Amendment 29 (ORCS Revisions to Control Rule)
Snapper Grouper Amendment 31 (Blueline Tilefish Rebuilding Program)
System Management Plan for SG Amendment 14 MPAs
Dolphin/Wahoo Amendment 7 (Fillets from Bahamas)
Fishery Ecosystem Plan (Update #1)
Comprehensive Ecoystem-Based Amendment #3 (Bycatch only)
Coral Amendment 9 (Adjustment of CHAPC Boundary)
Shrimp Closure Work (if required; done in 2011)
Joint Mackerel Amendment 20B (Boundaries & Transit & Fishing Year)
Joint SA/GM Mackerel Framework (Spanish Mackerel)
Joint SA/GM Amendment 24 (Allocations)
Joint SA/GM Amendment 26 (Permit Split)
Joint SA/GM Charterboat Reporting Amendment
Joint SA/GM Generic Commercial Logbook Amendment (on hold pending Pilot Study)
Generic Allocation/Accountability Measure Amendment
Visioning Workshops with Fishermen
Calico Scallop FMP
Council Member Name:
Directions: For each amendment, indicate your priority (Hi, Med, Lo) with a check mark.