## 2025 - 2029 workplan
| Activity | Notes | Summer 2025 | Winter 2026 | Summer 2026 | Winter 2027 | Summer 2027 | Winter 2028 | Summer 2028 | x | Future to be decided at the meeting
Blueprint specifics | Website Transition | Work starting Dec 2023 | x | [6 empty] | x | Underway
Reuccuring Habitat AP ACTIVITIES | Communication strategy development | Work starting Jan 2023 | x | x | x | x | x | x | x | x | Finished
| Implement 2024 EFH Recommendations (food web working group) | Work Starting Jan 2025 must be completed by Dec 2029 | x | x | x | x | x | x | x
| Workplan update |  | x | x | x | x | x | x | x
| Annual report |  |  | x |  | x |  | x | x
| Citizen science updates |  |  | x |  | x |  | x | x
| EFH Consultations updates |  | x | x |  | x |  | x | x
Council and AP requests | Space program impact on habitat: reaction to FOIA? Next steps? | Need FOIA information | x
| Revise the Flow policy |  | x | x
| Beneficial Use Projects and EFH consult resources |  | x
| Spawning SMZ working group report | Chip Collier |  | x
| IRA overview including EFH project update | Lara Klibansky | x | x | x | x | x | x | x
| Integrated Ecosystem Assessment - goals and objectives |  | x | x
| CEFI Overview |  | x
Potential habitat impact projects/Offshore energy development - requested every winter | CVOW update fon habitat created by wind farms and fish death | BOEM | x
| Subsea transmission cables | AECOM | x
EFH 5 Year Review | Identify Higher abundance locations and (improving EFH tier structure) |  | x | x | x | x | x | x | x
| additional life stage information for EFH clarification in each FMP |  | x | x | x | x | x | x | x
ITEMS PER MEETING: |  |  | 15 | 12 | 6 | 9 | 6 | 9 | 9
| Other long term goals |  |  | Other short term goals
| Goal | year |  | Goals |  |  |  |  | meeting
| Habitat Production relationships and map using Ecopath/Ecosim |  |  | EFH assessment on wind farms |  |  |  |  | Winter 2026
Modeling species habitat use using SEFIS and AI
Compiling habitat data with the Climate vulnerability assessment
Requesting a Habitat assessment from NMFS
Expand Deepwater CHAPCs
Research and monitoring goals
|  |  |  | Goals |  |  |  |  | Meeting
HCD request for information: Review grain size compatibility and ecological and economic benefits of using compatible sand to the USACOE and CZM agencies.
Flow working group: NOAA Fisheries in cooperation with the Council, develop a list of regionally specific requirements or Best Management Practices for flow-altering projects that can potentially impact EFH or other resources and support scheduling projects to not coincide with spawning migrations or early development of sensitive species.
Food Web working Group: Characterize life history of primary prey for Council managed species, including snapper grouper, king and Spanish mackerel, cobia, dolphin and wahoo.