## 2025 - 2029 workplan
| Activity | Notes | Winter 2026 | Summer 2026 | Winter 2027 | Summer 2027 | Winter 2028 | Summer 2028 | Winter 2028 | x | Future to be decided at the meeting
Reuccuring Habitat AP ACTIVITIES | Communication strategy development | Currently developing FAQs | x | x | x | x | x | x | x | x | Underway
| Workplan update |  | x | x | x | x | x | x | x | x | Finished
| Annual report |  | x |  | x |  | x | x | x
| Citizen science updates |  |  | x |  | x |  | x
| EFH Consultations updates | Anne Deaton | x |  | x |  | x | x | x
Council and AP requests | Space program impact on habitat |  |  | X
| Revise the Flow policy |  | x | x
| Spawning SMZ working group report - could be habitat seminar | Chip Collier | x
| Resiliant Fisheries | Lara Klibansky (as needed) | x | x | x | x | x | x | x
| Integrated Ecosystem Assessment - goals and objectives | Requesting presentation from Gulf and Mid |  | x
Projects with Potentially high habitat impact | Offshore energy updates | BOEM |  | X
| Subsea transmission cables - could be habitat seminar | Sea Risk Solution |  | x
EFH 5 Year Review (complete December 2029) | Identify Higher abundance locations and (improving EFH tier structure) | Work Starting fall 2025 |  | x | x | x | x | x | x
| Implement 2024 EFH Recommendations (food web working group) | Work Starting Jan 2025 | x | x | x | x | x | x | x
| additional life stage information for EFH clarification in each FMP | Swork Starting Fall 2025 |  | x | x | x | x | x | x
ITEMS PER MEETING: |  |  | 8 | 12 | 9 | 7 | 8 | 9
| Other long term goals |  |  | Other short term goals
| Goal | year |  | Goals |  |  |  |  | meeting
| Habitat Production relationships and map using Ecopath/Ecosim |  |  | EFH assessment on wind farms - HEAP discussion on how to handle decommisioned windfarms/art reef/efh |  |  |  |  | Winter 2027
| Modeling species habitat use using SEFIS and AI |  |  | Manomet |  |  |  |  | Summer 2026
| Compiling habitat data with the Climate vulnerability assessment |  |  | Port Everglades coral project - Habitat Seminar |  |  |  |  | Spring 2026
| Requesting a Habitat assessment from NMFS |  |  | Midatlantic IRA EFH Project |  |  |  |  | Summer 2026
| Expand Deepwater CHAPCs | 2027-03-01
Deepsea mining - university of hawaii presentation? Brendan Runde contact
Research and monitoring goals
|  |  |  | Goals |  |  |  |  | Meeting
Flow working group: NOAA Fisheries in cooperation with the Council, develop a list of regionally specific requirements or Best Management Practices for flow-altering projects that can potentially impact EFH or other resources and support scheduling projects to not coincide with spawning migrations or early development of sensitive species.
Food Web working Group: Characterize life history of primary prey for Council managed species, including snapper grouper, king and Spanish mackerel, cobia, dolphin and wahoo.