## 2025 - 2029 workplan
| Activity | Notes | Summer 2026 | Winter 2027 | Summer 2027 | Winter 2028 | Summer 2028 | Winter 2028 |  | x | Future to be decided at the meeting
Reoccuring Habitat AP ACTIVITIES | Communication strategy development | Currently developing FAQs | x | x | x | x | x | x |  | x | Underway
| Workplan update |  | x | x | x | x | x | x |  | x | Finished
| Annual report |  |  | x |  | x |  | x
| Citizen science updates |  |  | x |  | x |  | x
| EFH Consultations updates | Anne Deaton |  | x |  | x |  | x
| AP Member and vice chair/chair appointments |  | x
Council and AP requests | Space program impact on habitat (include research and monitering recs) |  | X
| Revise the Flow policy |  | x
| Deepsea mining - university of hawaii presentation | Unavailable for summer 2026 |  | x
| Resiliant Fisheries | Lara Klibansky (as needed) | x | x | x | x | x | x
| Expand Deepwater CHAPCs |  |  | x
| Integrated Ecosystem Assessment - goals and objectives | Requesting presentation from Gulf and Mid | x
Projects with Potentially high habitat impact | Offshore energy and development updates | BOEM | X
| Manomet - thin layer placement and beneficial use for corp identifying locations |  | x
| Midatlantic IRA EFH Project |  | x
| Mapping off of Florida | Brendan contact |  | X
| Subsea transmission cables - could be habitat seminar | Sea Risk Solution | Habitat Informational webinar late july
EFH 5 Year Review (complete December 2029) | Identify Higher abundance locations and (improving EFH tier structure) | Work Starting fall 2026 |  | x | x | x | x | x
| Implement 2024 EFH Recommendations (food web working group) | Work Starting Jan 2025 | x | x | x | x | x | x
| additional life stage information for EFH clarification in each FMP | Work Starting Fall 2025 | x | x | x | x | x | x
ITEMS PER MEETING: |  |  | 13 | 10 | 6 | 9 | 6 | 9
| Other long term goals |  |  | Other short term goals
| Goal | year |  | Goals |  |  |  |  | meeting
| Habitat Production relationships and map using Ecopath/Ecosim |  |  | EFH assessment on wind farms - HEAP discussion on how to handle decommisioned windfarms/art reef/efh |  |  |  |  | Winter 2027
Modeling species habitat use using SEFIS and AI
| Compiling habitat data with the Climate vulnerability assessment |  |  | Port Everglades coral project - Habitat Seminar |  |  |  |  | Spring 2026
Requesting a Habitat assessment from NMFS
Research and monitoring goals
|  |  |  | Goals |  |  |  |  | Meeting
Flow working group: NOAA Fisheries in cooperation with the Council, develop a list of regionally specific requirements or Best Management Practices for flow-altering projects that can potentially impact EFH or other resources and support scheduling projects to not coincide with spawning migrations or early development of sensitive species.
Food Web working Group: Characterize life history of primary prey for Council managed species, including snapper grouper, king and Spanish mackerel, cobia, dolphin and wahoo.