## 2025 - 2029 workplan
| Activity | Notes | Summer 2025 | Winter 2026 | Summer 2026 | Winter 2027 | Summer 2027 | Winter 2028
Blueprint specifics | Website Transition | Work starting Dec 2023 | x | [5 empty] | x | Underway
Reuccuring Habitat AP ACTIVITIES | Communication strategy development | Work starting Jan 2023 | x | x | x | x | x | x | x | Finish
| Implement 2024 EFH Recommendations (food web working group) | Work Starting Jan 2025 must be completed by Dec 2030 | x | x | x | x | x | x
| Workplan update |  | x | x | x | x | x | x
| Annual report | May be done via email for 2024 |  | x |  | x |  | x
| Citizen science updates |  |  | x |  | x |  | x
| EFH Consultations |  |  | x |  | x |  | x
Council and AP requests | Space program impact on habitat: reaction to FOIA? Next steps? | Need FOIA information | x
| Revise the Flow policy |  | x
| Beneficial Use Projects and EFH consult resources | Molly Bost | x
| Spawning SMZ working group report |  | x
| IRA overview including EFH project update | Lara Klibansky | x
| CEFI Overview |  | x
Major habitat impact project/Offshore energy development - | CVOW update from dominion on habitat created by wind farms and fish death | BOEM | x
| SeaOptic Fiber Cables | Benjamin Theaupaut and Stacie Crowe | x
Other | Identify Higher abundance locations and additional life stage information for EFH clarification in each FMP (improving EFH tier structure) |  | x | x | x | x | x | x
ITEMS PER MEETING: |  |  | 13 | 7 | 4 | 7 | 4 | 7
| Other long term goals |  |  | Other short term goals
| Goal | year |  | Goals |  |  |  |  | meeting
| EFH Review | 2029/2030 |  | EFH assessment on wind farms |  |  |  |  | Winter 2026
Habitat Production relationships and map using Ecopath/Ecosim
Modeling species habitat use using SEFIS and AI
Compiling habitat data with the Climate vulnerability assessment
Requesting a Habitat assessment from NMFS
Integrated Ecosystem assessment - need a request from the council