## Slide 1: Oct 2017 SSC SEDAR Updates
Scamp Research Track (GoM & SA)
SEDAR 48 Southeast Black Grouper
SEDAR 58 Atlantic Cobia
SEDAR 59 South Atlantic Greater Amberjack
SEDAR 60: South Atlantic Red Porgy
SEDAR 55: South Atlantic Vermilion Snapper
SEDAR 56 South Atlantic Black Seabass

## Slide 2: Scamp Research Track
SEDAR Steering Committee support GoM & SA Scamp as Research Track pilot
SEFSC will develop draft work plan to be reviewed by Plan Review Team
Action Item:
  Identify two SSC representatives for Plan Review Team

## Slide 3: SEDAR 48: Southeast Black Grouper
Variety of issues identified during Data Stage (March 2017); assessment halted
DW report available on SEDAR website
http://sedarweb.org/sedar-48

## Slide 4: SEDAR 58: Atlantic Cobia
Benchmark assessment with Stock ID evaluation prior to Data Workshop
Multi-step Stock ID process
Organizing Committee developed draft ToRs and schedule; SEDAR Steering Committee will approve
  SAFMC SSC & ASMFC feedback on ToRs via email
  GMFMC SSC will provide feedback at Oct 31 meeting

## Slide 5: SEDAR 58: Atlantic Cobia
Event | Dates & Method | Action Items
Cobia Stock ID Workshop | Apr 10-12, 2018 In-person | 1-2 SSC Panel reps: Potential Workshop Chair: Additional experts?
Cobia Stock ID Review Workshop | June 5-7, 2018 In-person | 1 SSC Reviewer: Potential Review Workshop Chair: Additional experts?
Cobia Stock ID Cooperator Technical Review | July/Aug 2018 Webinar | 2 SSC Reviewers:

## Slide 6: SEDAR 59 & SEDAR 60
Project | Dates & Method | Action Items
SEDAR 59 SA Greater Amberjack | Mar-Dec 2018 Series of 5 webinars | ToR & Schedule review 2-3 SSC Panel reps:
SEDAR 60 SA Red Porgy | June 2018 - Mar 2019 Series of 5 webinars | ToR & Schedule review 2-3 SSC Panel reps:

## Slide 7: SEDAR 55: SA Vermilion Snapper
Timing update
  Delay in data submissions due to Hurricane Irma
  SEDAR 55 Panel recommends extending assessment ~ 1 month
  Tentative new completion date: April 16, 2018
Potential issues to be considered not in ToR
  Method to estimate recreational historic catch
  Use of all ages
  Use of batch by size/age in reproductive analyses
  New method to combine SERFS trap/video index

## Slide 8: SEDAR 56: SA Black Seabass
Timing update
  Request to delay 6 week due to late data submissions
  SEDAR Steering Committee approved delay; delay longer than 6 weeks so could advance terminal year (2016)
  New completion date ~April 6, 2018
Potential issues to be considered not in ToR
  New discard mortality study