## Sheet1
Council's |  | 2015 | [11 empty] | 2016
Priorities | SAFMC CY 2015 SCHEDULE | Jan | Feb | Mar | Ap | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept
(March 2015) | FMPS/AMENDMENTS/FRAMEWORKS
1 | Visioning Public Input |  |  | D |  | Jun: Ah/P; Jul: P; Aug: P; Sep: D; Oct: A; Dec: Ah? A
1 | Snapper Grouper Amendment 37 (Hogfish) |  |  | O |  | Jun: D/As; Jul: Ps; Aug: Ps; Sep: Ah; Nov: P; Dec: P/A
| Proposed Revised Timeline: (Statutory Deadline; regulations need to be effective 1/1/17) |  |  | O |  | Jun: D/As; Aug: Ps; Sep: D; Dec: Ah; 2016 Jan: P; 2016 Feb: P; 2016 Mar: A/F/S
| Snapper Grouper Amendment 41 (Mutton Snapper) |  |  |  |  | Sep: As; Dec: Ah?
| Proposed Revised Timeline: (Responding to Assessment results; no specific timing) |  |  |  |  | Dec: As; 2016 Jan: Ps; 2016 Feb: Ps; 2016 Mar: Ah?; 2016 June: Ah?
2 | Snapper Grouper Amendment 36 (Spawning SMZs) |  |  | Ah | P | May: P; Jun: Ah; Aug: P; Sep: P/A; Dec: F; 2016 Jan: S
3 | System Management Plan for SG Amendment 14 MPAs |  |  | D |  | Jun: D; Jul: IP; Aug: IP; Sep: P/A; Dec: F
4 | Joint SA/GM Charterboat Reporting Amendment (Gulf Lead) (COUNTS AS 2 AMENDMENTS) |  |  | O |  | Jun: O; Sep: Ah; Nov: P; Dec: A; 2016 Mar: F; 2016 May: S
| Separate SA For-Hire Reporting Amendment |  |  |  |  | Sep: O; Dec: Ah; 2016 Jan: P; 2016 Feb: P; 2016 Mar: A; 2016 June: F; 2016 July: S
5 | Snapper Grouper Regulatory Amendment 16 (BSB Pot Closure) |  |  | O |  | Jun: Ah; Aug: P; Sep: A; Dec: F/S
6 | Fishery Ecosystem Plan II |  |  | D | bar: Jun; Sep; Dec
6 | Joint SA/GM CMP Am 26 (King Mackerel ACLs/Boundary/MMSs; Gulf Lead) (2 AMENDMENTS) | Ps |  | O |  | Jun: O; Sep: O; Dec: Ah; 2016 Jan: P; 2016 Feb: P; 2016 Mar: A/F; 2016 Apr: S?; 2016 May: S?
7 | Joint SA/GM Amendment (Issues from South Florida Committee) (Gulf Lead) (2 AMENDMENTS) |  |  | O |  | Jun: O; Sep: D; Dec: Ah??
| Joint SA/GM SG/Reeffish Am (Yellowtail ABC/ACL & AM; SA Lead) (pulled from S.FL Amendment) |  |  |  |  | Sep: D; Dec: Ah; 2016 Jan: P; 2016 Feb: P; 2016 Mar: A/F; 2016 Apr: S
9 (done) | Snapper Grouper Amendment 35 (Removing species & Golden Tilefish Endorsement) |  |  | P/A |  | Jun: F/S
| Snapper Grouper Regulatory Am 23 (BSB Bag, Jacks Trip limit & GT FY Start) |  |  |  |  | Aug: Ps; Sep: D; Dec: Ah
Possible New Items for 2016: (these would delay SG RA 23 until 2016) | bar: May to Dec; 2016 Mar; 2016 June; 2016 Sept
| Blueline Tilefish, Yellowtail Fishing Year, & BSB Bag???? Framework |  |  |  |  | Sep: O/Ah; Nov: P; Dec: A; 2016 Mar: F/S
| Dolphin Framework (commercial trip limit) |  |  |  |  | Sep: O/Ah; Nov: P; Dec: A/F/S
Red Snapper Framework (Adaptive Management for 2016) | bar: 2016 Mar
Items for 2016: | bar: May to Dec
(split from Am37) | Snapper Grouper Regulatory Amendment 24 (Multiple Species) |  |  |  |  | Jun: As; Jul: Ps; Aug: Ps; Sep: Ah; Nov: P; Dec: P/A
10 | Snapper Grouper Regulatory Amendment 23 (Golden Tilefish) |  |  | O |  | Jun: D/As; Jul: Ps; Aug: Ps; Sep: Ah; Nov: P; Dec: P/A
13 | Comprehensive Ecosystem-Based Amendment #3 (Bycatch) |  |  | D | bar: Jun; Sep; Dec
8 | Joint SA/GM Generic Commercail Logbook Amendment
9 | Snapper Grouper Amendment 42 43 (Update Wreckfish ITQ)
11 | Coral/Shrimp Golden Crab Amendment XX (Modify GC & Establish RS Fishing Areas)
12 | Shrimp Closure Work (states can request directly to NMFS)
13 | Joint SA/GM Amendment 24 (Atlantic Spanish Mackerel Allocations)
13 | Calico Scallop FMP
Moved fm 2015 | Snapper Grouper Amendment XX (Short-term Visioning)
Moved fm 2015 | Snapper Grouper Amendment XX (Allocations from Visioning)
4 | Snapper Grouper Amendment 38 (Blueline Tilefish)(Defer to 2016/17) |  |  | O | bar: Jun; Sep; Dec; 2016 Mar; 2016 June; 2016 Sept
New | Dolphin Amendment (approx. 7 actions = major amendment)
Snapper Grouper Amendment - Red Snapper (assessment results & changes to management)
D = Plan development; AS = Approve for public scoping; Ps = Public Scoping
O = Develop options/review options paper; Ah = Approve for public hearing
P = Public hearing; IP = Informal public hearing; N = NMFS informal review
A = Council approve; F = Final Review; NDC = NMFS determination of complet for DEIS filing
S = Submit for Secretarial review