## Draft 2016-17
APPROACH FOR COMMITTEE/COUNCIL CONSIDERATION AT THE DECEMBER 2015 MEETING:
1 | Visioning input from Monday's session for executive committee to consider.
2 | Species committees provide input during committee meetings for executive committee to consider.
3 | Executive/Finance Committee - review Visioning & Species Committee input and develop recommendation for consideration during full Council meeting.
4 | Council determines final staff 2016/17 amendment slots during full Council meeting on Friday, December 11, 2015.
Note: This approach replaces the previous priority ranking used by the Council.
DRAFT SAFMC STAFF AMENDMENT SLOTS FOR 2016/17:
|  | Brian |  | Kari |  | Myra |  | Chip |  | Gregg/? |  | Roger
Year | Quarter | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
2016 | 1 | Allocation | Econ analysis | CMP Am 26 | Social analysis | SG Am 37 | SG Am 41 |  | SG AM 43 | SG Am 36 | For-Hire Am | FEP II | FEP II & EFH/Ecosystem
| 2 | Allocation | Econ analysis | Cobia Fmwk | Social analysis | SG Am 37 | SG Am 41 | CEBA 3 | SG Am 43 |  | For-Hire Am | FEP II | FEP II & EFH/Ecosystem
| 3 | Allocation | Econ analysis | Cobia Fmwk | Social analysis | Fisheries Seasonality/Retention | SG Am 41 | CEBA 3 | SG Am 43 | G.Tile/Gray Trigger |  | FEP II | FEP II & EFH/Ecosystem
| 4 | Allocation | Econ analysis | Cobia Fmwk | Social analysis | Fisheries Seasonality/Retention | SG Am 41 | CEBA 3 | SG Am 43 |  |  | FEP II | FEP II & EFH/Ecosystem
2017 | 1 | 1: D/W Am 10; 2: Econ analysis; 4: Social analysis; 5: Fisheries Seasonality/Retention; 7: CEBA 3; 11: FEP II; 12: EFH/Ecosystem
| 2 | 1: D/W Am 10; 2: Econ analysis; 4: Social analysis; 5: Fisheries Seasonality/Retention; 7: Coral/Shrimp; 11: FEP II; 12: EFH/Ecosystem
| 3 | 1: D/W Am 10; 2: Econ analysis; 4: Social analysis; 7: Coral/Shrimp; 12: EFH/Ecosystem
| 4 | 1: D/W Am 10; 2: Econ analysis; 4: Social analysis; 7: Coral/Shrimp; 12: EFH/Ecosystem
2018 | 1 | 7: Coral/Shrimp
2
Notes: | 1. Allocation Amendment would look at temporary allocation shifts (Yellowtail & Dolphin; others???)
2. Golden tile H&L fishing year start; red porgy split season; jacks trip limit; shallow water spawning season closure
Com Logbook Am
Notes: | 1. Two amendment leads or 1 lead plus the social/economic analyses on non-lead amendments is a full load for each staff person. | 9: Com Logbook Am
|  | Need to build in some time to address new methods for analyzing impacts and for special topics that may surface. | [7 empty] | Com Logbook Am
| 2. The Council could be addressing up to 10 amendments at each meeting; this is more than a full load for the Council. | 9: Com Logbook Am
3. Items in bold are carry-over from 2015.
|  | Amendment = 4 quarters |  | Reg Am = | 3 quarters
4. Draft items added in plain text are either non-snapper grouper items or items that were ranked high by the Council in 2015 but not completed.
5. SG Reg Am 23 - jacks trip limit & golden tilefish fishing year
6. SG Reg Am 24 - spawning season closure for shallow water groupers, red grouper size limit, restructure jacks complex, almaco trip limit, split red porgy season & remove deepwater size limits.
Consider combining RA 23/RA 24 and adding assessment-related actions for golden tilefish & gray triggerfish
7. New assessment results for golden tilefish, gray trigger & red snapper @ June 2016 Council meeting; add golden tile & gray trigger to RA 24?; red snapper in Am 43.
SG Am 43 - address red snapper only actions from assessment; ok to remove current framework for opening, closures and add new items in one amendment.
8. SG Am 38 (Blueline tilefish) - preliminary stock ID results @ December 2015 Council meeting; timing????
9. Spiny lobster - may need an amendment to address catch > ACT?
10. Coral/Shrimp - looking at allowable fishing areas for rock shrimp & modifying the areas for golden crab.
11. New assessment results for blueline tile & red grouper @ March or June 2017 Council meeting; will require Reg Am to make these changes.
12. Updating the Wreckfish ITQ - not shown above.
13. Allocations & Short-term Visioning moved from 2015 and not shown above.