## Sheet1
Amendment | Topics | SERO Staff Lead | Council Staff Lead | IPT Tier | Begin Dev | Scoping | Actions/Alts | Public Hearing | Select Prefs | Approval | Notes
SG A38 | Blueline Tilefish N of Hatteras | Mary | Roger | II | 2015-03-01 |  |  | Sep/Dec-19 |  | Sep/Dec-19
SG A44 | YT Snapper long term | Nikhil | John H | V | 2016-06-01 | 2016-08-01 | 2016-09-01 | Jan/Feb-17 |  |  | Focus shifted to RA32 Mar-18
SG A46 | Rec Permit & Reporting | Rick/Frank | Chip | V | 2017-12-01
SG RA29 | Best Practices & Powerheads | Frank | Christina | II | 2018-03-01 | 2018-08-01 | 2018-09-01 | Spring-19 | 2019-03-01 | 2019-09-01
SG RA30 | Red Grouper Rebuilding | Mary | John H | I | 2018-03-01 |  | 2018-06-01 | 2018-09-01 | 2018-09-01 | 2019-06-01
| Wreckfish ITQ review | Nikhil | Brian | II | 2017-06-01 |  |  |  |  | 2019-09-19 | Tier score based on analysis revisions and completion of section writing that is needed. Not an Amendment, but a required review of the catch share program
Deep H2O Species Allocation
SG RA 33 | Red snapper seasons | Frank | Myra | III | 2019-03-01 |  | 2019-06-19 | 2019-09-19 | 2019-09-19 | 2019-09-19
SG RA 34 | NC & SC SMZs | ? | Myra |  | 2019-03-01
C 10/S 11/GC 10 | GC Areas/Oculina Ext/transit | Karla | Chip | V | 2018-03-01 | [5 empty] | Coral 10/Shrimp 11/Golden Crab 10
CMP 24 | Atlantic SM allocations | Karla | Christina | V | 2013-09-01 | 2014-01-01 |  |  |  |  | *Inactive*
CMP FW 8 | King mack trip limits S2 | Karla | Christina |  | 2019-03-01
DW A10 | Dolphin and Wahoo Management Measures | Nikhil | John H | V | 2016-06-01 | 2018-08-01 |  |  |  |  | Suspended until Dec 2018. Multiple new actions added. Likley needs to go out to scoping again.
| Bullet & Frigate Mack in DW FMP Scoping |  | John H |  |  | 2019-05-01 |  |  |  |  | Subject sent to scoping. No amendment assigned.
SG 45/GC 11/Sa 4/C 11 | ABC Control Rule | Nikhil | John C | IV | 2016-12-01 | 2019-01-19 |  |  |  |  | SG A45/GC A11/S A4/C A11
SG Reg 31/DW Reg 2 | Recreational AMs | Rick/Frank | Brian | III | 2017-12-01 | 2019-01-19 |  |  |  |  | SG RA31/DW RA2 - need to begin work on the amendment and have IPT meet
| Com Electronic Logbooks | Karla | John C | V | 2012-12-01
| Bycatch Reporting | Frank | Chip | V | 2014-09-01 | [5 empty] | Suspended until NMFS publishes Standard Bycatch Reporting Methodology (SBRM)
| Allocation Trigger Plan | ??? | Brian | I | 2018-12-18 | [5 empty] | Needs to begin in Dec 2018 - Need to have allocation review triggers plan by August 2019.
| Marine Aquaculture Plan | ??? | Roger | V | 2018-06-01 | [5 empty] | Need to determine the impact of the latest court ruling as to whether the Council can develop a Marine Aquaculture Plan
Council to work on in June 2019 |  |  |  | Abbreviation Explanations
SG RA29 | Best Practices & Powerheads |  |  | SG = Snapper Grouper
| Wreckfish ITQ review |  |  | A = Amendment
SG A38 | Blueline Tilefish N of Hatteras |  |  | RA = Regulatory Amendment
DW A10 | Dolphin and Wahoo Management Measures |  |  | AF = Abbreviated Framework
| Allocation Trigger Plan |  |  | C = Coral
SG RA30 | Red Grouper Rebuilding |  |  | CMP = Coastal Migratory Pelagics = King Mackerel, Spanish Mackerel, and Cobia
| KM 2nd Season Trip Limits |  |  | DW = Dolphin Wahoo
| Jacks Removal from SG OP |  |  | SL = Spiny Lobster
CMP 24 | Spanish Mackerel Allocations |  |  | Black bars indicate where not required
Bullet & Frigate Mack in DW FMP Scoping
Allocation Presentation
SSC Update on MRIP
SG RA 33 | Red snapper seasons
Tentative for September 2019 |  |  |  | Tentative for December 2019
SG RA29 | Best Practices & Powerheads
Wreckfish ITQ review
C 10/S 11/GC 10 | GC Areas/Oculina Ext/transit
SG A38 | Blueline Tilefish N of Hatteras
SG 45/GC 11/Sa 4/C 11 | ABC Control Rule
SG Reg 31/DW Reg 2 | Recreational AMs
SG 46 | Rec Permits & Reporting
Com Electronic Logbooks
SG Reg 34 | SMZ Amendment
Allocation Discussion
SG Reg 33 | Red snapper seasons
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This would adjsut fishing levels for the entire SA, including the portion north of Hatteras. Uness the Council wants to change management measures, this could be an AF and could technically be approved in September.

## Sheet2
Amendment | Topics | IPT Tier | Council Score | September | December
SG RA30 | Red Grouper Rebuilding | II
SG RA29 | Best Practices & Powerheads | III |  | X
DW A10 | Dolphin ACL sharing, OY, etc. | V
SG A46 | Rec Permit & Reporting | V |  | X
SG Reg 31/DW Reg 2 | Recreational AMs | III |  | X
SG A38 | Blueline Tilefish N of Hatteras | V
SG A44 | YT Snapper long term | V
| Allocation Trigger Plan | I
SG 45/GC 11/Sa 4/C 11 | ABC Control Rule | IV |  | X
Options paper - KM Trip Limits
| Com Electronic Logbooks | V |  | X
| Wreckfish ITQ review | II |  | X
CMP 24 | Atlantic SM allocations | V
C 10/S 11/GC 10 | GC Areas/Oculina Ext/transit | V |  | X
| Bycatch Reporting | V |  | Update
| Marine Aquaculture Plan | V
| SMZ Amendment |  |  | X
Bullet & Frigate Mackerel Scoping
Options for Jacks Paper
Allocation Presentation
| Allocation Discussion 4 hrs |  |  | X
Updatt from SSC on MRIP