## Sheet1
Amendment | Topics | Staff Lead | Begin Dev | Scoping | Actions/Alts | Public Hearing | Select Prefs | Approval | Notes
SG A38 | BLT N of Hatteras | Roger | 2015-03-01
SG A42 | Turtle release/SG Framework | Christina | 2018-03-01 | 2018-04-18 | 2018-06-18 | 2018-09-18 | 2018-09-18 | 2018-09-18
SG A44 | YT Snapper long term | John H | 2016-06-01 | 2016-08-01 | 2016-09-01 | Jan/Feb-17 |  |  | Focus shifted to RA32 Mar-18
SG A46 | Rec Permit & Reporting | Chip | 2017-12-01
SG A47 | SG for-hire permit modif. | John H | 2016-06-01 | Aug/Oct-18
SG AF2 | VS & BSB ACLs | Brian | 2018-06-01 |  | 2018-06-01 | 2018-09-01 | 2018-09-01 | 2018-09-01
SG RA26 | Rec Visioning | Myra | 2016-09-01 | Jan/Feb-17 | 2017-06-01 | 2018-05-01 | 2018-06-01 | 2018-12-01
SG RA27 | Com Visioning | Myra | 2016-09-02 | Jan/Feb-17 | 2017-06-02 | 2018-05-01 | 2018-06-01 | 2018-09-01
SG RA29 | Best Practices & Powerheads | Christina | 2018-03-01 | 2018-08-01 | 2018-09-01 | Jan/Feb-19 |  | 2019-03-01
SG RA30 | Reg Grouper Rebuilding | John H | 2018-03-01 |  | 2018-06-01 | 2018-09-01 | 2018-09-01 | 2018-12-01
SG RA32 | Yellowtail AMs | Myra | 2018-03-01 | 2018-08-01 | 2018-09-01 |  |  | 2018-12-01
| Wreckfish ITQ review | Brian | 2017-06-01
C A10 | GC Areas/Oculina Ext/transit | Chip | 2018-03-01 | [5 empty] | Coral 10/Shrimp 11/Golden Crab 10
CMP FA6 | KM Trip Limits | Christina |  | 2017-03-01 | 2018-06-01 | 2018-06-01 | 2018-09-01 | 2018-09-01
SL A13 | Spiny mgt w/FL & gear mod. | Christina | 2017-06-01 | 2018-01-01 | 2018-06-01 | 2018-09-01 | 2018-06-01 | 2018-09-01
| ABC Control Rule | John C | 2017-09-01 | [5 empty] | SG A45/GC A11/S A4/C A11
| Recreational AMs | Brian | 2017-12-01 | [5 empty] | SG RA31/DW RA2
| Com Electronic Reporting | John C | 2012-12-01 | [5 empty] | *Inactive*
CMP 24 | Atlantic SM allocations | Christina | 2013-09-01 | 2014-01-01 |  |  |  |  | *Inactive*
DW A10 | Dolphin ACL sharing, OY, etc. | John H | 2016-06-01 | 2018-08-01 |  |  |  |  | Suspended until new MRIP estimates are available
| Bycatch Reporting | Chip | 2014-09-01 | [5 empty] | Suspended until NMFS publishes Standard Bycatch Reporting Methodology (SBRM)
| Marine Aquaculture Plan | Roger | 2018-06-01
Council to work on in September 2018 |  |  | Abbreviation Explanations
SG RA27 | Com Visioning |  | SG = Snapper Grouper
SL A13 | Spiny mgt w/FL & gear mod. |  | A = Amendment
CMP FA6 | KM Trip Limits |  | RA = Regulatory Amendment
SG RA32 | Yellowtail AMs |  | AF = Abbreviated Framework
SG RA26 | Rec Visioning |  | C = Coral
SG RA30 | Reg Grouper Rebuilding |  | CMP = Coastal Migratory Pelagics = King Mackerel, Spanish Mackerel, and Cobia
SG AF2 | VS & BSB ACLs |  | DW = Dolphin Wahoo
SG RA29 | Best Practices & Powerheads |  | SL = Spiny Lobster
SG A47 | SG for-hire permit modif. |  | Black bars indicate where not required