## Draft 2016-19
SAFMC PRIORITIES FOR 2016 - 2019:
|  | John H. |  | Kari/Christina |  | Myra |  | Chip |  | Brian |  | John C. |  | Roger
Year | Quarter | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
2016 | 1 |  | Econ analysis | CMP Am 26 | Social analysis | SG Am 37 | SG Am 41 |  | SG AM 43 | SG Am 36 |  | For-Hire Am | SEDAR/SSC | FEP II | FEP II & EFH/Ecosystem
| 2 |  | Econ analysis | CMP Am 29 | Social analysis | SG Am 37 | SG Am 41 | Bycatch | SG Am 43 | DW10/SG44 | For-hire Limited Entry | For-Hire Am | SEDAR/SSC | FEP II | FEP II & EFH/Ecosystem
| 3 | DW10/SG44 | Econ analysis | CMP Fmwk 4/5 | Social analysis | Visioning - Recreational | SG Am 41 | Bycatch | SG Am 43 | DW10/SG44 | For-hire Limited Entry | For-Hire Am | SEDAR/SSC | FEP II | FEP II & EFH/Ecosystem
| 4 | DW10/SG44 | Econ analysis | CMP 30 | Social analysis | Visioning - Recreational | SG Am 41 | Bycatch | SG Am 43 | DW10/SG44 | For-hire Limited Entry | For-Hire Am | SEDAR/SSC | FEP II | FEP II & EFH/Ecosystem
2017 | 1 | DW10 & SG44 | Econ analysis | SGFor-HireLE & SpLobRA4 | Social analysis | Visioning - Recreational | Visioning - Commercial | Bycatch | SG AM 43 | Wreckfish ITQ Rev |  | For-Hire Am | SEDAR/SSC | FEP II | EFH/Ecosystem
| 2 |  | Econ analysis | SGFor-HireLE & SpLobRA4 | Social analysis | Visioning - Recreational | Visioning - Commercial | Bycatch | SG Am 43 | Wreckfish ITQ Rev |  | DW10/SG44 Control Rule | SEDAR/SSC | FEP II | EFH/Ecosystem
| 3 | SG Portfolio | Econ analysis | SGFor-HireLE & Cobia trans | Social analysis | Visioning - Recreational | Visioning - Commercial | Bycatch | SG Am 43 | Wreckfish ITQ Rev |  | ABC Control Rule | SEDAR/SSC | FEP II | EFH/Ecosystem
| 4 | SG 42 & for-hire | Econ analysis | Cobia transfer | Social analysis | Visioning - Recreational | Visioning - Commercial | Bycatch | SG Am 46 | Wreckfish ITQ Rev | Red Gr. ACL Framework | ABC Control Rule | SEDAR/SSC | FEP II | EFH/Ecosystem
2018 | 1 | SG 42 & for-hire | Econ analysis | Cobia transfer & Spiny Lob | Social analysis | Visioning - Recreational | Visioning - Commercial | SMP Rev & Coral/Shrimp | SG Am 46 | Wreckfish ITQ Rev | SG Am 45 | ABC Control Rule | SEDAR/SSC | SG Am 38 | EFH/Ecosystem
| 2 | SG 42 & DW 11 | Econ analysis | Cobia transfer & Spiny Lob | Social analysis | Visioning - Recreational | Visioning - Commercial | SMP Rev & Coral/Shrimp | SG Am 46 | Wreckfish ITQ Rev | SG Am 45 | ABC Control Rule | SEDAR/SSC | SG Am 38 | EFH/Ecosystem
| 3 | SG 42 & DW 11 | Econ analysis |  | Social analysis | Visioning - Recreational | Visioning - Commercial | SMP Rev & Coral/Shrimp | SG Am 46 | Wreckfish ITQ Rev | Allocation Policy | ABC Control Rule | SEDAR/SSC | SG Am 38 | EFH/Ecosystem
| 4 | SG 42 & DW 11 | Econ analysis |  | Social analysis | Vermilion Snapper | Black Sea Bass | SMP Rev & Coral/Shrimp | SG Am 46 | MRIP Revisions | Allocation Policy | ABC Control Rule | SEDAR/SSC | SG Am 38 | EFH/Ecosystem
2019 | 1 | DW Am 11 | Econ analysis |  | Social analysis | Vermilion Snapper | Black Sea Bass | Coral Activity |  | MRIP Revisions | Allocation Policy | ABC Control Rule | SEDAR/SSC |  | EFH/Ecosystem
| 2 | DW Am 11 | Econ analysis |  | Social analysis | Vermilion Snapper | Black Sea Bass | Coral Activity |  |  | Allocation Policy | Com. eLogbook | SEDAR/SSC |  | EFH/Ecosystem
| 3 | 2: Econ analysis; 4: Social analysis; 5: Vermilion Snapper; 6: Black Sea Bass; 7: Coral Activity; 11: Com. eLogbook; 12: SEDAR/SSC; 14: EFH/Ecosystem
| 4 | 2: Econ analysis; 4: Social analysis; 7: Coral Activity; 11: Com. eLogbook; 12: SEDAR/SSC; 14: EFH/Ecosystem
Current Notes:
1 | Spiny Lobster RA 4 - GMFMC Administrative Lead
2 | SG Amendment 43- red snapper
3 | Cobia Amendment to transfer management to ASMFC
4 | SG Amendment 38 - blueline tilefish - need time before starting on amendment to work with Gulf and MidAtlantic councils to determine ABC allocations by Council
5 | SG Amendment 45 - golden tilefish - assumes only change in ACL - more time needed if management changes are made
6 | SG Amendment 42 - red grouper rebuilding plan amendment
7 | For-hire Limited Entry- Whitepaper to examine use of limited entry in Snapper Grouper For-hire Fishery
8 | ABC Control Rule - generic control rule for remaining species; based on lessons learned with ABC Control Rule for SG45 & DW10
9 | SMP Rev - System Management Plan Review; the first report for Spawninng SMZs is due in 2018
10 | New assessment results for red grouper @ June 2017 Council meeting; will require Plan Am to establish rebuilding program (if needed) and change management mesures.
11 | New assessment results for black sea bass @ December 2017 Council meeting; will require Plan Am to establish rebuilding program (if needed) and change management measures.
12 | Annual Review of Snapper Grouper Visioning progress
13 | Bycatch reporting to comply with SBRM
14 | Spiny Lobster - Bully-Net and FL Process/Procedures
15 | Kari MacLauchlin will complete portfolio analysis as a contractor - completion date 3/18
Highlight indicates suggested revisions or additions.
Highlight indicates timeslots that might need to be adjusted.
Future Notes:
1 | Two amendment leads or 1 lead plus the social/economic analyses on non-lead amendments is a full load for each staff person.
2 | Need to build in some time to address new methods for analyzing impacts and for special topics that may surface.
3 | The Council could be addressing up to 10 amendments at each meeting; this is more than a full load for the Council.
4 | In general, Amendment = 4-6 quarters, Reg Amendment 3 quarters, Abbreviate Framework = 1-2 quarters
5 | Coral/Shrimp - looking at allowable fishing areas for rock shrimp & modifying the areas for golden crab.
6 | New assessment results for blueline tilefish @ June 2018 Council meeting; will require Reg Am to make these changes.
7 | New assessment results for vermilion snapper @ June 2018 meeting
8 | New assessment results for black grouper @ June 2018 meeting
9 | MRIP Revisions - TBD (Expected mid to late 2018)
10 | *In March 2017, the Council voted to suspend work on DW10 & SG44 until MRIP data are revised.
11 | DW10 includes redefining OY, modifying the recreational ACT, establishing a commercial ACT, adaptive management of sector ACLs, revising AMs, ABC Control Rule for carry-over, exceptions for prohibited gears, and removal of the Operator Card requirement
12 | SG44 includes merging SA&GOM yellowtail ABC and ACL, modifying sector allocations, adaptive management of sector ACLs, and revising Ams
13 | CMP 30 - Cobia - change fishing year for cobia - suspeneded indefinitely
14 | Spiny Lobster - Bully-Net and FL Process/Procedures
15 | Sargassum - set ABC=0