## SAFMC
| Status of South Atlantic Council Amendment Under Review (updated 6/6/17) | [7 empty] | TODAY: | 2018-02-06
SAFMC | Council |  |  |  | Amend | Prposed | Comments | Final | Regs | Days from sent to SOC
Amendment | Approval* | To NMFS | NOA Pub. | Cmts Due | Approved | Rule Pub | Due | Rule Pub | Effective | Until Regs Effective | Comments
SG Amendment 36 (Sp SMZs) | 2016-03-11 | 2016-08-30 | 2017-01-04 | 2017-03-06 | 2017-04-04 | 2017-01-18 | 2017-02-17 | 2017-06-30 | 2017-07-31 | 335 | protection for red grouper; exposes location of MPAs previously secret
SG Amendment 37 (Hogfish) | 2017-09-16 | 2016-09-23 | 2016-10-07 | 2016-12-06 | 2016-12-28 | 2016-12-16 | 2017-01-17 | 2017-07-25 | 2017-08-24 | 335 | One stock overfished/overfishing with Statutory deadline=2/17/17; continued overfishing in 2017
SG Amendment 41 (Mutton) | 2016-12-09 | 2017-02-28 | 2017-09-26 | 2017-11-27 |  | 2017-10-24 | 2017-11-27 | 2018-01-11 | 2018-02-10 | 343
CMP Amendment 26 (King Mackerel) | 2016-03-01 | 2016-07-07 | 2016-12-15 | 2017-01-30 |  | 2016-12-29 | 2017-01-30 | 2017-04-11 | 2017-05-11 | 308 | Modifies stock boundary; increases ACL for Gulf and Atlantic king mackerel. All Gulf zones had
(Joint GMFMC/SAFMC Amendment) | [10 empty] | closed (quotas met) before the final rule was posted. Gulf Western, Northern, and Southern gillnet
re-opened after the new ACLs became effective in May 2017. Gulf Western Zone had been closed
since Oct 2016; southern gillnet had closed 2/10/17.
CMP Framework 4 (Atlantic Cobia) | 2016-09-01 | 2016-10-28 |  |  |  | 2017-02-21 | 2017-03-23 | 2017-08-04 | 2017-09-05 | 312 | Rec harvest limits and commercial limits for Atlantic cobia; modified rec AMs for Atlantic cobia.
(Joint GMFMC/SAFMC Amendment) | [10 empty] | These measures would likely have resulted in a longer recretional season for 2017, but
NMFS closed the EEZ to recreational harvest of Atlantic cobia on Jan 24, 2017.
CMP Framework 5 (Permit Restrictions) | 2016-10-01 | 2016-12-02 |  |  |  | 2017-03-01 | 2017-03-30 | 2017-08-01 | 2017-08-31 | 272 | Modifies KM commercial permit restrictions to allow bag limit retention (not a high priority for SA)
(Joint GMFMC/SAFMC Amendment)
SA For-Hire Electronic Reporting Amendment | 2016-12-09 | 2017-03-03 | [7 empty] | 340 | Council requested implementation by 1/1/18; Council providing one data collection vehicle & storage
through ACCSP so minimal cost to agency to implement SA reporting requirements.
Interim Rule for Golden Tilefish | 2017-06-16 | 2017-06-27 |  |  |  | 2017-10-30 | 2017-11-14 | 2018-01-02 | 2018-01-02 | 224 | Council requested that NMFS implement interim measures to reduce overfishing of Golden
Tilefish in the South Atlantic region while the South Atlantic Council (Council) develops an
Notes: | [10 empty] | amendment to adjust fishing levels for that stock.
*Goal is to send document to Secretary of Commerce/NMFS prior to following Council meeting.
The MSA specifies a statutory deadline for reviewing plans/amendments: immediately commence review & immediately publish a Notice of Availability; 60 day comment period from day published.
The Secretary shall approve, disapprove, or partially approve a plan or amendment within 30 days of the end of the comment period. Total of 90 days.
The MSA defines "immediately" - means on or before the 5th day after the day on which a Council transmits to the Secretary a FMP, Amendment, or proposed regulation.
Regulations - immediately initiate an evaluation to determine if consistent with FMP, amendment, MSA & other applicable law; within 15 days if yes publish for 15-60 day comment period.
If no, notify Council in writing of inconsistencies and provide recommendations to fix; Final regulations published within 30 days after the end of the comment period.
There is no statutory deadline for review of Regulatory Amendments, however, the statutory deadline for regualtions above applies.

## NEFMC
| Status of New England Council Amendments/Frameworks Under Review (updated 7/05/17) | [8 empty] | TODAY: | 2018-02-06
NEFMC | Council | Preliminary | Formal |  |  | Amend | Proposed | Comments | Final | Regs | Days from sent to SOC
Amendment | Approval | Submission | Submission | NOA Pub. | Cmts Due | Approved | Rule Pub | Due | Rule Pub | Effective | Until Regs Effective | Comments
Omnibus Habitat Amendment 2 | 2015-06-16 | 2016-01-14 | [9 empty] | Modifies EFH and Habitat Management Areas. Formal submission delaed by uncertainty over 2 for 1 rules, etc.
Industry Funded Monitoring Amendment | 2017-04-20 | [10 empty] | Structure for industry funded monitoring programs and herring IFM coverage. GARFO lead om document preparation.
Groundfish Amendment 18 | 2015-04-21 | 2015-10-30 | 2016-08-12 | [7 empty] | 543
Groundfish Framework 56 | 2017-01-25 | 2017-04-13 | 2017-06-29 |  |  |  | 2017-06-22 | 2017-07-07 |  |  | 222 | Specifications for FY 2017 and other management program changes
Monkfish Framework 10 | 2016-11-15 | 2017-04-17 | 2017-05-05 |  |  |  | 2017-05-09 | 2017-05-24 | 2017-07-12 | 2017-07-12 | 68 | Specifications for FY 2017 and other management program changes
Scallop Framework 28 | 2016-11-16 | 2017-02-02 | 2017-03-08 |  |  |  | 2017-01-19 | 2017-02-07 | 2017-03-27 | 2017-03-23 | 15 | Specifications for FY 2017 and other management program changes
Skate FW 3 (Specifications 2016-2018) | 2015-12-01 | 2016-03-18 | 2016-06-03 |  |  |  | 2016-06-06 | 2016-06-21 | 2016-08-17 | 2016-08-17 | 75
Groundfish Framework 55 | 2016-01-27 | 2016-02-19 | 2016-04-04 |  |  |  | 2016-03-21 | 2016-04-05 | 2016-05-02 | 2016-05-01 | 27
Scallop Framework 27 | 2015-12-02 | 2016-01-27 | 2016-03-14 |  |  |  | 2016-02-24 | 2016-03-25 | 2016-05-04 | 2016-05-04 | 51 | First use of expedited process on scallop specifications; allows earlier publication of the Proposed Rule.
Whiting Specifications 2016-2017 | 2015-10-01 | 2015-12-03 | 2016-01-04 |  |  |  | 2016-04-07 | 2016-04-22 | 2016-06-28 | 2016-06-28 | 176
Notes:
NEFMC and GARFO use a preliminary submission to resolve document issues before formal submission
The MSA specifies a statutory deadline for reviewing plans/amendments: immediately commence review & immediately publish a Notice of Availability; 60 day comment period from day published.
The Secretary shall approve, disapprove, or partially approve a plan or amendment within 30 days of the end of the comment period. Total of 90 days.
The MSA defines "immediately" - means on or before the 5th day after the day on which a Council transmits to the Secretary a FMP, Amendment, or proposed regulation.
Regulations - immediately initiate an evaluation to determine if consistent with FMP, amendment, MSA & other applicable law; within 15 days if yes publish for 15-60 day comment period.
If no, notify Council in writing of inconsistencies and provide recommendations to fix; Final regulations published within 30 days after the end of the comment period.
There is no statutory deadline for review of Regulatory Amendments, however, the statutory deadline for regualtions above applies.
Not all NEFMC fishing years begin January 1. Whiting, skates, groundfish, monkfish begin May 1; Scallops begins April 1; herring begins January 1.,